## Work List
Exported on: 2026-10-23 10:29:54
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JHUKARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GUNA / CHANCHODA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1706008014/DP/22012034618042 — Sarvjanik Kup Nirman Kary Sarjan Ke Makan Ke Pass Gram Sagodiya | Approved | 0 | 0 | 2024-06-01
GUNA / CHANCHODA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1706008014/DP/22012034618043 — Sarvjanik Kup Nirman Kary Dhan Singh Ke Makan Ke Pass Gram Sagodiya | Approved | 0 | 0 | 2024-06-01
GUNA / CHANCHODA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1706008014/DP/22012034618044 — Sarvjanik Kup Nirman Kary Mohan Singh Bheel Ke Makan Ke Pass Gram Jhuakra | Approved | 0 | 0 | 2024-06-01
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1706008014/IC/22012034892064 — Sarvajanik koop nirman kusumpura road par gram sagodiya Jhukra | New | 0 | 0 | 2025-04-14
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1706008014/IF/22012035221759 — kapil dhaara koop nirmaan kaary jagadeesh /hajaaree bheel jhukara | Ongoing | 285510.34 | 0 | 2025-12-18
GUNA / CHANCHODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1706008014/IF/22012035503592 — Koop recharge Rodilal Sagodiya Jhukra | Approved | 25899.46 | 0 | 2025-04-14
GUNA / CHANCHODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1706008014/IF/22012035503695 — Koop recharge Kachorilal sagodiya Jhukra | Approved | 25899.46 | 0 | 2025-04-14
GUNA / CHANCHODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1706008014/IF/22012035503912 — Sarvjanik koop recharge 1 Sagodiya Jhukra | New | 0 | 0 | 2025-04-14
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1706008014/IF/22012035505328 — JGSA 2025 Khet talab Babulal/Neenakram sagodiya Jhukra | Approved | 147621.16 | 0 | 2025-04-14
GUNA / CHANCHODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1706008014/IF/22012035517111 — JGSA 2025 Well Recharge Work Mangi Lal/Gheesa Lal Jhukra | Approved | 25899.46 | 0 | 2025-04-01
GUNA / CHANCHODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1706008014/IF/22012035517117 — JGSA 2025 Well Recharge Work Rodi Lal/Hazari Lal Jhukra | Approved | 25899.46 | 0 | 2025-04-01
GUNA / CHANCHODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1706008014/IF/22012035517120 — JGSA 2025 Well Recharge Work Pappu Lal/Raghunath Jhukra | Approved | 25899.46 | 0 | 2025-04-01
GUNA / CHANCHODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1706008014/IF/22012035517125 — JGSA 2025 Well Recharge Work Ramcharan/Hazarilal Sagaudia | Approved | 25899.46 | 0 | 2025-04-01
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1706008014/IF/22012035517247 — JGSA 2025 Khet Talab Nirman kaluram /gagaram jhukra | Approved | 0 | 0 | 2025-04-01
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1706008014/IF/22012035517250 — JGSA 2025 Khet Talab Nirman udam singh / Raghunath bhil jhukra | New | 0 | 0 | 2025-04-01
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1706008014/IF/22012035517251 — JGSA 2025 Khet Talab Nirman udam singh / Raghunath bhil jhukra | Approved | 0 | 0 | 2025-04-01
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1706008014/IF/22012035517253 — JGSA 2025 Khet Talab Nirman Bharat singh /moti lal jhukri | Approved | 0 | 0 | 2025-04-01
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1706008014/IF/22012035517260 — JGSA 2025 Khet Talab Nirman pawan/amrat lal jhukri | Approved | 0 | 0 | 2025-04-01
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1706008014/IF/22012035517264 — JGSA 2025 Khet Talab Nirman Rustam /Daru jhukra | Approved | 0 | 0 | 2025-04-01
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1706008014/IF/22012035517277 — JGSA 2025 Farm pond construction papulal/ Raghunath Sagodiya | Approved | 0 | 0 | 2025-04-01
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1706008014/IF/22012035517292 — JGSA 2025 Farm pond construction Ganpat/Jagannath Harijan Sagoria | Approved | 0 | 0 | 2025-04-15
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1706008014/IF/22012035517304 — JGSA 2025 Farm Pond Construction Pappu Raghunath Jhukra | Approved | 0 | 0 | 2025-04-01
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1706008014/IF/22012035517318 — JGSA 2025 Farm Pond construction Hemraj / Madan Lal Sen Sagodia | Approved | 0 | 0 | 2025-04-01
GUNA / CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/4676791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122868054 | Ongoing | 27000 | 0 | 2024-12-22
GUNA / CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/4704834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121556773 | Ongoing | 27000 | 0 | 2025-03-10
GUNA / CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/4759033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119655703 | Ongoing | 27000 | 0 | 2025-03-10
GUNA / CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/4767279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122867357 | Ongoing | 27000 | 0 | 2025-03-10
GUNA / CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/4770694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124752323 | Ongoing | 27000 | 0 | 2025-03-10
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/4823490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120555357 | Ongoing | 27000 | 0 | 2026-02-17
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5750356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121548131 | Physically Completed | 27000 | 0 | 2025-08-30 | 2026-10-04
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5751332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123484502 | Ongoing | 27000 | 0 | 2025-11-12
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5751363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126514871 | Ongoing | 27000 | 0 | 2025-11-12
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5751398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120555738 | Ongoing | 27000 | 0 | 2025-11-12
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5751606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121658312 | Physically Completed | 23490 | 0 | 2025-11-12 | 2026-07-26
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5751630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120554992 | Physically Completed | 23490 | 0 | 2025-11-12 | 2026-07-26
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5752019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123856732 | Ongoing | 27000 | 0 | 2025-11-12
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5798821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121564653 | Ongoing | 27000 | 0 | 2025-12-04
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5798935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124073908 | Ongoing | 27000 | 0 | 2025-11-12
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5799008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124153802 | Physically Completed | 23490 | 0 | 2025-11-12 | 2026-07-26
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5799035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121658845 | Physically Completed | 23490 | 0 | 2025-11-23 | 2026-07-12
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5799057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120807219 | Ongoing | 27000 | 0 | 2025-11-12
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5799076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121561677 | Ongoing | 27000 | 0 | 2025-11-12
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5799253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120878604 | Ongoing | 27000 | 0 | 2026-01-19
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5799627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122527412 | Ongoing | 27000 | 0 | 2025-10-07
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5800000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123488123 | Ongoing | 27000 | 0 | 2025-10-07
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5800242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120819621 | Ongoing | 27000 | 0 | 2025-09-18
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5843263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120899369 | Ongoing | 27000 | 0 | 2026-02-17
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5853670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120554758 | Ongoing | 27000 | 0 | 2026-02-17
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5853695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118703661 | Ongoing | 27000 | 0 | 2026-02-17
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5853712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126635084 | Ongoing | 27000 | 0 | 2025-11-10
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5858111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118704322 | Ongoing | 27000 | 0 | 2025-11-23
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5858161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122811066 | Ongoing | 27000 | 0 | 2025-11-23
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5858162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121662659 | Physically Completed | 23490 | 0 | 2025-11-23 | 2026-08-09
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5858184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126508743 | Ongoing | 27000 | 0 | 2025-11-23
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5858210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121665377 | Ongoing | 27000 | 0 | 2025-11-23
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5858219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122786395 | Ongoing | 27000 | 0 | 2025-11-23
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5858303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121663281 | Ongoing | 27000 | 0 | 2025-11-23
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5858409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123188186 | Ongoing | 27000 | 0 | 2025-11-23
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5858509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118844637 | Ongoing | 27000 | 0 | 2025-11-23
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5858602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118845634 | Ongoing | 27000 | 0 | 2026-02-17
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5858604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121641843 | Ongoing | 27000 | 0 | 2025-11-23
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5858607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120805657 | Ongoing | 27000 | 0 | 2025-11-23
GUNA / CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5858783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125232104 | Ongoing | 27000 | 0 | 2025-11-23
GUNA / CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/5878931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123189906 | Ongoing | 27000 | 0 | 2026-05-27
GUNA / CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008014/IF/IAY/6289180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120557653 | Approved | 27000 | 0 | 2024-09-14
GUNA / CHANCHODA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1706008014/RC/22012034594430 — Navin puliya nirman karya Patel ke makan ke pas nale par | Ongoing | 996349.72 | 0 | 2021-11-20
GUNA / CHANCHODA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1706008014/WC/22012034945166 — Amritsarover panda Ji ke khet ke pass sagoriya gram Panchayat jukara | Ongoing | 2495236.75 | 0 | 2022-04-21
GUNA / CHANCHODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1706008014/WC/22012035303278 — JGSA 2025 Sarvjanik koop recharge sagodiya 1 Jhukra | Approved | 25899.46 | 0 | 2025-04-14