## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1707001059/AV/22012034571026 — Dining hall gms kena | Completed | 16093.2 | 15850 | 2021-07-10 - 2022-01-12
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1707001059/AV/22012034611214 — नवीन बाउंड्रीवॉल निर्माण हाईस्कूल केना | Closed | 0 | 0 | 2021-08-16 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1707001059/AV/22012034612192 — Bundray wall nirman high school keina | Deleted | 0 | 0 | 2021-08-16 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1707001059/DP/1063 — सडक कि‍नारे ब़क्षारोपड समुदायि‍क भवन से मानसरोवर मुख्‍य सडक | Completed | 207000 | 83236 | 2010-08-16 - 2013-12-31
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1707001059/DP/1099 — नंदनफलोउदयान कलपना/अरविनद शमा | Deleted | 136000 | 0 | 2008-07-22 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1707001059/DP/1154 — सडक कि‍नारे ब़क्षारोपण झांसी मउ रोड से बदली के कुआ की ओर केना | Completed | 294000 | 97158 | 2011-07-22 - 2014-11-10
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1707001059/DP/22012034441674 — sarwjanik koop santidham ke pass | Completed | 445000 | 383458 | 2019-02-28 - 2023-06-27
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1707001059/DP/22012034529645 — नवीन ब्रक्षारोपन कार्य गोदाम के पास केना | Completed | 394489.84 | 241490.6 | 2021-06-20 - 2025-07-30
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1707001059/DP/22012034531248 — posan batika nirman kary GMC kaina | Closed | 11674.6 | 0 | 2021-04-14 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1707001059/DP/22012034531478 — Maa ki bagiya gms kena | Completed | 18284.89 | 3088 | 2021-08-29 - 2022-12-16
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1707001059/DP/22012034531479 — Maa ki bagiya gms kena | Closed | 0 | 0 | 2021-04-14 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1707001059/DP/22012034579247 — बृक्षारोपण कार्य झांसी मऊ रोड से कैना | Ongoing | 427106.07 | 137756.77 | 2023-07-05 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1707001059/DP/niw7 — सडक किनारे व़क्षारोपण कार्य, कैना | Deleted | 486000 | 105484 | 2006-09-11 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707001059/IF/22012034331382 — कपिलधारा कूप कपूरी /रामसेवक कुशवाहा | Completed | 230000 | 200184 | 2017-04-25 - 2020-04-02
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1707001059/IF/22012034342414 — वक्षारोपड कार्य शान्तिधाम तलैया के पास | Completed | 335000 | 223264 | 2017-06-13 - 2022-06-20
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1707001059/IF/22012034351418 — ब़क्षारोपड आंगनवाडी से नदी की ओर | Completed | 335000 | 206028 | 2017-08-11 - 2022-06-20
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707001059/IF/22012034385980 — Kapildhara kup nirman | Closed | 0 | 0 | 2018-04-14 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1707001059/IF/22012034397495 — KHET TALAB NIRMAN PARSHURAM /KASHIPRASAD KUSHWAHA KENA | Completed | 28500 | 348 | 2018-06-18 - 2020-06-19
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1707001059/IF/22012034397901 — खेत तालाब निर्माण सीताराम / दीने कुशवाहा केना | Completed | 28500 | 348 | 2018-06-18 - 2020-06-19
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1707001059/IF/22012034422939 — braksha ropan work kaushal ke makan se devrakhera ki or | Completed | 335000 | 177628 | 2018-07-17 - 2022-06-22
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707001059/IF/22012034460647 — kapildhara koop nirman kuswaha | Closed | 0 | 0 | 2019-01-26 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707001059/IF/22012034460656 — kapildhara koop nirman | Closed | 0 | 0 | 2019-01-26 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707001059/IF/22012034544550 — कपिलधारा कूप निर्माण हितग्राही रामसहाय तनय बाबूलाल कुशवाहा ग्राम कैैैैना | Completed | 259724.75 | 240083.04 | 2020-05-16 - 2023-12-04
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1707001059/IF/22012034586712 — Nandan phalhodayan dharmveer kushwaha gram kaina | Completed | 135219.86 | 104136.09 | 2020-08-03 - 2024-04-15
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1707001059/IF/22012034586722 — Nandan phalhodayan nirman parsuram kushwaha gram kaina | Completed | 135219.86 | 111052.09 | 2020-08-01 - 2024-04-15
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1707001059/IF/22012034586724 — Nandan phalyodayan nirman annadi kushwaha gram kaina | Completed | 135219.86 | 112217.09 | 2020-07-26 - 2024-04-15
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1707001059/IF/22012034586727 — Nandan phalyodan nirman matadeen kumhar gram kaina | Completed | 135219.86 | 110041.09 | 2020-07-26 - 2024-04-15
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1707001059/IF/22012034588863 — Nandan phalyodan nirman harcharn kushwaha gram kaina | Completed | 135219.86 | 103555.09 | 2020-08-01 - 2024-04-15
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1707001059/IF/22012034605153 — Nandan falyodan dayaram s/o magan kushwaha gram kaina | Completed | 142431.49 | 64023.9 | 2020-09-04 - 2024-12-03
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1707001059/IF/22012034605157 — Nandan phaloudyan syamlal s/o ramdeen kushwaha gram kaina | Completed | 116265.03 | 102683.11 | 2020-09-03 - 2024-04-15
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1707001059/IF/22012034605159 — Nandan phaloudayan halke s/o lakhanlal kushwaha gram kaina | Completed | 116265.03 | 102444.11 | 2020-09-03 - 2024-04-15
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1707001059/IF/22012034605163 — Nandan phaloudyan Vrikhbhan s/o sukharam kushwaha gram kaina | Completed | 116265.03 | 73783.11 | 2020-09-03 - 2024-04-15
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1707001059/IF/22012034609183 — Nandan phaloudyan Surendra kumar kushwaha gram kena | Completed | 116265.03 | 97400.11 | 2020-09-17 - 2024-04-15
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1707001059/IF/22012034609189 — Nandan phalyaudan nirman methli kushwaha gram kaina | Completed | 116265.03 | 101805.41 | 2020-09-17 - 2024-10-16
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707001059/IF/22012034609194 — Kapil dara koop nirman anadilal kushwaha gram kaina | Completed | 259724.75 | 239776.29 | 2020-12-06 - 2024-12-28
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707001059/IF/22012034609205 — kapil dhara koop nirman harcharan kushwaha gram kaina | Completed | 259724.75 | 227878.79 | 2020-11-07 - 2023-08-14
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707001059/IF/22012034765164 — khet talab nirman tejkunvar kushwaha gram kaina | Completed | 68532.93 | 26055 | 2021-06-20 - 2022-04-25
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1707001059/IF/22012034769098 — medbhandan kary prabhoodayal kushwaha kaina | Completed | 42757.66 | 16405 | 2021-06-04 - 2021-10-20
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1707001059/IF/22012034769143 — Medbhandan kary sukhnandan kushwaha kaina | Completed | 43253.64 | 28371 | 2021-06-04 - 2021-10-20
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1707001059/IF/22012034830971 — Nandan falyodan nirman lal khan s/o bhure khan gram kaina gp tila | Completed | 117912.51 | 62145 | 2021-09-10 - 2024-11-15
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1707001059/IF/22012034830986 — Medbandhan nirman kary lal khan s/o bhure khan gram kaina | Closed | 0 | 0 | 2021-04-14 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1707001059/IF/22012035022314 — नवीन ब्रक्षरोपन कार्य हाई स्कूल केना | Physically Completed | 218969.64 | 169388.38 | 2022-10-16 - 2026-06-29
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1707001059/IF/22012035134958 — Nandan falodhan nirman brijkishor s/o parsuram kushwha gp kena | Physically Completed | 133212.69 | 120056.24 | 2023-08-21 - 2026-06-24
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1707001059/IF/22012035137951 — Nandan falodhan nirman brijkishor /parsuram kushwaha gp kena | Closed | 0 | 0 | 2023-04-16 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1707001059/IF/22012035182229 — nandan falodhan nirman dwarka prasad /ramdeen kushwaha gp kaina | Physically Completed | 133212.69 | 114465.74 | 2023-12-29 - 2026-06-24
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1707001059/IF/22012035236860 — nandan falodhan nirman ramgopal /kurre kushwaha gp kena | Physically Completed | 145050.83 | 87695.13 | 2024-07-25 - 2026-06-24
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1707001059/IF/22012035362718 — JGSA Recharge pit kapil dhara koop Anandi Lal / Dasi kushwaha gram kena 1707001059/if/22012034609194 | Physically Completed | 25899.46 | 21992.28 | 2025-05-09 - 2026-05-07
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1707001059/IF/22012035362886 — JGSA Recharge pit kapil dhara koop Ramsahay / babu lal kushwaha kena 1707001059/if/22012034544550 | Physically Completed | 25899.46 | 22987.81 | 2025-05-09 - 2026-05-07
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1707001059/IF/22012035362992 — JGSA Recharge pit kapil dhara koop Harcharan / ummed kushwaha 1707001059/if/22012034609205 | Physically Completed | 25899.46 | 20471.05 | 2025-05-09 - 2026-05-22
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1707001059/IF/22012035450799 — JGSA Recharge pit koop nirman Parshuram / kashiprasad Kushwaha gram kena | Physically Completed | 25899.46 | 19178.6 | 2025-05-25 - 2026-05-22
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1707001059/IF/22012035457488 — JGSA Parcolation tank nirman kallu and prakash / sarju prajapati | Approved | 25899.46 | 0 | 2025-04-14 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1707001059/IF/22012035482052 — JGSA Khet Talab nirman kallu and prakash / Sarju Prajapati kena | Ongoing | 147621.16 | 68643 | 2025-05-14 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1707001059/IF/22012035482486 — JGSA Khet Talab nirman Anandi Lal / Dashi kushwaha kena | Completed | 147621.16 | 23674.8 | 2025-05-14 - 2026-05-30
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1707001059/IF/22012035488365 — JGSA Khet Talab nirman Ramshroop / sarman Kushwaha kena | Completed | 147621.16 | 31581 | 2025-05-14 - 2026-05-30
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1707001059/IF/22012035488414 — JGSA Khet Talab nirman Ramprakash / sarman Kushwaha kena | Completed | 147621.16 | 25317 | 2025-05-14 - 2026-05-30
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1707001059/IF/22012035488513 — JGSA Recharge pit koop nirman Ramprakash / Sarman kushwaha kena | Physically Completed | 25899.46 | 21731.25 | 2025-05-16 - 2026-05-07
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1707001059/IF/22012035598484 — Ek Bagiya maa ke naam kiran kushwaha / Brajkishor kushwaha gram kena | Ongoing | 134765.98 | 261 | 2025-09-09 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707001059/IF/9993696243 — कपिलधारा कूप सुखनंन्‍दन/सुन्‍दरलाल कुशवाहा | Completed | 350000 | 349918 | 2015-12-31 - 2018-03-15
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707001059/IF/9993725459 — कपिलधारा कूप निर्माण | Deleted | 0 | 0 | 2016-04-14 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707001059/IF/9993725461 — कपिलधारा कूप निर्माण | Deleted | 0 | 0 | 2016-04-14 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1707001059/IF/9993725463 — मैडबंधान निर्माण्‍ कार्य | Deleted | 0 | 0 | 2016-04-14 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1707001059/IF/9993725466 — मैडबंधान निर्माण्‍ कार्य | Deleted | 0 | 0 | 2016-04-14 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1707001059/IF/9993725469 — मैडबंधान निर्माण्‍ कार्य | Deleted | 0 | 0 | 2016-04-14 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1707001059/IF/9993725470 — मैडबंधान निर्माण्‍ कार्य | Deleted | 0 | 0 | 2016-04-14 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1707001059/IF/9993725475 — मैडबंधान निर्माण्‍ कार्य | Deleted | 0 | 0 | 2016-04-14 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/1243705 — Construction of IAY House -IAY REG. NO. MP2346743 | Completed | 15480 | 15660 | 2018-05-28 - 2018-08-25
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/1244310 — Construction of IAY House -IAY REG. NO. MP3130904 | Completed | 15480 | 15660 | 2018-04-26 - 2019-01-02
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/1285446 — Construction of IAY House -IAY REG. NO. MP2346640 | Completed | 15480 | 15660 | 2018-05-25 - 2018-08-25
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2542182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5039844 | Completed | 17100 | 17100 | 2020-07-01 - 2020-12-07
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2548195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5325782 | Completed | 17100 | 17100 | 2020-07-03 - 2021-02-17
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2548196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5325807 | Completed | 17100 | 17100 | 2020-06-08 - 2021-01-13
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2550015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5421303 | Completed | 17100 | 17100 | 2020-07-01 - 2021-01-13
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2571350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4322386 | Completed | 17100 | 17100 | 2020-06-24 - 2020-10-22
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2571351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4322406 | Completed | 17100 | 17100 | 2020-06-24 - 2021-03-04
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/268140 — Construction of IAY House -IAY REG. NO. MP1197707 | Completed | 15030 | 15370 | 2017-02-03 - 2018-02-15
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2768092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5041653 | Completed | 17100 | 17177 | 2021-04-05 - 2022-02-05
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2768711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4976556 | Completed | 17100 | 17370 | 2021-04-05 - 2021-12-28
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2772661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5379913 | Completed | 17100 | 17177 | 2021-04-05 - 2022-02-05
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2772728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5447227 | Completed | 17100 | 17177 | 2021-04-05 - 2022-02-05
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2772901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5415628 | Completed | 17100 | 17370 | 2021-04-05 - 2022-01-27
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2774164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5504797 | Completed | 17100 | 17177 | 2021-04-05 - 2021-12-28
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2777334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5656870 | Completed | 17100 | 17177 | 2021-04-05 - 2021-12-28
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2777540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5456741 | Completed | 17100 | 17177 | 2021-04-05 - 2022-02-05
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2925152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5030654 | Completed | 17100 | 16278 | 2021-06-18 - 2022-12-19
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2939099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5278057 | Completed | 17100 | 17177 | 2021-04-06 - 2022-02-05
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2939103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5415647 | Completed | 17100 | 17370 | 2021-04-05 - 2021-12-28
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2939104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5444980 | Completed | 17100 | 17177 | 2021-04-05 - 2022-02-05
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/2939535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5301093 | Completed | 17100 | 17370 | 2021-04-05 - 2022-01-27
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/3048326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4322350 | Completed | 17370 | 16471 | 2021-06-18 - 2022-12-19
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/3715709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116047043 | Completed | 18360 | 17544 | 2022-05-27 - 2023-08-11
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/3734720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116225645 | Completed | 18360 | 18360 | 2022-05-27 - 2022-12-20
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/3740216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118131906 | Completed | 18360 | 18258 | 2022-05-27 - 2023-08-11
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/3890802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129902257 | Completed | 18360 | 18360 | 2022-05-27 - 2022-12-20
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/3890853 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129910554 | Completed | 18360 | 18156 | 2022-05-27 - 2023-03-08
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/3991955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132237338 | Completed | 18360 | 18360 | 2022-05-27 - 2022-12-20
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/4024563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144519900 | Completed | 18360 | 18360 | 2022-05-27 - 2022-12-20
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/4248125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120270057 | Completed | 18360 | 18156 | 2022-08-05 - 2023-03-08
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/4248899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120893358 | Completed | 18360 | 18156 | 2022-08-05 - 2023-08-11
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/4258733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146054463 | Completed | 18360 | 18054 | 2022-08-05 - 2023-08-11
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/4563064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116243610 | Completed | 23490 | 21258 | 2024-12-03 - 2026-03-06
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/4588526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119944586 | Completed | 23490 | 20835 | 2025-01-29 - 2026-03-06
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/4589074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121578763 | Completed | 23490 | 21672 | 2024-11-15 - 2026-03-06
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/4611922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125488067 | Completed | 23490 | 20952 | 2025-01-27 - 2026-03-06
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/4636917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131042554 | Completed | 23490 | 21672 | 2024-11-28 - 2026-03-06
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/5482856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125044780 | Ongoing | 23490 | 21663 | 2025-05-05 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/5483061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149582530 | Completed | 23490 | 22968 | 2025-05-05 - 2026-07-13
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/5484647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119415100 | Ongoing | 23490 | 23229 | 2025-05-05 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/5485808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116290044 | Completed | 23490 | 23490 | 2025-05-05 - 2026-07-13
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/5486073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120609987 | Completed | 23490 | 23490 | 2025-06-23 - 2026-07-13
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/5609203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116292508 | Ongoing | 23490 | 22968 | 2025-07-05 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/5801315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130918978 | Ongoing | 23490 | 20358 | 2025-10-10 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/5801381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131400213 | Completed | 23490 | 23229 | 2025-10-06 - 2026-05-30
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/5801424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121405217 | Ongoing | 23490 | 20097 | 2025-09-27 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/5801497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122735133 | Completed | 23490 | 23490 | 2025-09-27 - 2026-07-13
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/5801587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116279131 | Completed | 23490 | 23229 | 2025-09-27 - 2026-05-30
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/5801779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132230972 | Completed | 23490 | 23229 | 2025-09-27 - 2026-05-30
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/5801861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115925103 | Completed | 23490 | 23229 | 2025-09-27 - 2026-05-30
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/6234581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128481033 | Approved | 23490 | 0 | 2026-03-06 -
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/658788 — Construction of IAY House -IAY REG. NO. MP3093700 | Completed | 15030 | 15480 | 2017-06-06 - 2017-09-25
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/660389 — Construction of IAY House -IAY REG. NO. MP1394827 | Completed | 15030 | 15480 | 2017-06-21 - 2017-09-25
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/660595 — Construction of IAY House -IAY REG. NO. MP1429250 | Completed | 15030 | 15480 | 2017-07-07 - 2017-11-28
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/668388 — Construction of IAY House -IAY REG. NO. MP2208669 | Completed | 15030 | 15480 | 2017-07-17 - 2017-11-28
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/670587 — Construction of IAY House -IAY REG. NO. MP2344800 | Completed | 15030 | 15480 | 2017-06-09 - 2017-09-25
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/671172 — Construction of IAY House -IAY REG. NO. MP2388047 | Completed | 15030 | 15480 | 2017-07-17 - 2017-10-04
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/672244 — Construction of IAY House -IAY REG. NO. MP2495479 | Completed | 15030 | 15480 | 2017-06-09 - 2017-09-25
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/678088 — Construction of IAY House -IAY REG. NO. MP3118419 | Completed | 15030 | 15480 | 2017-06-12 - 2017-09-25
NIWARI / NIWARI / KENA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707001059/IF/IAY/681896 — Construction of IAY House -IAY REG. NO. MP3659380 | Completed | 15030 | 15480 | 2017-06-09 - 2017-09-25
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707001059/LD/22012034248690 — Khel medan nirman samuday bhawan road ke pass kena | Completed | 639000 | 479292.5 | 2016-01-12 - 2017-09-04
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707001059/LD/22012034248693 — Shanti dham nirman talaiya ke pass kena | Deleted | 499000 | 0 | 2015-04-14 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707001059/LD/22012034265359 — शान्तिधाम निर्माण | Deleted | 0 | 0 | 2016-04-14 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1707001059/LD/22012034306108 — शांतिधाम निर्माण तलैया के पास कैना | Completed | 245000 | 244989 | 2017-04-04 - 2019-01-01
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1707001059/LD/22012034593882 — Amrit batika meri mati Mera Desh gram kena | Physically Completed | 55847.4 | 41010.91 | 2023-08-21 - 2026-06-24
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1707001059/LD/22012034952192 — Sudur sadak nirman samudayak bhavan se shidh baba ki or | Approved | 0 | 0 | 2025-01-25 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707001059/LD/23 — मेढ बन्‍धान कार्य (दशई/भगुवा), कैना | Completed | 23000 | 22600 | 2010-05-03 - 2010-06-15
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707001059/LD/24 — मेढ बन्‍धान कार्य (आशीष,सनद/तुलसी), कैना | Completed | 23000 | 22500 | 2010-05-10 - 2010-06-15
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707001059/LD/31 — मेड वंधान कार्य (बदली/वल्‍देव सौर),कैना | Completed | 23000 | 22500 | 2010-05-17 - 2010-06-23
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707001059/LD/5 — मेढ बन्‍धान कार्य, कैना | Deleted | 110000 | 0 | 2008-06-20 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707001059/LD/75 — मेडबंधन बीरपाल सि‍ह /मंगल सि‍ह | Completed | 23000 | 22982 | 2010-06-23 - 2011-02-07
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707001059/LD/8905 — मेडबंधन कार्य दौलतराम/दुर्जन गडरि‍या केना | Completed | 29000 | 22936 | 2011-04-24 - 2013-12-31
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707001059/LD/8906 — मेडबंधन कार्य मनमोहन,रामसहाय/बाबबूलाल कुशवाहा केना | Completed | 58000 | 28182 | 2011-06-24 - 2013-12-31
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707001059/LD/8913 — नंदनफलोउद्वान मनमोहन,रामसहाय/बाबूलाल कुशवाहा केना | Completed | 92000 | 12652 | 2011-11-19 - 2013-12-31
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/01 — सीसी रोड निर्माण, कैना | Completed | 499000 | 139420 | 2006-08-01 - 2007-03-23
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034171245 — सी सी रोड निर्माण कार्य आशाराम पाल के मकान से झुमक | Completed | 161252 | 155483.12 | 2013-06-22 - 2013-12-31
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034178491 — (पंचपरमेश्‍वर) सी सी रोड असरफ के मकान से राजाराम क | Completed | 161000 | 162087 | 2013-12-24 - 2015-09-14
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034206525 — (विधायकमद) सी सी रोड थोवन कुशवाहा के मकान से रामप् | Completed | 113000 | 110728 | 2014-02-22 - 2015-09-14
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034209638 — पंचपरमेश्‍वर सी सी रोड हरदास के मकान से देशराज के | Completed | 185000 | 179799.99 | 2014-03-04 - 2016-02-22
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034209646 — पंचपरमेश्‍वर सी सी रोड रामकुमार के मकान से असगर के | Completed | 185000 | 229594 | 2014-03-04 - 2015-09-14
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1707001059/RC/22012034211016 — (सुदूर सडक) मैनरोड कैना से रामरतन के कुआ तक | Completed | 1455000 | 6132 | 2014-03-04 - 2023-09-22
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1707001059/RC/22012034211944 — (सुदूर सडक) आगनवाडी से वदी की ओर | Completed | 834000 | 100602 | 2014-03-05 - 2023-08-29
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034298967 — 14 vitt सी सी रोड शासकीय कुआ से तिजू कुशवाहा की ओर | Completed | 70000 | 69138 | 2016-04-13 - 2017-09-25
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034298986 — 13 vitt पुलिया निर्माण देवराखेरा एवं कैना रोड पर | Completed | 90000 | 89846 | 2016-04-13 - 2016-12-12
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034303642 — सी सी रोड निर्माण कार्य | Deleted | 0 | 0 | 2016-04-14 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1707001059/RC/22012034307654 — सुदूर सडक निर्माण | Deleted | 0 | 0 | 2016-04-14 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034318903 — 14 vitt पुलिया निर्माण देवराखेरा से कैना मार्ग पर | Completed | 270000 | 269880 | 2017-01-03 - 2017-09-25
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034322538 — सी सी रोड निर्माण कार्य | Deleted | 0 | 0 | 2017-01-26 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034397445 — cc rod ompartap ke makan se roshan ke mkan tak | Completed | 531000 | 79518 | 2018-10-04 - 2019-09-25
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034397452 — cc rod jagdeesh pal ke makan se sarwajanik chabutra tak | Completed | 132000 | 18792 | 2018-10-04 - 2019-09-24
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034446434 — cc rod kallu ke makan se sobh and mahadev ke makan se ramsingh | Completed | 58000 | 57816 | 2019-02-28 - 2019-07-15
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034474843 — cc rod jhumak lal ke makan lal ke makan tak | Completed | 74000 | 74272 | 2019-08-29 - 2019-12-10
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Mitti Murram Roads for Comm / Repair and maintenance of Mitti Murram Roads for Community | Repair & maint of Road | 1707001059/RC/22012034522037 — approach road gram se samsaan ghat tak | Completed | 416579.32 | 415728 | 2020-06-24 - 2023-06-27
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Mitti Murram Roads for Comm / Repair and maintenance of Mitti Murram Roads for Community | Repair & maint of Road | 1707001059/RC/22012034522038 — sudur sadak kaina se devrakhera road tak | Deleted | 0 | 0 | 2020-01-26 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034531636 — cc road nirman and nali nirman asgar khan ke makan se mahesh kushwaha ke makan tak gram kaina | Deleted | 0 | 0 | 2020-01-26 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034533665 — CC road nirman asgar ke makan se mahesh kushwaha ke makan tak gram kaina | Completed | 54000 | 53580 | 2020-08-20 - 2020-11-26
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707001059/RC/22012034543744 — aproach road mukh sadak se devrakhera se anganwadi ki or gram kaina | Completed | 990388.54 | 845494 | 2020-12-10 - 2022-09-28
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034546730 — सी सी रोड एवं नाली लखपत के मकान से धर्मदास के मकान की ओर | Completed | 47800 | 47500 | 2020-11-11 - 2021-03-31
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034576329 — pewers nirman kary GMC kaina | Closed | 0 | 0 | 2021-04-14 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1707001059/RC/22012034585252 — approach road high school se gram panchayat kena ki or | Deleted | 0 | 0 | 2021-08-16 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707001059/RC/22012034585257 — Khet sadak main road se barjendra prajapati ke khet tak | Deleted | 0 | 0 | 2021-08-16 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707001059/RC/22012034585261 — Khet sadak mahadev kushwaha ke makan se parshuram kushwaha ke khet tak | Closed | 0 | 0 | 2021-08-16 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707001059/RC/22012034585532 — approach road nirman sidhh baba churaha se high school tak | Closed | 0 | 0 | 2021-08-16 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707001059/RC/22012034585533 — approach road nirman gram se high school tak | Closed | 0 | 0 | 2021-08-16 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707001059/RC/22012034585535 — kheth sadak mukh sadak se ramratan prajapati ke kheth tak gram kaina | Closed | 0 | 0 | 2021-08-16 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/22012034594151 — सी सी रोड एवं नाली निर्माण अच्‍छेलाल पाल के मकान से अंगद रामसेवक लक्ष्‍मीनारायण के मकान तक | Ongoing | 121000 | 5404 | 2021-11-12 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1707001059/RC/7881 — GSB Road Nirman Kaina to Pajanpura | Completed | 1847000 | 541176 | 2007-05-31 - 2016-06-21
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707001059/RC/7918 — सी सी रोड निर्माण, कैना | Deleted | 499000 | 397996 | 2009-02-11 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707001059/RC/7928 — मिटटी मुरम कार्य, अग्रवाल, कैना | Deleted | 389000 | 70000 | 2009-05-01 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707001059/RC/7999 — डल्‍लू वी एम रोड ि‍नर्माण | Deleted | 472000 | 0 | 2007-05-25 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/81497 — सीसीरोड निर्माण काशीराम के मकान से माशा तक | Completed | 498000 | 161160 | 2012-05-01 - 2013-12-31
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/8156 — सीसीरोड निर्माण कारसदेव के स्‍थान से दयाराम पाल के मकान तक | Completed | 165000 | 50808 | 2012-12-02 - 2013-03-31
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707001059/RC/a-077 — ि‍मटटी मुरम ि‍नमार्ण कार्य कैना | Completed | 362000 | 92174 | 2007-04-13 - 2007-06-30
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707001059/RC/a-70 — सीसीरोड निर्माण कैना2 | Completed | 499000 | 164100 | 2006-09-11 - 2007-03-23
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034255773 — (मर्यादा) शौचालय चन्‍दभान/विलास कुशवाहा | Deleted | 5400 | 0 | 2014-07-30 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034255776 — (मर्यादा) शौचालय कैलाश/धनीराम पाल | Deleted | 5400 | 0 | 2014-07-30 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034255782 — (मर्यादा) शौचालय दिलीपचन्‍द/प्रभुदयाल | Completed | 5400 | 4570 | 2014-10-21 - 2015-08-05
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034255864 — (मर्यादा) शौचालय कासिम/भ्‍ाुल्‍लू खॉ | Completed | 5400 | 4640 | 2014-10-21 - 2015-08-05
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034255867 — (मर्यादा) शौचालय मातादीन/हल्‍के कुम्‍हार | Completed | 5400 | 2983 | 2014-10-21 - 2015-08-06
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034255870 — (मर्यादा) शौचालय ब़षभान/गोकल पाल | Deleted | 5400 | 0 | 2014-07-30 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034255875 — ((मर्यादा) शौचालय देवेन्‍द्र/शालिकराम शर्मा | Completed | 5400 | 3140 | 2014-10-21 - 2015-08-06
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034255877 — (मर्यादा) शौचालय संतराम/कल्‍यान पाल | Deleted | 5400 | 0 | 2014-07-30 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034255878 — (मर्यादा) सुखनंन्‍दन/सुन्‍दर कुशवाहा | Completed | 5400 | 4640 | 2014-10-21 - 2015-08-05
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034255880 — (मर्यादा) शौचालय ब़षभान/उम्‍मेद कुशवाहा | Completed | 5400 | 4640 | 2014-10-21 - 2015-08-05
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034255881 — (मर्यादा) शौचालय अंगद/आशाराम पाल | Deleted | 5400 | 0 | 2014-07-30 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034278217 — [मर्यादा] शौचालय रामशहाय/बाबूलाल | Deleted | 5400 | 0 | 2014-08-15 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034278218 — [मर्यादा] शौचालय हरचरन/जानकी | Deleted | 5400 | 0 | 2014-10-25 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034278220 — [मर्यादा] शौचालय सीताराम/दीने | Deleted | 5400 | 0 | 2014-08-15 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034278222 — [मर्यादा] शौचालय अशोक/दायराम | Deleted | 5400 | 0 | 2014-08-15 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034278223 — [मर्यादा] शौचालय प्रकाश/चपट्टू बढई | Deleted | 5400 | 0 | 2014-08-15 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034278225 — [मर्यादा] शौचालय दीनदयाल/छन्दी कुशवाहा | Deleted | 5400 | 0 | 2014-08-15 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034278227 — [मर्यादा] शौचालय गनेश/परमानन्द कुशवाहा | Deleted | 5400 | 0 | 2014-08-15 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034278229 — [मर्यादा] शौचालय रामकुमार /सुनू कुशवाहा | Deleted | 5400 | 0 | 2014-10-21 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034278378 — मर्यादा] शौचालय भागीरथ/बिलाशी | Deleted | 5400 | 0 | 2014-08-15 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034278379 — [मर्यादा ] शोचलाय चिंतमन/मुन्नालाल | Deleted | 5400 | 0 | 2014-08-15 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707001059/RS/22012034278380 — [मर्यादा] शोचलाय मोहन/देशराज | Deleted | 5400 | 0 | 2014-08-15 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1707001059/RS/22012034494579 — Nadep tanka lakhpatram kr makan ke pass gram kaina | Completed | 12412.41 | 380 | 2020-09-10 - 2022-01-05
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1707001059/RS/22012034494580 — Nadep tanka ashish prajapati ke makan ke pass gram kaina | Completed | 12412.41 | 11211 | 2020-09-10 - 2022-09-28
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1707001059/RS/22012034494582 — Nadep tanka ramesh joshi ke makan ke pass gram kaina | Completed | 12412.41 | 11211 | 2020-09-10 - 2022-09-28
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1707001059/RS/22012034494583 — Nadep tanka puliya ke pass gram kaina | Completed | 12412.41 | 11211 | 2020-09-10 - 2022-09-28
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707001059/RS/22012034500154 — नाली निर्माण कार्य प्रकाश के मकान से स्कूल तक केना | Completed | 15000 | 15299 | 2020-11-11 - 2021-06-30
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707001059/RS/22012034608236 — नाली निर्माण कार्य लखपत के मकान से प्‍यारेलाला के मकान एवं थोवन के मकान से दयाराम के मकान तक | Ongoing | 82000 | 17370 | 2021-11-13 -
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707001059/RS/22012034608244 — नाली निर्माण कार्य आशीष प्रजापति के मकान से सुआरा नाला की ओर | Completed | 70800 | 69947 | 2021-11-12 - 2022-10-09
NIWARI / NIWARI / KENA | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707001059/RS/22012034676963 — Nali nirman mahesh ke makan se Guljari ke makan tak and government ke handpump tak | Closed | 0 | 0 | 2022-08-16 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/02 — स्‍टाप डेम निर्माण रावली नाला | Completed | 432000 | 530297 | 2006-05-02 - 2007-03-23
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034464225 — chekdem nirman suaara nala | Deleted | 0 | 0 | 2019-04-14 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034464226 — chekdem nirman rawli nala | Deleted | 0 | 0 | 2019-04-14 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034548067 — check dam nirman suaara nala kaina | Deleted | 0 | 0 | 2020-01-26 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034558987 — 15 nag loose bolder check dam nirman rawali nala kena | Physically Completed | 186237.44 | 1710 | 2020-06-24 - 2022-02-07
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034578318 — Naveen chek dem nirman suanara nala jayram kushwaha ke khet ke pass gram kaina | Completed | 740974.56 | 737720 | 2020-10-13 - 2021-02-17
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034623374 — Naveen check dem ghanshyam ke khet ke pass sunvara nala kaina | Closed | 0 | 0 | 2021-01-21 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034623376 — jeenodar staf dam pasuram ke khet ke pass pakhi nala kaina | Closed | 0 | 0 | 2021-01-21 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034623379 — jeenodar check dam desraj ke khet ke pass pakhi nala kaina | Closed | 0 | 0 | 2021-01-21 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034646212 — Naveen check dem ghanshyam ke khet ke pass sunvara nala kaina | Completed | 694632.7 | 680432.83 | 2021-04-24 - 2021-08-09
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1707001059/WC/22012034710062 — CTR roop water harvesting anganwadi kena | Completed | 33204.5 | 32762.95 | 2021-05-22 - 2022-09-28
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1707001059/WC/22012034710069 — CTR roop water harvesting panchayat bhawan kena | Completed | 48365.5 | 48082 | 2021-05-22 - 2022-09-28
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034832159 — Naveen check dam nirman pyarelal kushwaha ke kheth ke pass sunara nala | Closed | 0 | 0 | 2021-08-16 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034832160 — Naveen check dam nirman pyarelal kushwaha ke kheth ke pass sunara nala | Deleted | 0 | 0 | 2021-08-16 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034832163 — Naveen check dam nirman devkinandan kushwaha ke kheth ke pass rouli nala | Closed | 0 | 0 | 2021-08-16 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034833870 — check dam nirman sunara nala bhagirath kushwaha ke kheth ke pass gram kaina | Completed | 836058.28 | 828392.95 | 2021-11-19 - 2026-05-05
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034924859 — check dam nirman jeondhar rawali nala sobharam kushwaha ke khet ke pass gram kena | Completed | 260432.31 | 202787.96 | 2022-04-05 - 2023-06-27
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707001059/WC/22012034938560 — नवीन खेत तालाब निर्माण राजेश प्रजापति ग्राम केना | Closed | 0 | 0 | 2022-03-08 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034966203 — Check dam nirman jeebondhar suara nala kalpana sharma ke khet pass gram kena | Closed | 0 | 0 | 2022-04-14 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012034966306 — Check dem nirman jidodhar dyaram pal ke khet ke pas rawali nala gram kena | Closed | 0 | 0 | 2022-04-14 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012035004168 — jeenodhar check dam nirman kalpana sharma ke khet ke pass sunara nala gram kaina | Closed | 0 | 0 | 2022-08-16 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1707001059/WC/22012035143129 — Parkoleshan tank nirman shanti dham ke pass kena | Closed | 0 | 0 | 2023-10-02 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707001059/WC/22012035144782 — parcolation tank nirman shantidham ke pass gp kena | Closed | 391818.99 | 0 | 2023-10-02 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707001059/WC/22012035165950 — परकोलेशन टैक निर्माण कार्य | New | 0 | 0 | 2024-01-25 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012035177388 — naveen checkdam nirman rouli nala devkinandan ke khet ke pass gram kena | Closed | 0 | 0 | 2024-01-24 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/22012035188480 — naveen checkdam nirman ramlal ke khet ke pass panki nala gp kena | Closed | 0 | 0 | 2024-01-25 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707001059/WC/22012035245689 — Parkolation tank nirman shanti dham ke pass gram kena | Completed | 199385.06 | 122482.42 | 2025-01-28 - 2026-05-30
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1707001059/WC/22012035270829 — JGSA Recharge pit sarwjanik koop puliya ke pass kena | Approved | 0 | 0 | 2025-04-14 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1707001059/WC/22012035290985 — JGSA Recharge pit koop nirman puliya ke pass gram kena | Physically Completed | 25899.46 | 21077.04 | 2025-05-16 - 2026-06-12
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/5478 — परकोलेशन टैन्‍क निर्माण तलैयाहार, कैना | Completed | 134000 | 40200 | 2009-05-22 - 2010-05-30
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1707001059/WC/5648 — कपि‍ल धारा कूप र्नि‍माण हरकू बेबा /रतन कुशवाहा केन | Completed | 245000 | 261654 | 2011-05-07 - 2015-09-14
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1707001059/WC/5690 — कपिलधारा कूप निर्माण वीरपाल सिंह/मंगलसिंह ठाकुर के | Completed | 271000 | 270222 | 2011-11-25 - 2016-05-23
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1707001059/WC/5691 — कपिलधारा कूप निर्माण सनद,आशीष/तुलसी कुम्‍हार केना | Completed | 271000 | 274155 | 2011-11-21 - 2015-09-14
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/5823 — Stopdam cum cugabey barkola ghat Kaina | Physically Completed | 4165000 | 2276301 | 2012-01-20 - 2019-11-27
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/9993647543 — चैकडेम निर्माण रावली नाला बदली के कुआ के पास | Completed | 987000 | 292 | 2014-03-01 - 2016-07-29
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707001059/WC/9993648741 — चैकडम निर्माण सुवारा नाला रामरतन के खेत के पास कैन | Completed | 996000 | 5256 | 2014-03-04 - 2016-07-29
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1707001059/WC/niw49 — जल सम्‍भरण क्षमता कार्य, कैना | Deleted | 221000 | 40174 | 2007-11-15 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707001059/WH/22012034440040 — jeendhar chekdem nirman rawli nala | Closed | 0 | 0 | 2019-04-14 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707001059/WH/22012034440041 — jeendhar chekdem nirman rawli nala BRINDAWAN | Closed | 0 | 0 | 2019-04-14 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707001059/WH/22012034447337 — jeenodar staf dam pasuram ke khet ke pass pakhi nala kaina | Completed | 998348.44 | 995513 | 2021-05-31 - 2021-12-07
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707001059/WH/22012034447338 — jeenodar check dam desraj ke khet ke pass pakhi nala kaina | Completed | 500184.14 | 498462.5 | 2021-05-31 - 2022-09-25
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707001059/WH/5114 — चैक डेम निर्माण रावली नाला, कैना | Deleted | 499000 | 388520 | 2009-06-15 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707001059/WH/H-0059 — खेत तालाब निर्माण 10 कैना | Deleted | 134000 | 15056 | 2006-08-16 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707001059/WH/niw419 — कपिल धारा कूप निमाउ जयराम् रामचरन कैना | Deleted | 174000 | 111850 | 2008-05-12 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707001059/WH/niw420 — कपिल धारा कूप निमाउ कलपना/अरविनउ कैना | Deleted | 174000 | 94980 | 2008-03-18 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707001059/WH/niw421 — कपिल धारा कूप निमाउ सुनू /कममोउ कैना | Deleted | 174000 | 93040 | 2008-03-10 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707001059/WH/niw422 — कपिल धारा कूप निमाउ बदली/बलदेव कैना | Deleted | 174000 | 147420 | 2008-03-06 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707001059/WH/niw423 — कपिल धारा कूप निमाउ सावजनिक कूप नदी के पास कैना | Deleted | 174000 | 181550 | 2008-03-10 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707001059/WH/niw424 — कपिल धारा कूप निमाउ सावजनिक कूप सोसायटी कैना | Deleted | 174000 | 89520 | 2008-02-24 -
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707001059/WH/niw425 — कपिल धारा कूप निमाउ हरदास/दयाराम कैना | Completed | 174000 | 111154 | 2008-02-13 - 2009-06-30
NIWARI / NIWARI / KENA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707001059/WH/niw426 — कपिल धारा कूप निमाउ सकूर खां/बाबूखां कैना | Deleted | 174000 | 81220 | 2008-02-13 -