## Work List
Exported on: 2026-10-25 09:54:13
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: RAMGARH
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
TIKAMGARH / JATARA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Nursery Raising / Raising of Nursery for Community | Nursery Development | 1707003078/DP/22012034236385 — फार्म पोण्‍ड निर्माण नंदू/रजूआ अादिवासी | Completed | 48000 | 47094 | 2016-11-15 | 2017-07-10
TIKAMGARH / JATARA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1707003078/DP/22012034236386 — फार्म पोण्‍ड निर्माण दिलकू बेबा नथुवा अादिवाासी की भूमि पर | Completed | 48000 | 44088 | 2016-11-15 | 2017-07-10
TIKAMGARH / JATARA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1707003078/DP/22012034236387 — फार्म पोण्‍ड निर्माण घनश्‍याम आदिवासी की भूमि पर | Completed | 48000 | 45090 | 2016-11-15 | 2017-07-10
TIKAMGARH / JATARA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1707003078/DP/22012034236388 — फार्म पोण्‍ड निर्माण राजू आदिवासी की भूमि पर | Completed | 48000 | 44088 | 2016-11-15 | 2017-07-10
TIKAMGARH / JATARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1707003078/DP/80414 — आंवला व्रक्षारोपण किले की पहाडी रामगढ | Completed | 477000 | 239800 | 2010-08-06 | 2013-12-05
TIKAMGARH / JATARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1707003078/DP/80419 — आंवला व्रक्षारोपण वगाज माता की पहाडी | Completed | 477000 | 148200 | 2010-08-09 | 2013-12-05
TIKAMGARH / JATARA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1707003078/DP/80486 — आवला व्रक्षारोपण आदिवासी खिरक के पास | Completed | 311000 | 110431 | 2011-08-03 | 2013-12-05
TIKAMGARH / JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1707003078/IF/22012035230866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4799290 | Completed | 19000 | 17010 | 2024-06-19 | 2024-10-03
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/1152033 — Construction of IAY House -IAY REG. NO. MP2372476 | Completed | 15480 | 15516 | 2017-07-04 | 2018-05-21
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/1161743 — Construction of IAY House -IAY REG. NO. MP3733267 | Completed | 15480 | 14738.4 | 2017-07-04 | 2018-12-25
TIKAMGARH / JATARA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/1223716 — Construction of IAY House -IAY REG. NO. MP3021309 | Completed | 17100 | 16656 | 2018-09-07 | 2023-12-10
TIKAMGARH / JATARA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/1248970 — Construction of IAY House -IAY REG. NO. MP1393160 | Completed | 17100 | 17003.2 | 2018-08-15 | 2023-10-02
TIKAMGARH / JATARA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/1571554 — Construction of IAY House -IAY REG. NO. MP2384671 | Completed | 15480 | 14442 | 2018-08-15 | 2019-09-09
TIKAMGARH / JATARA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/1884290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1001521 | Completed | 17100 | 15396 | 2018-11-30 | 2023-11-02
TIKAMGARH / JATARA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/2278213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4717407 | Completed | 15840 | 14995.2 | 2019-08-09 | 2019-12-26
TIKAMGARH / JATARA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/2278221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4728288 | Completed | 17100 | 15184.8 | 2019-08-09 | 2020-11-13
TIKAMGARH / JATARA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/2278625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5425070 | Completed | 15840 | 15980.8 | 2019-08-09 | 2020-01-07
TIKAMGARH / JATARA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/2278659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5471003 | Completed | 17100 | 17094 | 2019-08-09 | 2024-02-05
TIKAMGARH / JATARA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/2278683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5504299 | Completed | 17100 | 16254.8 | 2019-08-09 | 2023-09-13
TIKAMGARH / JATARA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/2291696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5080927 | Completed | 15840 | 15980.8 | 2019-08-09 | 2020-01-07
TIKAMGARH / JATARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/2584632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2486719 | Completed | 17100 | 16908 | 2020-06-25 | 2024-06-24
TIKAMGARH / JATARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/2588710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5414735 | Completed | 17100 | 15960 | 2020-06-25 | 2021-01-14
TIKAMGARH / JATARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/2813237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4826385 | Completed | 17100 | 17177 | 2021-04-15 | 2022-01-25
TIKAMGARH / JATARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/2821360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4798437 | Completed | 17100 | 17177 | 2021-04-15 | 2022-04-21
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3802813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114674598 | Completed | 18360 | 17748 | 2022-06-08 | 2024-05-06
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3820456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117398848 | Completed | 18360 | 18258 | 2022-06-08 | 2023-08-31
TIKAMGARH / JATARA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3837834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125538747 | Completed | 18360 | 18227 | 2024-03-10 | 2024-11-21
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3921123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115424888 | Completed | 18360 | 18241 | 2022-06-08 | 2023-09-13
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3923642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115714812 | Completed | 18360 | 17469 | 2022-09-28 | 2024-10-05
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3923652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115717039 | Completed | 18360 | 18333 | 2022-06-08 | 2024-06-13
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3923673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115720535 | Completed | 18360 | 18168 | 2022-12-02 | 2024-07-19
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3923687 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115724399 | Completed | 18360 | 18012 | 2022-06-08 | 2024-05-06
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3923697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115726435 | Completed | 18360 | 17646 | 2022-10-28 | 2023-08-31
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3926270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115740397 | Completed | 18360 | 17136 | 2022-06-08 | 2023-12-01
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3926271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115742284 | Completed | 18360 | 18156 | 2022-09-20 | 2023-01-15
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3926292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115749869 | Completed | 18360 | 18241 | 2022-09-20 | 2023-08-31
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3927216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115025826 | Completed | 18360 | 18241 | 2022-12-02 | 2023-10-02
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3931116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116833761 | Completed | 18360 | 17544 | 2022-11-03 | 2023-08-18
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3931117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116833785 | Completed | 18360 | 17953 | 2022-10-28 | 2024-06-24
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3931118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116833804 | Completed | 18360 | 16830 | 2022-09-18 | 2023-07-29
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3931119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116833861 | Completed | 18360 | 16422 | 2022-06-08 | 2023-12-01
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3931320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117772736 | Completed | 18360 | 17952 | 2022-09-20 | 2023-01-15
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3931376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117793498 | Completed | 18360 | 18258 | 2022-06-09 | 2023-09-13
TIKAMGARH / JATARA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3939151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114674456 | Completed | 18360 | 18099 | 2023-09-02 | 2024-05-13
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3939152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114674692 | Completed | 18360 | 17952 | 2022-06-08 | 2024-02-18
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3939511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125512856 | Completed | 18360 | 16728 | 2022-12-17 | 2023-08-22
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3940488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119850015 | Completed | 18360 | 18241 | 2022-09-20 | 2023-08-22
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3944149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122464548 | Completed | 18360 | 18156 | 2022-06-08 | 2023-01-15
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3958438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125264105 | Completed | 18360 | 18087 | 2022-12-25 | 2024-11-14
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3969717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115416319 | Completed | 18360 | 17136 | 2022-09-07 | 2023-09-13
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3972771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116833827 | Completed | 18360 | 17527 | 2023-01-01 | 2023-08-31
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3972772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116833844 | Completed | 18360 | 18339 | 2022-06-08 | 2024-06-24
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3979993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115728298 | Completed | 18360 | 17646 | 2022-06-08 | 2023-08-22
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3980069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115749898 | Completed | 18360 | 16728 | 2022-09-18 | 2023-08-31
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3981369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122062432 | Completed | 18360 | 18156 | 2022-09-18 | 2023-08-31
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3981773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117397785 | Completed | 18360 | 17952 | 2022-06-08 | 2023-11-02
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3981785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117402778 | Completed | 18360 | 17958 | 2022-09-22 | 2024-04-30
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3981798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117405569 | Completed | 18360 | 17136 | 2022-09-27 | 2023-07-29
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3982695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119077178 | Completed | 18360 | 17646 | 2022-09-27 | 2023-09-13
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3985772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125091415 | Completed | 18360 | 18020 | 2022-09-20 | 2023-08-31
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3989942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125051540 | Completed | 18360 | 16932 | 2022-09-20 | 2023-08-31
TIKAMGARH / JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/3989947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125051947 | Completed | 18360 | 16932 | 2022-12-13 | 2023-12-01
TIKAMGARH / JATARA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/430185 — Construction of IAY House -IAY REG. NO. MP1395556 | Completed | 17100 | 12528 | 2018-09-04 | 2024-10-24
TIKAMGARH / JATARA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/459948 — Construction of IAY House -IAY REG. NO. MP1689756 | Completed | 15030 | 15444 | 2017-02-04 | 2018-09-21
TIKAMGARH / JATARA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/576181 — Construction of IAY House -IAY REG. NO. MP1387026 | Completed | 15030 | 15360 | 2017-02-03 | 2018-05-21
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/662630 — Construction of IAY House -IAY REG. NO. MP1689731 | Completed | 15030 | 15390 | 2017-07-04 | 2018-09-04
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/662886 — Construction of IAY House -IAY REG. NO. MP1727906 | Completed | 15030 | 15492 | 2017-07-04 | 2018-11-13
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/668256 — Construction of IAY House -IAY REG. NO. MP2199169 | Completed | 15030 | 15576 | 2017-07-04 | 2018-09-04
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/668684 — Construction of IAY House -IAY REG. NO. MP2227215 | Completed | 15030 | 15480 | 2017-07-04 | 2018-04-01
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/670570 — Construction of IAY House -IAY REG. NO. MP2344359 | Completed | 15030 | 15612 | 2017-07-04 | 2018-11-13
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/672134 — Construction of IAY House -IAY REG. NO. MP2482921 | Completed | 15030 | 15698.4 | 2017-07-04 | 2018-05-21
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/672701 — Construction of IAY House -IAY REG. NO. MP2525412 | Completed | 15030 | 14932.8 | 2017-07-04 | 2018-09-10
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/676662 — Construction of IAY House -IAY REG. NO. MP2960629 | Completed | 15030 | 15504 | 2017-07-04 | 2018-09-04
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/676916 — Construction of IAY House -IAY REG. NO. MP2997490 | Completed | 15030 | 15402 | 2017-07-04 | 2018-09-04
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/676920 — Construction of IAY House -IAY REG. NO. MP2997540 | Completed | 15030 | 15564 | 2017-07-04 | 2018-11-13
TIKAMGARH / JATARA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/678630 — Construction of IAY House -IAY REG. NO. MP3196373 | Completed | 15030 | 15973.2 | 2018-04-26 | 2018-11-19
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/678968 — Construction of IAY House -IAY REG. NO. MP3242944 | Completed | 15030 | 15458 | 2017-07-04 | 2019-09-24
TIKAMGARH / JATARA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/679180 — Construction of IAY House -IAY REG. NO. MP3298992 | Completed | 15030 | 15660 | 2018-04-26 | 2018-09-08
TIKAMGARH / JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003078/IF/IAY/683236 — Construction of IAY House -IAY REG. NO. MP3935275 | Completed | 15030 | 15540 | 2017-07-04 | 2018-08-01
TIKAMGARH / JATARA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707003078/LD/25 — शांति धाम निर्माण रामगढ | Completed | 464000 | 442609 | 2012-12-01 | 2016-01-21
TIKAMGARH / JATARA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/22012034177291 — सी सी रोड एवं नाली आदिवासीकूप से प्रधानमंत्री सडक | Completed | 89100 | 83480 | 2013-08-02 | 2016-02-05
TIKAMGARH / JATARA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/22012034177294 — सी सी रोड एवं नाली प्रीतम के मकान से मुददी के मकान | Completed | 89100 | 90646 | 2013-08-02 | 2016-02-05
TIKAMGARH / JATARA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/22012034200149 — सी सी रोड एवं नाली गौशाला से बगाज माता तक | Completed | 165000 | 38988 | 2014-01-24 | 2016-09-03
TIKAMGARH / JATARA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1707003078/RC/22012034220224 — पुलिया सह एप्रोच निर्माण गौशाला से देवी जी तक | Completed | 994000 | 589324 | 2014-06-13 | 2016-09-03
TIKAMGARH / JATARA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/22012034288170 — C.C.ROAD HARDAS DHEEMAR KE MAKAN SE CHIPAN GHAT TAK | Completed | 192000 | 24804 | 2015-11-03 | 2016-02-02
TIKAMGARH / JATARA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1707003078/RC/22012034288173 — KHET SADAK BASURYANA MUHALLA SE KACHIYA GHAT TAK | Completed | 1432000 | 382206.7 | 2015-11-03 | 2018-09-07
TIKAMGARH / JATARA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/22012034519105 — सीसी रोड निर्माण सह नाली‍ निर्माण अडकू आदिवासी के मकान से सीताराम वंशकार के मकान तक | Completed | 41000 | 40128 | 2020-02-26 | 2020-04-01
TIKAMGARH / JATARA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707003078/RC/22012034571455 — एप्रोच रोड निर्माण कार्य कारसदेव से जाट बाबा हार तक | Completed | 1468097.46 | 1461862 | 2021-07-17 | 2022-08-02
TIKAMGARH / JATARA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/22012034629927 — सी सी रोड सह नाली निर्माण कार्य मुख्‍य सड़क से माता मंदिर तक | Completed | 46800 | 46189 | 2023-09-21 | 2024-02-20
TIKAMGARH / JATARA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/22012034629929 — सी सी रोड निर्माण कार्य धनी कुशवाहा के मकान से गेबू पाल के मकान तक | Completed | 45000 | 44200 | 2023-08-22 | 2023-11-02
TIKAMGARH / JATARA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/86208 — पुलिया निर्माण रामगढ 2 | Completed | 128000 | 128240 | 2009-07-01 | 2011-08-29
TIKAMGARH / JATARA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707003078/RC/86254 — मिटटी मुरम रोड नि आदिवासी खिरक से चदउआखेरा | Completed | 492000 | 423208 | 2010-05-25 | 2015-04-13
TIKAMGARH / JATARA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1707003078/RC/86272 — पुलिया निर्माण 1 रामगढ् | Completed | 144000 | 102256 | 2009-04-03 | 2011-08-29
TIKAMGARH / JATARA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707003078/RC/86273 — मिटटी मुरम रोड रामगढ से कछयाघाट नाले तक | Completed | 283000 | 138680 | 2009-04-03 | 2011-08-29
TIKAMGARH / JATARA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707003078/RC/86350 — मिटटी मुरम रोड वलखन्‍डी से चतुरकारी मार्ग तक | Completed | 253000 | 237483 | 2011-10-07 | 2015-04-13
TIKAMGARH / JATARA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707003078/RC/86402 — मिटटी मुरम रोउ मउवारे के कुवां से नदी तक | Completed | 253000 | 239288 | 2011-12-01 | 2015-04-13
TIKAMGARH / JATARA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707003078/RC/86403 — मिटटी मुरम रोड वलखण्‍डी से नाले तक | Completed | 297000 | 280996.1 | 2012-02-01 | 2015-04-13
TIKAMGARH / JATARA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/86446 — सीसी रोड निर्माण भग्‍गू पाल के मकान से हरिया बसोर तक | Completed | 234000 | 50888 | 2012-05-01 | 2013-08-06
TIKAMGARH / JATARA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/86447 — सीसी रोड निर्माण रामेश्‍वर के मकान से किशन के मकान तक | Completed | 234000 | 50888 | 2012-05-08 | 2013-08-06
TIKAMGARH / JATARA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/86512 — सीमेंट कांक्रीट रोड एवं नाली हरिया के मकान से महुआ | Completed | 270000 | 71097 | 2012-11-01 | 2013-12-05
TIKAMGARH / JATARA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/86647 — सी सी रोड खरकुआ कूप से हरिया ढीमर के मकान तक रामगढ | Completed | 89100 | 81210 | 2013-01-01 | 2016-02-05
TIKAMGARH / JATARA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/950 — सी सी रोड निर्माण ग्राम पंचायत रामगढ | Completed | 484000 | 370350 | 2006-07-15 | 2023-07-12
TIKAMGARH / JATARA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003078/RC/952 — सी सी रोड निर्माण ग्राम पंचायत रामगढ | Completed | 492000 | 401228 | 2006-08-17 | 2023-07-12
TIKAMGARH / JATARA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707003078/RC/JTR-715 — मिटटी मुरम मार्ग रामगढ | Completed | 490000 | 234318 | 2007-04-09 | 2008-07-15
TIKAMGARH / JATARA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707003078/RC/JTR-723 — मिटटी मुरम रोड कारसदेव से भडराघाट | Completed | 458000 | 276126 | 2008-05-10 | 2011-08-29
TIKAMGARH / JATARA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707003078/RS/22012034686307 — नाली निर्माण कार्य पुल से शंकर जी मंदिर तक | Completed | 39750 | 39627 | 2023-07-11 | 2023-10-02
TIKAMGARH / JATARA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707003078/RS/22012034690535 — नाली निर्माण कार्य मंजी पाल के मकान से गोपी पाल के मकान तक | Completed | 39700 | 39338 | 2023-08-22 | 2023-10-02
TIKAMGARH / JATARA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1707003078/RS/22012034699404 — नाली निर्माण धनी कुशवाहा के मकान से गेबू पाल के मकान तक | Completed | 50000 | 47515 | 2023-08-14 | 2024-02-08
TIKAMGARH / JATARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707003078/RS/22012035129673 — नाली निर्माण कार्य पडुवा वाले मकान से धनश्याम रैकवार के मकान तक | Completed | 66000 | 65862.32 | 2025-01-13 | 2025-06-03
TIKAMGARH / JATARA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707003078/RS/38592 — रमश/ सरमन विश्‍वकर्मा शौचालय निर्माणस मर्यादा | Completed | 4400 | 2628 | 2013-07-05 | 2016-01-19
TIKAMGARH / JATARA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707003078/RS/38597 — हरिराम/ तुलसीदास कुशवाहा शौचालय निर्माणस मर्यादा | Completed | 4400 | 1168 | 2013-07-05 | 2016-01-19
TIKAMGARH / JATARA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707003078/RS/38621 — सुंदर/ शिवशंकर नापित शौचालय निर्माण मर्यादा | Completed | 4400 | 2628 | 2013-07-05 | 2016-01-19
TIKAMGARH / JATARA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707003078/RS/38625 — भूपेंद्र सिंह/ मोहन सिंह शौचालय निर्माण मर्यादा | Completed | 4400 | 2628 | 2013-07-12 | 2016-01-19
TIKAMGARH / JATARA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1707003078/RS/38632 — रामकिशन/ रामभरोसे नापित शौचालय निर्माण मर्यादा | Completed | 4400 | 2628 | 2013-07-12 | 2016-01-19
TIKAMGARH / JATARA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Feeder Channel / Construction of Feeder Canal for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1707003078/WC/100012 — नवीन तालाब निर्माण ओंदी की नरिया रामगढ | Completed | 451000 | 443704 | 2010-04-01 | 2011-08-29
TIKAMGARH / JATARA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Feeder Channel / Construction of Feeder Canal for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1707003078/WC/100514 — नवीन तालाब निर्माण रामगढ | Completed | 463000 | 460853 | 2011-11-01 | 2016-09-03
TIKAMGARH / JATARA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/100682 — नवीन कूप छिदामी/अर्जुन सौरं रामगढ | Completed | 251000 | 227900 | 2011-12-13 | 2016-02-05
TIKAMGARH / JATARA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003078/WC/100683 — नवीन कूप भूरीवाई/मुनीम सौर रामगढ | Completed | 251000 | 57258 | 2011-12-13 | 2021-02-19
TIKAMGARH / JATARA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003078/WC/100684 — नवीन कूप झददी, नथुआ सौर रामगढ | Completed | 251000 | 21960 | 2011-12-13 | 2016-09-03
TIKAMGARH / JATARA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003078/WC/100686 — नवीन कूप श्‍याम/मिम्‍मा गनपत/श्‍याम सौर | Completed | 251000 | 240677 | 2011-12-13 | 2015-04-13
TIKAMGARH / JATARA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/100833 — नवीन तालाब आदिवासी खिरक के पास | Completed | 490000 | 423988 | 2012-02-01 | 2016-09-03
TIKAMGARH / JATARA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/101275 — नवीन तालाब निर्माण रामगढ प्रथम | Completed | 497000 | 481828 | 2013-02-01 | 2016-09-03
TIKAMGARH / JATARA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/101276 — नवीन तालाब निर्माण द्वितीय | Completed | 497000 | 491330 | 2013-02-01 | 2016-03-29
TIKAMGARH / JATARA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/22012034296812 — नवीन तालाव निर्माण पहाडी हार | Completed | 1494000 | 1482584 | 2016-06-18 | 2018-11-27
TIKAMGARH / JATARA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003078/WC/22012034329173 — तालाब सुदृढीकरण बलखंडी तालाब रामगढ | Completed | 834000 | 828700.76 | 2017-06-03 | 2018-07-20
TIKAMGARH / JATARA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003078/WC/22012034441236 — नवीन तलब निर्माण केतबारा नाला के ऊपर रामगढ | Completed | 1179000 | 1174352 | 2019-03-04 | 2020-03-31
TIKAMGARH / JATARA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003078/WC/22012034446223 — नवीन तालाब निर्माण मडी हार रामगढ | Completed | 1304000 | 1278862.82 | 2019-03-08 | 2019-11-01
TIKAMGARH / JATARA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/22012034542203 — Naveen Talab Nirman Puliya Ke Pass | Completed | 1229060.84 | 1236560 | 2020-05-28 | 2021-11-11
TIKAMGARH / JATARA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/22012034546986 — Naveen Talab Nirman Mathra Dhimar Ki Jamin Ke Pass | Completed | 1233353.84 | 1230660 | 2020-06-04 | 2026-05-20
TIKAMGARH / JATARA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/22012034558566 — RFR परकुलेशन टेंक मडियन घाट के पास | Completed | 901232.17 | 895240 | 2020-06-22 | 2021-02-07
TIKAMGARH / JATARA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003078/WC/22012034634954 — स्टापडेम निर्माण मरघटयाऊ नरिया कैलाश की भूमि के पास | Completed | 1448988.67 | 1412946 | 2021-04-29 | 2024-02-20
TIKAMGARH / JATARA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/22012034664109 — CTR मेडबंधान निर्माण कार्य सरजू बाई कि भूमी पर | Completed | 28924.94 | 23160 | 2021-06-07 | 2024-01-24
TIKAMGARH / JATARA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/22012034664141 — CTR मेडबंधान निर्माण कार्य कैलाश / गुलाबी नामदेव कि भूमी पर | Completed | 28924.94 | 23160 | 2021-06-07 | 2024-01-24
TIKAMGARH / JATARA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/22012034664144 — CTR मेडबंधान निर्माण कार्य हरदास रैकवार कि भूमी पर | Completed | 28924.94 | 23160 | 2021-06-07 | 2024-01-24
TIKAMGARH / JATARA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/22012034664168 — CTR मेडबंधान निर्माण कार्य प्रेमनारायन / सुनू कि भूमी पर | Completed | 28924.94 | 27792 | 2021-06-07 | 2021-07-19
TIKAMGARH / JATARA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/22012034664177 — CTR मेडबंधान निर्माण कार्य बबलू / जस्सू रैकवारकि भूमी पर | Completed | 28924.94 | 20844 | 2021-06-07 | 2024-01-24
TIKAMGARH / JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/22012035033269 — डग आउट पोड निर्माण कार्य किले की पहाड़ी के पास | Completed | 498772.67 | 465746 | 2023-10-05 | 2024-10-25
TIKAMGARH / JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair and maintenance of Mini Percolation Tank for Community | Repair & maint of Percolation Tank | 1707003078/WC/22012035033468 — डग आउट पोंड निर्माण मंगल सिंह के हार के पास रामगड | Completed | 498772.67 | 478428 | 2023-09-28 | 2024-10-25
TIKAMGARH / JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003078/WC/22012035120960 — WC/डग आउट पोंड रक्खू पाल के हार के पास रामगढ | Completed | 484310.81 | 462145.26 | 2023-10-06 | 2026-02-03
TIKAMGARH / JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003078/WC/22012035120980 — WC/डगआउट पोंडनिर्माण कार्य रामेश्वर रायके कुआँ के पास रामगढ | Completed | 484310.81 | 433674 | 2023-10-06 | 2024-10-25
TIKAMGARH / JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003078/WC/22012035121003 — WC/तालाब निर्माण कार्य विष्णुघोष के हार के पास रामगढ | Completed | 1156272.83 | 1069179 | 2024-01-28 | 2025-11-07
TIKAMGARH / JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/22012035156568 — डग आउट पोंड निर्माण कार्य सुडाहार | Completed | 490176.87 | 462547.5 | 2024-03-14 | 2026-02-03
TIKAMGARH / JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/22012035156570 — dag out pond nirman kary harishchandra ray ke khet paas | Completed | 490176.87 | 463793.52 | 2024-03-14 | 2026-02-03
TIKAMGARH / JATARA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003078/WC/99853 — चैक डेम निर्माण रामगढ | Completed | 451000 | 455230 | 2009-06-24 | 2016-02-05
TIKAMGARH / JATARA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003078/WC/99854 — चैक डेम निर्माण रामगढ | Completed | 467000 | 419522 | 2009-06-24 | 2016-02-05
TIKAMGARH / JATARA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/9993643404 — नवीन तालाब निर्माण किले के पास | Completed | 976000 | 626382 | 2014-01-24 | 2016-09-03
TIKAMGARH / JATARA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/9993644008 — नवीन तालाब निर्माण अडकू सौंर की भूमि के पास | Completed | 979000 | 926434 | 2014-01-31 | 2016-09-03
TIKAMGARH / JATARA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/9993644010 — नवीन तालाब निर्माण नथुवा सौंर की भूमि पर | Completed | 979000 | 620568 | 2014-01-31 | 2016-09-03
TIKAMGARH / JATARA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/9993647312 — नवीन तालाब निर्माण बलखंडी नाले पर | Completed | 1315000 | 458946 | 2014-02-28 | 2016-09-03
TIKAMGARH / JATARA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003078/WC/9993647315 — नवीन तालाब निर्माण ओंदी की नरिया रामगढ | Completed | 1219000 | 490764 | 2014-02-28 | 2016-09-03
TIKAMGARH / JATARA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003078/WC/JTR-714 — नवीन तालाब निर्माण रामगढ | Completed | 490000 | 465346 | 2007-04-09 | 2011-08-29
TIKAMGARH / JATARA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003078/WC/JTR-716 — नवीन कूप बती/बक्‍सी सौंर रामगढ | Completed | 170000 | 129328 | 2008-03-08 | 2011-08-29
TIKAMGARH / JATARA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003078/WC/JTR-717 — नवीन पेयजल कूप आदिवासी खिरक रामगढ | Completed | 170000 | 65253 | 2008-03-15 | 2012-02-04
TIKAMGARH / JATARA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003078/WC/JTR-719 — नवीन कूप प्रभू/स्‍वामी खंगार रामगढ | Completed | 170000 | 29355 | 2008-03-29 | 2011-08-29
TIKAMGARH / JATARA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003078/WC/JTR-721 — नवीन पेयजल कूप गढरयाना मु रामगढ | Completed | 170000 | 79100 | 2008-05-10 | 2012-02-04
TIKAMGARH / JATARA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003078/WC/JTR-722 — नवीन पेयजल कूप आदिवासी मुहल्‍ला रामगढ | Completed | 170000 | 5100 | 2008-05-10 | 2012-02-04
TIKAMGARH / JATARA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707003078/WH/19957968 — स्‍टापडेम वाल एवं गेट फिलिंग सुवाजा नाला रामगढ | Completed | 718000 | 411920 | 2017-05-17 | 2017-06-07
TIKAMGARH / JATARA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707003078/WH/19958011 — स्‍टाप डेम निर्माण एवं गेट फिलिंग पडरीघाट रामगढ | Completed | 527000 | 504118 | 2017-01-24 | 2017-06-27
TIKAMGARH / JATARA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003078/WH/22012034333569 — Talab jeerdoddhar karya Ghat baba ke pass ramgarh | Completed | 504000 | 494029.37 | 2018-06-15 | 2020-01-12
TIKAMGARH / JATARA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1707003078/WH/22012034439387 — Stopdem Marammat Ketwara nala | Completed | 545000 | 539773 | 2019-03-08 | 2020-03-31
TIKAMGARH / JATARA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003078/WH/22012034450678 — CTR जीर्णाद्वार कार्य स्‍टापडेम नरेंद्र सिंह परमार की भूमि के पास रामगढ | Completed | 969639.69 | 940460 | 2022-05-14 | 2024-02-20