## Work List
Exported on: 2026-09-09 09:52:21
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: DARGAYA KHURD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
TIKAMGARH / JATARA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1707003090/AV/22012034660669 — Naveen puliya Nirman karya Raju Yadav ke kuwa ke pass dargaykhurd | New | 0 | 0 | 2024-04-15
TIKAMGARH / JATARA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1707003090/AV/22012034660672 — Naveen puliya Nirman karya Raju Yadav ke kuwa ke pass dargaykhurd | New | 0 | 0 | 2024-04-15
TIKAMGARH / JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1707003090/IC/VB/22012034893393 — सार्वजनिक कूप निर्माण कार्य नई वस्ती के पीछे खस बाबा देहरे के पास दरगाय खुर्द | New | 0 | 0 | 2026-07-12
TIKAMGARH / JATARA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003090/IF/22012035169204 — Khet talab nirman Kary rampyare ahirwar ki bhumi par | Ongoing | 277360.41 | 0 | 2024-01-28
TIKAMGARH / JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003090/IF/22012035231761 — khet talab nirman kary durga prasad yadav ki bhumi par gp dargaykhurd | Approved | 0 | 0 | 2024-06-08
TIKAMGARH / JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003090/IF/22012035304699 — khet talab nirman kary Teela har gram panchayat dargaykhurd | New | 0 | 0 | 2025-01-26
TIKAMGARH / JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003090/IF/22012035304704 — khet talab nirman kary Teela har gram panchayat dargaykhurd | New | 0 | 0 | 2025-01-26
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1707003090/IF/22012035406924 — Dugwell recharge Durga. Durg in ok if] | Approved | 0 | 0 | 2025-04-15
TIKAMGARH / JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003090/IF/22012035475798 — Khet Talab nirman kary kutu ahirwar ki bhumi par Dargaykhurd | Ongoing | 147621.16 | 0 | 2025-05-10
TIKAMGARH / JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003090/IF/22012035522000 — Khet Talab Nirman Kary Pramod ahirwar ki Bhumi par dargaykhurd | Ongoing | 147621.16 | 3900 | 2025-06-07
TIKAMGARH / JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003090/IF/22012035522495 — Khet Talab Nirman Kary Gayatri chaturvedi ki bhumi par Dargaykhurd | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003090/IF/22012035552935 — Kapildhara koop nirman Ramesh ahirwar ki bhumi par | Approved | 322434.5 | 0 | 2025-04-14
TIKAMGARH / JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707003090/IF/22012035604226 — एक बगिया मॉ के नाम रामकुमारी रजक की भूमि पर दरगांयखुर्द | Approved | 0 | 0 | 2025-08-01
TIKAMGARH / JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003090/IF/IAY/5721449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144655303 | Ongoing | 27000 | 0 | 2025-08-25
TIKAMGARH / JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003090/IF/IAY/5886451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143822505 | Ongoing | 27000 | 0 | 2026-06-09
TIKAMGARH / JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003090/IF/IAY/5886680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120030333 | Ongoing | 27000 | 0 | 2026-05-22
TIKAMGARH / JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003090/IF/IAY/6358425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145182213 | Ongoing | 27000 | 0 | 2026-09-02
TIKAMGARH / JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003090/IF/IAY/6358586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125651462 | Ongoing | 27000 | 0 | 2026-09-02
TIKAMGARH / JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003090/IF/IAY/6380958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125662952 | Approved | 27000 | 0 | 2026-07-15
TIKAMGARH / JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003090/IF/IAY/6381106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127086852 | Approved | 27000 | 0 | 2026-07-15
TIKAMGARH / JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003090/IF/IAY/6381246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125661444 | Approved | 27000 | 0 | 2026-07-25
TIKAMGARH / JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1707003090/LD/22012034602017 — गौठान निर्माण कार्य मरोरा घाट मेन रोड के पास GP dargaykhurd | Ongoing | 686316.55 | 0 | 2024-03-13
TIKAMGARH / JATARA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003090/RC/22012034846781 — सीसी रोड़ निर्माण कार्य खस के देहरे के पास दरगांयखुर्द | Ongoing | 73094 | 5400 | 2026-04-10
TIKAMGARH / JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1707003090/WC/22012035074711 — नवीन तालाब निरमाण कार्य लबा लोट के पास | Ongoing | 1481393.56 | 0 | 2023-09-29
TIKAMGARH / JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003090/WC/22012035082621 — नवीन तालाब निर्माण पटेरिया हार में दरगाय खुर्द | Ongoing | 1409995.81 | 7200 | 2023-06-19
TIKAMGARH / JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003090/WC/22012035240859 — Parcoletoin tenk nirman kary jwalamukhi har second dargay khurd | Approved | 0 | 0 | 2024-10-02
TIKAMGARH / JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003090/WC/22012035251602 — parcoletion tenk nirman kary jalau har dwitiya-2 dargaykhurd | Approved | 0 | 0 | 2025-01-26
TIKAMGARH / JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003090/WC/22012035251604 — naveen talab nirman kary bharya har dargay khurd | Approved | 0 | 0 | 2024-10-02
TIKAMGARH / JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003090/WC/22012035251835 — Percoletion tenk nirman kary jwalamukhi har dwitiya 2 gram panchayat dargaykhurd | Approved | 0 | 0 | 2025-01-26
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003090/WC/22012035251836 — परकोलेशन टेन्क निरमाण कार्य डगडायलोट हार ग्राम पन्चायत दरगाय खुर्द | Ongoing | 198295.51 | 50100 | 2025-06-19
TIKAMGARH / JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003090/WC/22012035251839 — परकोलेशन टेन्क निरमाण कार्य गोरनी हार तितीया -3 ग्राम पन्चायत दरगाय खुर्द | Approved | 0 | 0 | 2025-01-26
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003090/WC/22012035251843 — परकोलेशन टेन्क निरमाण कार्य टीला हार ग्राम पन्चायत दरगाय खुर्द | Ongoing | 198295.51 | 0 | 2025-06-19
TIKAMGARH / JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003090/WC/22012035253402 — Parcoletoin tenk nirman kary bharya har dargay khurd | Approved | 198295.51 | 0 | 2024-10-02
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003090/WC/22012035259454 — Talab marammat kary raswadi talab par dargaykhurd | Ongoing | 967058.81 | 0 | 2026-02-14
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003090/WC/22012035259460 — Talab marammat kary bahrebay har ke pass Dargaykhurd | Approved | 0 | 0 | 2025-04-05
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003090/WC/22012035259462 — Stamdem marammat kary jalau har dargaykhurd | Approved | 0 | 0 | 2025-04-05
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003090/WC/22012035259465 — Stapdem marammat kary paachchhai Nale par dargaykhurd | Ongoing | 745628.74 | 24000 | 2026-02-14
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003090/WC/22012035259475 — Parcoletion tenk nirman kary Teela har dargaykhurd | Approved | 0 | 0 | 2025-04-05
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003090/WC/22012035259481 — parcoletion tenk nirman kary dugdaylot har dargaykhurd | Approved | 0 | 0 | 2025-04-05
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003090/WC/22012035259485 — Parcoletion tenk nirman kary bharya har dargaykhurd | Approved | 0 | 0 | 2025-04-05
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003090/WC/22012035259523 — Nveen Talab nirman kary bharya har dargaykhurd | Approved | 0 | 0 | 2025-04-05
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003090/WC/22012035259529 — Talab marammat kary Mor Pazza Teela har dargay khurd | Approved | 0 | 0 | 2025-04-05
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707003090/WC/22012035269566 — Parcoletion tenk Nirman Kary ladai har dargaykhurd | Approved | 198295.51 | 0 | 2025-04-14
TIKAMGARH / JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003090/WC/22012035292767 — Talab marammat Kary dugdaylot har gram Panchayat dargaykhurd | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / JATARA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1707003090/WC/VB/22012035334027 — Contoor trenches nirman kary shichai nahar ke pass dargaykhurd | Approved | 0 | 0 | 2026-07-14