## Work List
Exported on: 2026-09-04 14:49:25
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KANERA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
TIKAMGARH / PALERA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1707004022/AV/22012034563446 — खेल मैदान निर्माण शासकीय हाई स्कूल के पास ग्राम पंचायत कनेरा | Ongoing | 397917.67 | 0 | 2021-11-09
TIKAMGARH / PALERA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1707004022/DP/22012034408547 — व़क्षारोपण कार्य स्‍कूल प्रांगण ग्राम पंचायत कनेर | Ongoing | 342000 | 0 | 2018-08-04
TIKAMGARH / PALERA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1707004022/DP/22012034594382 — अमृत वाटिका (75) -वसुधा वंदन वृक्षारोपण प्राथमिक शाला बरियन खिरक ग्राम पंचायत कनेरा | Ongoing | 55847.4 | 0 | 2023-09-12
TIKAMGARH / PALERA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707004022/IF/22012034305907 — हरिशचचन्‍द्र/परसादी अहिरवार नवीन कपिल धारा कूप निर्माण कनेरा | Ongoing | 230000 | 0 | 2016-12-05
TIKAMGARH / PALERA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1707004022/IF/22012034351331 — व़क्षारोपण निर्माण पंचायत भवन से बरियापुरा तक सडक किनारे ग्राम पंचायत कनेरा | Ongoing | 335000 | 0 | 2017-07-22
TIKAMGARH / PALERA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707004022/IF/22012034470399 — कपिल धारा कूप निर्माण प्रभुदयाल यादव/गल्‍ली प्रसाद यादव गाम पंचायत कनेरा | Ongoing | 210000 | 0 | 2019-11-16
TIKAMGARH / PALERA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1707004022/IF/22012034588255 — नंदन फलउद्ध्यान उदयभान/हरीचंद यादव ग्राम पंचायात कनेरा | Ongoing | 116265.03 | 0 | 2021-01-13
TIKAMGARH / PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1707004022/IF/22012034593473 — मुर्गी पालन निर्माण तुलाराम वंशकार/दसई ग्राम पंचायत कनेरा | Ongoing | 51554.19 | 0 | 2020-12-09
TIKAMGARH / PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1707004022/IF/22012034593476 — पशु शेड निर्माण जीतेन्‍द्र यादव/कुवंरलाल ग्राम पंचायत कनेरा | Ongoing | 63531.21 | 0 | 2020-12-09
TIKAMGARH / PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1707004022/IF/22012034593480 — पशु शेड निर्माण प्रभूदयाल यादव/गल्‍ली यादव ग्राम पंचायत कनेरा | Ongoing | 63531.21 | 0 | 2020-10-08
TIKAMGARH / PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1707004022/IF/22012034593482 — पशु शेड निर्माण काशीराम कुशवाहा/मठुआ ग्राम पंचायत कनेरा | Ongoing | 63531.21 | 0 | 2020-12-09
TIKAMGARH / PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1707004022/IF/22012034593485 — पशु शेड निर्माण राकेश पाल/मोतीलाल ग्राम पंचायत कनेरा | Ongoing | 63531.21 | 0 | 2021-01-13
TIKAMGARH / PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1707004022/IF/22012034593486 — पशु शेड निर्माण jराकेश यादव/फूलसिंह ग्राम पंचायत कनेरा | Ongoing | 63531.21 | 0 | 2020-10-27
TIKAMGARH / PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1707004022/IF/22012034593489 — पशु शेड निर्माण कमलेश कुशवाहा/चन्‍द्रभान ग्राम पंचायत कनेरा | Ongoing | 63531.21 | 0 | 2020-10-27
TIKAMGARH / PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1707004022/IF/22012034593491 — पशु शेड निर्माण प्‍यारेलाल वंशकार/ भूरे वंशकार ग्राम पंचायत कनेरा | Ongoing | 63531.21 | 0 | 2020-08-25
TIKAMGARH / PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1707004022/IF/22012034593493 — पशु शेड निर्माण रामनारायण विश्‍वकर्मा/घनश्‍याम ग्राम पंचायत कनेरा | Ongoing | 63531.21 | 0 | 2020-11-26
TIKAMGARH / PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1707004022/IF/22012034593494 — पशु शेड निर्माण भैयालाल यादव/गल्‍ली यादव ग्राम पंचायत कनेरा | Ongoing | 63531.21 | 0 | 2020-12-09
TIKAMGARH / PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1707004022/IF/22012034595981 — पशु सैड निर्माण नारायणदास कुशवाहा/घनश्‍याम ग्राम पंचायत कनेरा | Ongoing | 63531.21 | 0 | 2020-10-27
TIKAMGARH / PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1707004022/IF/22012034596514 — पशु शैड निर्माण जानकी लुहार/खरगे लुहार ग्राम पंचायत कनेरा | Ongoing | 63531.21 | 0 | 2020-11-26
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1707004022/IF/22012034810055 — CTR खेत तालाब निर्माण तुलाराम /दसई बंशकार ग्राम पंचायत कनेरा | Ongoing | 111248.93 | 0 | 2025-05-25
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1707004022/IF/22012035410618 — koopriucharj pit Manoj kumar kori ke koop par | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707004022/IF/22012035426549 — khet talab nirman majboot singh yadav ke khet par g/p kanera | Ongoing | 147621.16 | 0 | 2025-05-27
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707004022/IF/22012035426822 — khet talab nirman mahesh singh yadav ke khet par g/p kanera | Ongoing | 147621.16 | 0 | 2025-05-25
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1707004022/IF/22012035499827 — JGSA डगवेल रिचार्ज पिट निर्माण गुबंदी कुशवाहा /नथू कुशवाहा ग्राम पंचायत कनेरा | Approved | 25899.46 | 0 | 2025-04-14
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707004022/IF/22012035643301 — एक बगिया मां के नाम लाडकुंवर यादव/प्रभू यादव ग्राम पंचायत कनेरा | Approved | 162980.94 | 0 | 2025-10-02
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707004022/IF/IAY/4696439 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117697368 | Physically Completed | 27000 | 0 | 2026-03-01 | 2026-09-01
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707004022/IF/IAY/5311892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117895679 | Ongoing | 27000 | 0 | 2025-04-16
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707004022/IF/IAY/5536346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117819281 | Ongoing | 27000 | 0 | 2025-09-06
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707004022/IF/IAY/5536406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117696153 | Physically Completed | 23490 | 0 | 2025-05-13 | 2026-08-02
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707004022/IF/IAY/5928226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117871220 | Approved | 27000 | 0 | 2025-02-17
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707004022/IF/IAY/6378949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117819398 | Approved | 27000 | 0 | 2026-08-12
TIKAMGARH / PALERA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1707004022/RC/22012034534501 — चंद्रभान कुशवाहा के माकन से टीला नरेनी की और | Ongoing | 1312778.42 | 0 | 2020-09-16
TIKAMGARH / PALERA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707004022/RC/22012034579170 — सीसी रोड निर्माण लालराम सूृत्रकार के मकान से रामरतन कुशवाहा के मकान तक ग्राम पंचायत कनेरा | Ongoing | 27900 | 0 | 2022-05-05
TIKAMGARH / PALERA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707004022/RC/22012034825290 — सीसी रोड निर्माण पूरन कुशवाहा के मकान से हरिराम की ओर ग्राम पंचायत कनेरा कनवर्जेन्स | Approved | 81600 | 0 | 2024-07-06
TIKAMGARH / PALERA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707004022/RS/22012034698705 — नाली निर्माणश धूराम के मकान से गंगा यादव के मकान तक ग्राम पंचायत कनेरा | Ongoing | 72142 | 0 | 2023-08-18
TIKAMGARH / PALERA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707004022/RS/22012035117894 — नाली निर्माण मय स्लैरब बरियन मोहल्ला ग्राम पंचायत कनेरा (कनवर्जेन्सव) | Ongoing | 10918 | 0 | 2023-10-09
TIKAMGARH / PALERA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1707004022/WC/22012034444649 — तालाब निर्माण इकपनिया हार के पास ग्राम पंचायत कनेरा | Ongoing | 1346000 | 0 | 2019-03-10
TIKAMGARH / PALERA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707004022/WC/22012035158377 — dug out pwaintpatre har haricharan ke ket ke pas | Ongoing | 346617.59 | 0 | 2024-03-16
TIKAMGARH / PALERA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707004022/WC/22012035158551 — Dug out pwaint patre ka har mukesh ke khet ka pas | Ongoing | 346617.59 | 0 | 2024-03-16
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1707004022/WC/22012035283968 — koopriucharj pit Harishchand ahirwar ke koop par | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / PALERA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707004022/WH/22012034389028 — स्‍टापडेम मरम्‍मत कार्य पहलवान के खेत के पास ग्राम पंचायत कनेरा | Ongoing | 185000 | 0 | 2018-07-15
TIKAMGARH / PALERA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707004022/WH/22012034445084 — तालाब जीर्णोद्धार भुजयाऊ हार में ग्राम पंचायत कनेरा | Ongoing | 966105.18 | 0 | 2022-02-08