## Work List
Exported on: 2026-10-09 00:56:19
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KHARGOOPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
TIKAMGARH / PALERA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1707004061/DP/22012034408366 — व्रक्षारोपण कार्य शाला प्रांगण मे ग्राम पंचायत खरगूपुरा | Ongoing | 342000 | 0 | 2018-07-18
TIKAMGARH / PALERA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1707004061/DP/22012034524033 — Braksha ropan nirman hanuman pahadi Aalpur | Ongoing | 116279.95 | 0 | 2021-11-09
TIKAMGARH / PALERA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1707004061/DP/22012034524037 — Nandan phalodhan nirman chaina ahirwar /chintu khargupura | Ongoing | 116279.95 | 0 | 2021-05-24
TIKAMGARH / PALERA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation of Forestry-Community / Canal Line Plantation for Community | Plantation | 1707004061/DP/22012034577062 — nandanphal mahesh ahirwar gram kankanpura | Ongoing | 133212.69 | 0 | 2023-10-09
TIKAMGARH / PALERA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1707004061/DP/22012034586441 — अमृत वाटिका (75) -वसुधा वंदन वृक्षारोपण बजरंगवली मंदिर के पास आलपुर ग्राम पंचायत खरगूपुरा | Ongoing | 55847.4 | 0 | 2023-09-03
TIKAMGARH / PALERA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707004061/IF/22012034350720 — हनुमान जी की पहाडीया पर व़क्षारोपण ग्राम पंचायत खरगूपुरा | Ongoing | 535000 | 0 | 2017-07-26
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707004061/IF/22012035276804 — कपिल धारा कूप निर्माण मनोज यादव ग्राम काकनपुरा ग्राम पंचायत खरगूपुरा | Approved | 312155.12 | 0 | 2024-04-15
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707004061/IF/22012035299147 — कपिलधारा कूप निर्माण सिमखा अहिरवार/भजन ग्राम पंचायत खरगूपुरा | Approved | 0 | 0 | 2025-01-25
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1707004061/IF/22012035413256 — परकोलेशन टैंक निर्माण कार्य बादला बाई हार मनोज यादव के खेत के पास ग्राम काकनपुरा ग्राम पंचायत खरगूपु | Ongoing | 199036.51 | 0 | 2025-05-26
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1707004061/IF/22012035439741 — डगवेल रिचार्ज पिट रामसेवक / रद्धू प्रजापति कपिल धारा कूप काकनपुरा ग्राम पंचायत खरगूपुरा | Approved | 25899.46 | 0 | 2025-04-14
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1707004061/IF/22012035439833 — खेत तालाब निर्माण कल्लू /लक्ष्मन प्रजापति ग्राम काकनपुरा ग्राम पंचायत खरगूपुरा | Ongoing | 147621.16 | 0 | 2025-05-13
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1707004061/IF/22012035561583 — डगवेल रिचार्ज पिट जशरथ/ मनगुट्टे अहिरवार कपिल धारा कूपग्राम काकनपुरा ग्राम पंचायत खरगूपुरा | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1707004061/IF/22012035561597 — डगवेल रिचार्ज पिटमोहन / घंसू बंशकार कपिल धारा कूपग्राम काकनपुरा ग्राम पंचायत खरगूपुरा | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1707004061/IF/22012035561602 — डगवेल रिचार्ज पिट रामप्रसाद / करन्जू अहिरवार कपिल धारा कूपग्राम काकनपुरा ग्राम पंचायत खरगूपुरा | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/2429235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5118144 | Approved | 27000 | 0 | 2020-04-29
TIKAMGARH / PALERA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/3920878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117320289 | Ongoing | 27000 | 0 | 2023-11-29
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4694088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115715474 | Ongoing | 27000 | 0 | 2025-01-13
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4694089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115715650 | Ongoing | 27000 | 0 | 2025-01-13
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4694099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115717651 | Ongoing | 27000 | 2100 | 2025-01-13
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4694154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115738122 | Physically Completed | 27000 | 6300 | 2025-01-13 | 2026-09-05
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4694191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115746010 | Physically Completed | 27000 | 0 | 2025-01-13 | 2026-09-05
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4697731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117502466 | Physically Completed | 27000 | 10200 | 2025-03-14 | 2026-09-05
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4697869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118068474 | Ongoing | 27000 | 6300 | 2025-03-14
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4697874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118070485 | Ongoing | 27000 | 6300 | 2025-03-14
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4700866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118063237 | Ongoing | 27000 | 14700 | 2026-05-26
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4702653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118174833 | Ongoing | 27000 | 12600 | 2026-02-08
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4712229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126177407 | Ongoing | 27000 | 0 | 2025-01-24
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4754111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118172128 | Physically Completed | 27000 | 0 | 2025-01-13 | 2026-09-05
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4755132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117502281 | Ongoing | 27000 | 0 | 2025-03-14
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4755464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118064576 | Approved | 27000 | 0 | 2024-09-28
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4759830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115016 | Ongoing | 27000 | 12000 | 2025-03-14
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4759831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115029 | Ongoing | 27000 | 0 | 2025-03-14
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4761389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120541334 | Physically Completed | 27000 | 0 | 2025-01-24 | 2026-09-05
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4778107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126408247 | Ongoing | 27000 | 10500 | 2025-04-05
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4847200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117501965 | Ongoing | 27000 | 0 | 2025-03-14
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4849384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126406098 | Ongoing | 27000 | 16200 | 2025-11-11
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/4864086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115343 | Approved | 27000 | 0 | 2024-10-07
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5248246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118172481 | Ongoing | 27000 | 14700 | 2025-12-07
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5248938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118172666 | Ongoing | 27000 | 4200 | 2025-11-11
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5253056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126184785 | Ongoing | 27000 | 0 | 2026-09-09
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5255471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118068168 | Ongoing | 27000 | 0 | 2025-11-11
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5260227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115119 | Ongoing | 27000 | 0 | 2026-09-09
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5260637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118062026 | Ongoing | 27000 | 20400 | 2026-07-10
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5262161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123127883 | Ongoing | 27000 | 14700 | 2026-02-04
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5262754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116870351 | Ongoing | 27000 | 0 | 2026-07-10
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5276590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127040428 | Ongoing | 27000 | 8700 | 2025-11-11
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5277606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115819 | Ongoing | 27000 | 1800 | 2026-09-09
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5279147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117503285 | Ongoing | 27000 | 0 | 2025-11-11
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5289707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124696837 | Ongoing | 27000 | 10500 | 2026-07-10
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5290446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115182 | Ongoing | 27000 | 0 | 2026-09-09
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5295725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118072227 | Approved | 27000 | 0 | 2025-03-09
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5296935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117503590 | Ongoing | 27000 | 0 | 2025-11-11
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5297653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118172931 | Ongoing | 27000 | 3900 | 2025-11-11
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5300223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118173091 | Ongoing | 27000 | 8400 | 2025-11-11
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5301055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118174219 | Ongoing | 27000 | 10500 | 2026-02-04
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5319070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118174040 | Ongoing | 27000 | 0 | 2025-11-11
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5329295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125643313 | Ongoing | 27000 | 22800 | 2026-02-04
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5333046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118062172 | Ongoing | 27000 | 1800 | 2025-11-11
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5336173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118062959 | Ongoing | 27000 | 7200 | 2026-02-04
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5338510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115006 | Ongoing | 27000 | 4200 | 2026-09-09
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5622600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118067227 | Physically Completed | 27000 | 10500 | 2025-11-11 | 2026-09-05
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5632093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118070858 | Approved | 27000 | 0 | 2025-05-20
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5653141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115099 | Approved | 27000 | 0 | 2025-03-08
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5653892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118067616 | Ongoing | 27000 | 0 | 2025-11-11
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5654491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115379 | Ongoing | 27000 | 16800 | 2026-08-19
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5654974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117886238 | Ongoing | 27000 | 21000 | 2026-03-23
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5709082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115256 | Approved | 27000 | 0 | 2025-06-10
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5709173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115732187 | Ongoing | 27000 | 8400 | 2026-08-19
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5730701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118073042 | Approved | 27000 | 0 | 2025-03-09
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5731126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115418 | Approved | 27000 | 0 | 2025-03-08
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5734509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118731079 | Ongoing | 27000 | 8400 | 2026-08-19
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5734674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115745840 | Ongoing | 27000 | 3900 | 2025-11-11
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5810529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123131176 | Approved | 27000 | 0 | 2025-03-09
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5828731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115069 | Ongoing | 27000 | 12600 | 2026-08-19
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5828732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115910 | Approved | 27000 | 0 | 2025-03-09
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5828877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118068923 | Approved | 27000 | 0 | 2025-03-09
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5829152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118831461 | Approved | 27000 | 0 | 2025-03-09
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5829218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120924967 | Approved | 27000 | 0 | 2025-03-18
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5829227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122412382 | Approved | 27000 | 0 | 2025-03-18
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5829292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117503080 | Ongoing | 27000 | 0 | 2025-11-11
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5829304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120541742 | Approved | 27000 | 0 | 2025-03-18
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5829462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118067542 | Ongoing | 27000 | 4200 | 2025-11-11
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5829463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117321000 | Ongoing | 27000 | 0 | 2026-03-10
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5829485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127038440 | Approved | 27000 | 0 | 2025-03-09
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5829558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125636421 | Ongoing | 27000 | 0 | 2025-11-11
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5829608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126179822 | Approved | 27000 | 0 | 2025-03-08
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5829796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126332510 | Approved | 27000 | 0 | 2025-03-09
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/5838039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116883042 | Physically Completed | 27000 | 0 | 2025-12-07 | 2026-09-05
TIKAMGARH / PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/6077540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118173871 | Ongoing | 27000 | 0 | 2026-09-09
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/6369280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118173580 | Approved | 27000 | 0 | 2025-03-18
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/6369305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124702428 | Approved | 27000 | 0 | 2025-03-09
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/6369342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118071117 | Approved | 27000 | 0 | 2025-06-10
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/6369369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117502151 | Approved | 27000 | 0 | 2025-03-09
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/6369390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118733400 | Approved | 27000 | 0 | 2025-03-08
TIKAMGARH / PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/6369416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118173744 | Approved | 27000 | 0 | 2025-06-10
TIKAMGARH / PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/6379166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120115736 | Approved | 27000 | 0 | 2025-03-09
TIKAMGARH / PALERA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1707004061/IF/IAY/660980 — Construction of IAY House -IAY REG. NO. MP1488990 | Approved | 27000 | 0 | 2017-03-10
TIKAMGARH / PALERA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1707004061/RC/22012034655610 — pempura sadak se badera har ki or sudur sadak nirman | Ongoing | 2165877.79 | 0 | 2024-12-30
TIKAMGARH / PALERA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1707004061/RS/22012034698703 — चबूतरा निर्माण ग्राम आलपुर ग्राम पंचायत खरगूपुरा | Ongoing | 12750 | 0 | 2023-04-14
TIKAMGARH / PALERA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707004061/WC/22012034391804 — MWC तालाब निर्माण श्ंकर के हार के पास ग्राम आलपुर ग्राम पंचायत खरगूपुरा | Ongoing | 1319000 | 0 | 2018-06-20
TIKAMGARH / PALERA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Gabion Spur for Community | Constr of Gabion | 1707004061/WC/22012035063705 — Parkolation tenk Nirman kacher har ke pas gram kakanpura | Ongoing | 409141.28 | 0 | 2023-06-16
TIKAMGARH / PALERA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1707004061/WC/22012035115834 — parcolation tank nirman paras badera har kankapura | Ongoing | 419678.4 | 0 | 2023-12-29
TIKAMGARH / PALERA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707004061/WC/22012035115878 — talab nirman noti toriya har allpur | Ongoing | 1466251.56 | 0 | 2023-10-08
TIKAMGARH / PALERA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1707004061/WC/22012035188604 — नवीन तालाब निर्माण जाचेर हार ग्राम आलपुर | Ongoing | 1463468.86 | 0 | 2024-05-13
TIKAMGARH / PALERA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707004061/WC/22012035256099 — परकोलेशन टैंक निर्माण कुड़रा हार ग्राम काकनपुरा ग्राम पंचायत खरगूपुरा | Approved | 453791.78 | 0 | 2025-01-25
TIKAMGARH / PALERA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707004061/WC/22012035256106 — परकोलेशन टैंक निर्माण उगड़ हार ग्राम खरगूपुरा ग्राम पंचायत खरगूपुरा | Approved | 435510.05 | 0 | 2025-01-25
TIKAMGARH / PALERA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707004061/WC/22012035256110 — परकोलेशन टैंक निर्माण आदिवासी हार के पास ग्राम खरगूपुरा ग्राम पंचायत खरगूपुरा | Approved | 0 | 0 | 2025-01-25
TIKAMGARH / PALERA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707004061/WC/22012035256111 — परकोलेशन टैंक निर्माण बादलबाई हार के पास ग्राम काकनपुरा ग्राम पंचायत खरगूपुरा | Approved | 0 | 0 | 2025-01-25
TIKAMGARH / PALERA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707004061/WC/22012035256113 — तालाब निर्माण महुआ हार के पास ग्राम खरगूपुरा ग्राम पंचायत खरगूपुरा | Approved | 0 | 0 | 2025-01-24
TIKAMGARH / PALERA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707004061/WC/22012035256114 — नवीन तालाब निर्माण कार्य तिलवा हार आलपुर ग्राम पंचायत खरगूपुरा | Approved | 0 | 0 | 2025-01-26
TIKAMGARH / PALERA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707004061/WC/22012035256115 — नवीन तालाब निर्माण कार्य उसरा हार ग्राम आलपुर ग्राम पंचायत खरगूपुरा | Approved | 0 | 0 | 2025-01-26
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1707004061/WC/22012035280360 — डगवेल रिचार्ज पिट सामुदायिक कूप जानकी अहिरवार के मकान के पास काकनपुरा ग्राम पंचायत खरगूपुरा | Approved | 25899.46 | 0 | 2025-04-14
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1707004061/WC/22012035280370 — डगवेल रिचार्ज पिट हल्काई प्रजापति का कूप काकनपुरा ग्राम पंचायत खरगूपुरा | Approved | 25899.46 | 0 | 2025-04-14
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1707004061/WC/22012035280374 — डगवेल रिचार्ज पिट चतुर अहिरवार का कूप ग्राम काकनपुरा ग्राम पंचायत खरगूपुरा | Approved | 25899.46 | 0 | 2025-04-14
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1707004061/WH/22012034943653 — चेकडेम जीर्णोद्धार बडेरा हार काकनपुरा ग्राम पंचायत खरगूपुरा | Approved | 0 | 0 | 2025-04-01
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1707004061/WH/22012034943654 — चेकडेम जीर्णोद्धार माधव अहिरवार के हार के पास खरगूपूरा | Approved | 0 | 0 | 2025-04-01
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1707004061/WH/22012034943656 — तालाब जीर्णोद्धार नरवा पठा हार काकनपुरा ग्राम पंचायत खरगूपुरा | Approved | 0 | 0 | 2025-04-01
TIKAMGARH / PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1707004061/WH/22012034943657 — फूटा तालाब जीर्णोद्धार आलपुर ग्राम पंचायत खरगूपुरा | Approved | 0 | 0 | 2025-04-01