## Work List
Exported on: 2026-10-25 07:34:15
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: TAKHA
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
TIKAMGARH / TIKAMGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1707006070/AV/22012034515759 — Boundry Ball Nirman Prathmik shala | Completed | 58000 | 40280 | 2020-08-13 | 2022-03-01
TIKAMGARH / TIKAMGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1707006070/AV/22012034543566 — BOUNDRI WALL MUKTIDHAM JHANSI ROAD KE PAAS BHAG - 1 | Completed | 60450 | 59470 | 2020-11-24 | 2021-06-30
TIKAMGARH / TIKAMGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1707006070/AV/22012034543569 — BOUNDRI WALL MUKTIDHAM JHANSI ROAD KE PAAS BHAG - 2 | Completed | 60300 | 49970 | 2020-11-24 | 2022-03-01
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1707006070/DP/22012034442568 — sarvjanak payjal koop khel maidan ke pass takha | Completed | 445000 | 399947 | 2019-03-09 | 2019-08-05
TIKAMGARH / TIKAMGARH | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1707006070/DP/92 — झांसी रोड पर सडक किनारे ब़क्षारोपण | Completed | 441000 | 91922 | 2011-07-09 | 2014-02-10
TIKAMGARH / TIKAMGARH | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707006070/IF/171 — कपिल धारा कूप निर्माण्‍ा खरगा / ठलुवा अहिरवार तखा | Completed | 212000 | 51496 | 2009-04-21 | 2016-06-30
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/22012035082236 — Construction of IAY House -IAY REG. NO. MP117815058 | Completed | 18360 | 17923 | 2023-04-24 | 2024-05-21
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/22012035082237 — Construction of IAY House -IAY REG. NO. MP117817775 | Completed | 18360 | 9436 | 2023-04-24 | 2024-05-22
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/22012035082242 — Construction of IAY House -IAY REG. NO. MP131396408 | Completed | 18360 | 10099 | 2023-04-24 | 2024-08-04
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/22012035082248 — Construction of IAY House -IAY REG. NO. MP131397014 | Completed | 18360 | 17745 | 2023-04-24 | 2025-04-21
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/22012035082252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131397055 | Completed | 18360 | 3094 | 2023-04-24 | 2024-05-01
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/22012035082255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141679632 | Completed | 18360 | 7514 | 2023-04-24 | 2024-05-01
TIKAMGARH / TIKAMGARH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707006070/IF/584 — कपिलधारा कूप निर्माण पप्‍पू/भुज्‍जा पाल | Completed | 298000 | 68492 | 2011-12-01 | 2016-08-15
TIKAMGARH / TIKAMGARH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707006070/IF/585 — कपिलधारा सिचाई कूप निर्माण किशोरी/समोसा आदिवासी | Completed | 350000 | 339867 | 2011-12-01 | 2017-12-26
TIKAMGARH / TIKAMGARH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707006070/IF/586 — कपिलधारा सिचाई कूप भगवानदास/मुन्‍ना वुनकर | Completed | 298000 | 129154 | 2011-12-29 | 2016-06-30
TIKAMGARH / TIKAMGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707006070/IF/9993693895 — Kapildhara koop Manka / parmu adiwasi | Completed | 350000 | 299741 | 2015-12-08 | 2017-12-26
TIKAMGARH / TIKAMGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707006070/IF/9993693896 — Kapildhara koop Jamuna bai / bandu pal | Completed | 350000 | 349436 | 2015-12-08 | 2017-12-26
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1204968 — Construction of IAY House -IAY REG. NO. MP2240571 | Completed | 15480 | 14616 | 2019-02-17 | 2019-06-09
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1277274 — Construction of IAY House -IAY REG. NO. MP1568275 | Completed | 15480 | 16530 | 2018-07-05 | 2018-12-19
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1277305 — Construction of IAY House -IAY REG. NO. MP1592068 | Completed | 15480 | 14442 | 2018-07-05 | 2018-11-20
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1278434 — Construction of IAY House -IAY REG. NO. MP2403851 | Completed | 15480 | 14442 | 2018-07-05 | 2018-12-07
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1316328 — Construction of IAY House -IAY REG. NO. MP1864297 | Completed | 15480 | 14616 | 2018-07-05 | 2019-03-19
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1316532 — Construction of IAY House -IAY REG. NO. MP1919023 | Completed | 15480 | 14616 | 2018-07-05 | 2019-04-12
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1317167 — Construction of IAY House -IAY REG. NO. MP2062220 | Completed | 15480 | 14798 | 2018-12-17 | 2019-07-29
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1317176 — Construction of IAY House -IAY REG. NO. MP2064899 | Completed | 15480 | 15312 | 2018-07-05 | 2019-06-09
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1318902 — Construction of IAY House -IAY REG. NO. MP2596860 | Completed | 15480 | 14616 | 2018-07-05 | 2019-02-15
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1319086 — Construction of IAY House -IAY REG. NO. MP2659453 | Completed | 15480 | 14616 | 2018-07-05 | 2019-02-15
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1319117 — Construction of IAY House -IAY REG. NO. MP2672196 | Completed | 15480 | 15138 | 2018-07-05 | 2019-06-09
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1319185 — Construction of IAY House -IAY REG. NO. MP2705287 | Completed | 15480 | 15486 | 2018-07-05 | 2019-01-13
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1342128 — Construction of IAY House -IAY REG. NO. MP3537622 | Completed | 15480 | 15660 | 2018-07-05 | 2019-01-02
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/1399645 — Construction of IAY House -IAY REG. NO. MP2297326 | Completed | 15480 | 14616 | 2018-07-05 | 2018-11-20
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/2265339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4274058 | Completed | 15840 | 15488 | 2019-10-31 | 2020-03-31
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/2265545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5044513 | Completed | 15840 | 15488 | 2019-10-31 | 2020-03-31
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/2265689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4693907 | Completed | 15840 | 15488 | 2019-10-31 | 2020-03-31
TIKAMGARH / TIKAMGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/2601111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4365607 | Completed | 17100 | 16689 | 2020-06-30 | 2022-01-10
TIKAMGARH / TIKAMGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/2602085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4596503 | Completed | 17100 | 16662 | 2020-06-30 | 2021-05-25
TIKAMGARH / TIKAMGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/2605087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5164082 | Completed | 17100 | 16891 | 2020-06-30 | 2021-12-16
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/293972 — Construction of IAY House -IAY REG. NO. MP1004968 | Completed | 15030 | 15824 | 2017-08-10 | 2018-03-08
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/294672 — Construction of IAY House -IAY REG. NO. MP1008173 | Completed | 15030 | 15362 | 2017-11-30 | 2018-05-18
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/3063785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5654662 | Completed | 17370 | 17267 | 2021-06-02 | 2024-05-01
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4327297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115811592 | Completed | 18360 | 18360 | 2022-09-28 | 2024-02-19
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4329781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117813337 | Completed | 18360 | 16150 | 2022-09-28 | 2024-08-06
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4329787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117818441 | Completed | 18360 | 16150 | 2022-09-28 | 2024-08-06
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4336528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117809892 | Completed | 18360 | 18224 | 2022-09-28 | 2024-01-02
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4336530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117812697 | Completed | 18360 | 15895 | 2022-11-15 | 2024-08-04
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4341863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115630726 | Completed | 18360 | 15538 | 2022-09-28 | 2024-08-04
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4342185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115811959 | Completed | 18360 | 17051 | 2022-11-11 | 2024-05-21
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4354363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131396683 | Completed | 18360 | 18276 | 2022-11-18 | 2024-08-04
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4370098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118840200 | Completed | 18360 | 16251 | 2022-11-18 | 2025-04-21
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4397725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115623156 | Completed | 19890 | 7735 | 2023-07-17 | 2024-05-22
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4397731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115627871 | Completed | 19890 | 14077 | 2023-07-17 | 2024-08-04
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4397915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115816599 | Completed | 19890 | 7735 | 2023-07-17 | 2024-05-22
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4398296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117815058 | Completed | 19890 | 3094 | 2023-07-17 | 2024-05-01
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4398300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117817775 | Completed | 19890 | 7735 | 2023-07-17 | 2024-05-22
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4407192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131396395 | Completed | 19890 | 4795 | 2023-07-17 | 2024-08-04
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4407193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131396408 | Completed | 19890 | 3094 | 2023-07-17 | 2024-05-22
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4407195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131397014 | Completed | 19890 | 7735 | 2023-07-17 | 2024-05-22
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4407196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131397033 | Completed | 19890 | 18318 | 2023-07-17 | 2024-08-01
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4408516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141679632 | Completed | 19890 | 10829 | 2023-07-17 | 2024-05-01
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/4408517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141679643 | Completed | 19890 | 7735 | 2023-07-17 | 2024-05-01
TIKAMGARH / TIKAMGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/57183 — Construction of IAY House -IAY REG. NO. MP-07-006-070-001/261 | Completed | 14310 | 14863 | 2016-06-07 | 2016-11-01
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/640043 — Construction of IAY House -IAY REG. NO. MP1001367 | Completed | 15030 | 14632 | 2019-06-12 | 2019-09-09
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/640045 — Construction of IAY House -IAY REG. NO. MP1001415 | Completed | 15030 | 15132 | 2017-11-30 | 2018-12-05
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/640173 — Construction of IAY House -IAY REG. NO. MP1005022 | Completed | 15030 | 16512 | 2017-05-04 | 2018-03-08
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/640174 — Construction of IAY House -IAY REG. NO. MP1005031 | Completed | 15030 | 14964 | 2017-08-10 | 2018-03-28
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/640234 — Construction of IAY House -IAY REG. NO. MP1006550 | Completed | 15030 | 15132 | 2017-11-30 | 2018-07-30
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/640275 — Construction of IAY House -IAY REG. NO. MP1008012 | Completed | 15030 | 15136 | 2017-09-01 | 2018-03-08
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/640287 — Construction of IAY House -IAY REG. NO. MP1008170 | Completed | 15030 | 15132 | 2017-11-30 | 2018-05-18
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/640537 — Construction of IAY House -IAY REG. NO. MP1016663 | Completed | 15030 | 14616 | 2018-07-04 | 2018-10-11
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/640790 — Construction of IAY House -IAY REG. NO. MP1024090 | Completed | 15030 | 15098 | 2017-09-01 | 2018-11-22
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/640792 — Construction of IAY House -IAY REG. NO. MP1024267 | Completed | 15030 | 13932 | 2017-08-10 | 2018-10-29
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/640797 — Construction of IAY House -IAY REG. NO. MP1024304 | Completed | 15030 | 14632 | 2019-06-12 | 2019-09-09
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/640798 — Construction of IAY House -IAY REG. NO. MP1024317 | Completed | 15030 | 14964 | 2017-08-10 | 2018-03-26
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/640800 — Construction of IAY House -IAY REG. NO. MP1024388 | Completed | 15030 | 15132 | 2017-11-30 | 2018-11-13
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/641926 — Construction of IAY House -IAY REG. NO. MP1105246 | Completed | 15030 | 17544 | 2017-08-10 | 2018-03-08
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/642123 — Construction of IAY House -IAY REG. NO. MP1124353 | Completed | 15030 | 15362 | 2017-11-30 | 2018-05-18
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/642331 — Construction of IAY House -IAY REG. NO. MP1137337 | Completed | 17100 | 1701 | 2024-06-21 | 2024-08-04
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/642347 — Construction of IAY House -IAY REG. NO. MP1139312 | Completed | 15030 | 14616 | 2018-07-05 | 2018-10-11
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/642364 — Construction of IAY House -IAY REG. NO. MP1140033 | Completed | 15030 | 14964 | 2018-10-18 | 2019-04-12
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/642407 — Construction of IAY House -IAY REG. NO. MP1142409 | Completed | 17100 | 1701 | 2024-06-21 | 2024-08-04
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/642409 — Construction of IAY House -IAY REG. NO. MP1142461 | Completed | 15030 | 15482 | 2017-11-30 | 2018-07-30
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/642570 — Construction of IAY House -IAY REG. NO. MP1153385 | Completed | 15030 | 15660 | 2017-11-30 | 2019-01-19
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/642582 — Construction of IAY House -IAY REG. NO. MP1154225 | Completed | 17100 | 15928 | 2018-07-05 | 2024-08-12
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/642643 — Construction of IAY House -IAY REG. NO. MP1158108 | Completed | 15030 | 15824 | 2017-08-10 | 2018-03-23
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/642649 — Construction of IAY House -IAY REG. NO. MP1158445 | Completed | 15030 | 17048 | 2017-11-30 | 2018-07-30
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/643973 — Construction of IAY House -IAY REG. NO. MP1238039 | Completed | 15030 | 17544 | 2017-08-10 | 2018-03-22
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/644480 — Construction of IAY House -IAY REG. NO. MP1299474 | Completed | 15030 | 16704 | 2017-11-30 | 2018-08-28
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/645567 — Construction of IAY House -IAY REG. NO. MP1462680 | Completed | 15030 | 15320 | 2017-08-10 | 2018-05-18
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/645801 — Construction of IAY House -IAY REG. NO. MP1502069 | Completed | 15030 | 15996 | 2017-05-11 | 2018-03-28
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/646045 — Construction of IAY House -IAY REG. NO. MP1558347 | Completed | 15030 | 15660 | 2018-07-05 | 2018-12-16
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/646083 — Construction of IAY House -IAY REG. NO. MP1567739 | Completed | 15030 | 15996 | 2017-05-11 | 2018-03-23
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648330 — Construction of IAY House -IAY REG. NO. MP2235697 | Completed | 15030 | 15308 | 2017-11-30 | 2018-07-30
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648355 — Construction of IAY House -IAY REG. NO. MP2241721 | Completed | 15030 | 14616 | 2018-07-05 | 2018-11-05
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648530 — Construction of IAY House -IAY REG. NO. MP2293959 | Completed | 15030 | 15482 | 2017-11-30 | 2018-08-02
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648635 — Construction of IAY House -IAY REG. NO. MP2333395 | Completed | 15030 | 15660 | 2018-07-05 | 2019-03-19
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648743 — Construction of IAY House -IAY REG. NO. MP2363916 | Completed | 15030 | 16512 | 2017-05-04 | 2018-03-22
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648744 — Construction of IAY House -IAY REG. NO. MP2363929 | Completed | 15030 | 17544 | 2017-08-10 | 2018-03-25
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648753 — Construction of IAY House -IAY REG. NO. MP2367243 | Completed | 15030 | 15196 | 2017-05-11 | 2018-11-05
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648766 — Construction of IAY House -IAY REG. NO. MP2372043 | Completed | 17100 | 16381 | 2018-07-05 | 2022-05-13
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648792 — Construction of IAY House -IAY REG. NO. MP2381210 | Completed | 15030 | 15482 | 2017-11-30 | 2018-07-30
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648793 — Construction of IAY House -IAY REG. NO. MP2381356 | Completed | 15030 | 15312 | 2017-11-30 | 2018-11-22
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648794 — Construction of IAY House -IAY REG. NO. MP2381418 | Completed | 15030 | 13050 | 2017-11-30 | 2019-07-29
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648795 — Construction of IAY House -IAY REG. NO. MP2381520 | Completed | 15030 | 15482 | 2017-11-30 | 2018-07-30
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648810 — Construction of IAY House -IAY REG. NO. MP2387117 | Completed | 15030 | 17544 | 2017-08-10 | 2018-03-25
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648821 — Construction of IAY House -IAY REG. NO. MP2389364 | Completed | 15030 | 15486 | 2018-07-05 | 2018-12-16
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648828 — Construction of IAY House -IAY REG. NO. MP2391281 | Completed | 15030 | 17744 | 2017-11-30 | 2018-11-14
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648830 — Construction of IAY House -IAY REG. NO. MP2391490 | Completed | 15030 | 14438 | 2017-11-30 | 2018-10-29
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648831 — Construction of IAY House -IAY REG. NO. MP2391830 | Completed | 15030 | 14964 | 2017-08-10 | 2018-08-28
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648865 — Construction of IAY House -IAY REG. NO. MP2403489 | Completed | 15030 | 15312 | 2018-07-05 | 2018-10-27
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/648867 — Construction of IAY House -IAY REG. NO. MP2403556 | Completed | 15030 | 17544 | 2017-08-10 | 2018-03-05
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/649150 — Construction of IAY House -IAY REG. NO. MP2541020 | Completed | 15030 | 14224 | 2017-05-11 | 2018-10-10
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/649169 — Construction of IAY House -IAY REG. NO. MP2555448 | Completed | 15030 | 14448 | 2017-05-04 | 2018-10-18
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/649499 — Construction of IAY House -IAY REG. NO. MP2768226 | Completed | 15030 | 15996 | 2017-05-11 | 2018-03-25
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/649643 — Construction of IAY House -IAY REG. NO. MP2858504 | Completed | 15030 | 16684 | 2017-05-04 | 2018-03-05
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/649782 — Construction of IAY House -IAY REG. NO. MP2940907 | Completed | 15030 | 16512 | 2017-05-04 | 2018-03-05
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/652142 — Construction of IAY House -IAY REG. NO. MP1016675 | Completed | 15030 | 14958 | 2017-11-30 | 2019-01-02
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/652604 — Construction of IAY House -IAY REG. NO. MP2287167 | Completed | 15030 | 15410 | 2017-11-30 | 2018-07-30
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/832268 — Construction of IAY House -IAY REG. NO. MP1134744 | Completed | 15480 | 15136 | 2017-09-01 | 2018-05-18
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/849413 — Construction of IAY House -IAY REG. NO. MP1483758 | Completed | 15480 | 14612 | 2017-11-30 | 2018-10-11
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/926349 — Construction of IAY House -IAY REG. NO. MP2529100 | Completed | 15480 | 15312 | 2017-11-30 | 2018-07-30
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/937250 — Construction of IAY House -IAY REG. NO. MP2768820 | Completed | 15480 | 14964 | 2017-11-30 | 2018-10-27
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/947335 — Construction of IAY House -IAY REG. NO. MP2976450 | Completed | 15480 | 15308 | 2017-09-01 | 2018-05-18
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/947434 — Construction of IAY House -IAY REG. NO. MP2978946 | Completed | 15480 | 15654 | 2017-11-30 | 2018-07-30
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/947976 — Construction of IAY House -IAY REG. NO. MP2994141 | Completed | 15480 | 15308 | 2017-11-30 | 2019-04-12
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/948049 — Construction of IAY House -IAY REG. NO. MP2996210 | Completed | 15480 | 15480 | 2017-11-30 | 2018-06-30
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/981840 — Construction of IAY House -IAY REG. NO. MP3954618 | Completed | 15480 | 15136 | 2017-09-01 | 2018-05-18
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006070/IF/IAY/982206 — Construction of IAY House -IAY REG. NO. MP3969211 | Completed | 17100 | 17175 | 2017-11-30 | 2021-05-10
TIKAMGARH / TIKAMGARH | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707006070/LD/22012034277254 — Med badhan Manka/parmu adiwasi | Completed | 22000 | 16366 | 2016-07-05 | 2016-11-01
TIKAMGARH / TIKAMGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1707006070/LD/22012034294302 — KHEL MAIDAN BEEGHA GHAT NALA KE PAAS | Completed | 849000 | 846576.31 | 2016-12-02 | 2019-11-28
TIKAMGARH / TIKAMGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1707006070/LD/3799426766 — Shantidham (Muktidham) B-ed College ke Pas | Completed | 493000 | 438627.37 | 2014-02-18 | 2018-04-24
TIKAMGARH / TIKAMGARH | 2014-2015 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1707006070/LD/9926713758 — Shantidham (Muktidham) Nala ke Pas | Completed | 257000 | 206081.31 | 2014-08-05 | 2018-04-03
TIKAMGARH / TIKAMGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006070/RC/100000 — सी सी रोड निर्माण कशिोरा अहिरवार के मकान से सईद खा | Completed | 150000 | 135623 | 2013-11-12 | 2015-04-25
TIKAMGARH / TIKAMGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707006070/RC/10200 — मिटटी मुरम रोड निर्माण झांसी रोड से मुक्तिधाम तक | Completed | 246000 | 29216 | 2011-09-03 | 2016-06-30
TIKAMGARH / TIKAMGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707006070/RC/1088 — पहुंच मार्ग निर्माण्‍ा झॉसी रोड से अनंतपुरा सीमा तक | Completed | 246000 | 31248 | 2011-09-03 | 2016-06-30
TIKAMGARH / TIKAMGARH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006070/RC/10900 — सी0सी0रोड निर्माण हरिजन बस्‍ती तखा | Completed | 398000 | 148192 | 2012-06-08 | 2014-02-10
TIKAMGARH / TIKAMGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006070/RC/22012034167330 — सी.सी. रोड निर्माण तखा मजरा हरिजन बस्‍ती में विधाय | Completed | 120000 | 73453 | 2013-06-11 | 2015-04-25
TIKAMGARH / TIKAMGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006070/RC/22012034192749 — C.C. Road Nali Dr Pateriya ke Makan se Khuman Ad | Completed | 150000 | 147371.9 | 2013-12-03 | 2015-04-25
TIKAMGARH / TIKAMGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006070/RC/22012034201752 — Nali Nirman Dewki Nandan ke Makan se Chakki Tak | Completed | 38400 | 30416 | 2014-02-02 | 2015-06-09
TIKAMGARH / TIKAMGARH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006070/RC/22012034223815 — C.C. Road Jhansi Road se Ginni Raja ke Makan Tak | Completed | 61000 | 60163 | 2014-07-01 | 2015-06-09
TIKAMGARH / TIKAMGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006070/RC/22012034317140 — c c road nirman sarju ke makan se ghashyam ke makan tak tulsi ke tak | Completed | 197000 | 189775 | 2017-01-12 | 2017-04-30
TIKAMGARH / TIKAMGARH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006070/RC/22012034505852 — नाली ि‍निर्माण कार्य आंगनवाडी भवन से सुल्‍तान ि‍सिंह के चबू‍तरा तक | Completed | 83000 | 83424 | 2019-11-21 | 2020-05-01
TIKAMGARH / TIKAMGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006070/RC/22012034556425 — NALI NIRMAN KARY AAGANWADI KENDRA SE KOMAL BABU KE MAKAN TAK | Completed | 31650 | 30789 | 2021-02-02 | 2021-08-17
TIKAMGARH / TIKAMGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006070/RC/22012034579198 — CC ROAD SAH NALI NIRMAN PRATHMIK PATH SHALA TKHA MAJRA SE RAMKISAN YADAV KE MAKAN TAK | Completed | 27800 | 27792 | 2021-10-01 | 2022-03-11
TIKAMGARH / TIKAMGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006070/RC/22012034579199 — NALI NIRMAN SULTAN SINGH BABA KE CHABUTRA SE | Completed | 57400 | 55584 | 2021-11-08 | 2022-03-11
TIKAMGARH / TIKAMGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006070/RC/22012034582811 — CC ROAD NIRMA JHANSI ROAD SE AASHRAM TAK | Completed | 53000 | 55584 | 2021-11-08 | 2022-03-01
TIKAMGARH / TIKAMGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006070/RC/22012034608239 — CC ROAD RAMDAS YADAV KE GHAR SE AGRWAL KE GHAR TAK | Completed | 48500 | 41688 | 2022-03-03 | 2022-11-19
TIKAMGARH / TIKAMGARH | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707006070/RC/90096 — मुख्‍य मार्ग से व़क्षारापेण तक मिटटी मरम कार्य तखा | Completed | 0 | 241409 | 2007-02-15 | 2014-03-04
TIKAMGARH / TIKAMGARH | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707006070/RC/90188 — पहुचमार्ग व़क्षारोपण से जगतराज वावा तक तखा | Completed | 0 | 283948 | 2008-02-27 | 2014-02-10
TIKAMGARH / TIKAMGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1707006070/RS/22012034489767 — स्वच्छता परिसर आंगनवाडी के पास ग्राम पंचायत तखा | Completed | 75000 | 74840 | 2020-08-06 | 2022-11-05
TIKAMGARH / TIKAMGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1707006070/RS/22012034647626 — NALI NIRMAN KARY KHUNNA PAL KE MAKAN SE ROSHAN ADIWASI KE MAKAN TAK | Completed | 20000 | 12852 | 2022-04-29 | 2022-11-19
TIKAMGARH / TIKAMGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707006070/RS/22012034676627 — NALI NIRMAN KARY SOLANKI KE GHAR SE PRATHMIK SHALA MAJRA KI OR | Completed | 57000 | 54270 | 2022-11-29 | 2025-05-06
TIKAMGARH / TIKAMGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707006070/RS/22012035117083 — Nali nirman sukhdayal Adiwasi ke Ghar se ratiram Adiwasi ke Ghar tak | Completed | 21000 | 15470 | 2024-02-13 | 2025-06-10
TIKAMGARH / TIKAMGARH | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006070/WC/0028 — stapdam | Completed | 0 | 240054 | 2006-06-18 | 2023-06-13
TIKAMGARH / TIKAMGARH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006070/WC/100000 — स्‍टाप डैम निर्माण तखा बडा नाला | Completed | 495000 | 272896 | 2009-04-13 | 2014-02-10
TIKAMGARH / TIKAMGARH | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1707006070/WC/101 — सोकपिट निर्माण पेयजल कूप करोदयाउ ंमजरा तखा | Completed | 11000 | 6344 | 2011-07-01 | 2011-09-01
TIKAMGARH / TIKAMGARH | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1707006070/WC/102 — हेण्‍ड पम्‍प सोकपिट निर्माण | Completed | 6000 | 36103 | 2011-06-24 | 2011-09-01
TIKAMGARH / TIKAMGARH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1707006070/WC/22012034318602 — TALAB NIRMAN KHACHCHAN KA | Completed | 400000 | 393711.71 | 2017-05-19 | 2018-10-25
TIKAMGARH / TIKAMGARH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1707006070/WC/22012034446240 — जल संबर्धन क्षमता ब्रदी बाॅध विस्‍तार वीगादार नाला तखा | Completed | 944000 | 905574 | 2019-03-10 | 2019-11-28
TIKAMGARH / TIKAMGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707006070/WC/22012034546215 — parcolation tenk nirman | Completed | 332572.21 | 223820 | 2020-05-08 | 2022-05-05
TIKAMGARH / TIKAMGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1707006070/WC/22012034659913 — CTR मेढ बधांन मोतीआ‍दिवासी के खेत मे | Completed | 35622.36 | 32419 | 2021-04-22 | 2022-03-11
TIKAMGARH / TIKAMGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1707006070/WC/22012034659928 — CTR CTR मेढ बधांन रामलाल आ‍दिवासी के खेत मे | Completed | 35622.36 | 16153 | 2021-04-22 | 2022-05-05
TIKAMGARH / TIKAMGARH | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006070/WC/719 — स्‍टाफ डेम निर्माण तखा | Completed | 0 | 243799 | 2006-05-22 | 2023-06-13
TIKAMGARH / TIKAMGARH | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006070/WC/99011 — जलक्षमता व़.ि वंड रेंजिग कार्य हरदिया नाला तलैया तखा | Completed | 0 | 47503 | 2007-07-09 | 2014-02-10
TIKAMGARH / TIKAMGARH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1707006070/WC/99012 — सिचाई कूप हरिया दलीपा सौर तखा | Completed | 174000 | 162873 | 2008-02-09 | 2018-10-25
TIKAMGARH / TIKAMGARH | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006070/WC/99013 — सिंचाई कूप निर्माण रमलू/ सगना सौर | Completed | 0 | 145215 | 2008-02-04 | 2011-12-27
TIKAMGARH / TIKAMGARH | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006070/WC/99014 — सिंचाई कूप निर्माण्‍ा हरदास/ कल्‍लू सौर | Completed | 0 | 155604 | 2008-02-02 | 2011-11-25
TIKAMGARH / TIKAMGARH | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006070/WC/99043 — नयीवस्‍ती आदिवासी वस्‍ती में पेयजल कूप निर्माण तखा | Completed | 0 | 148044 | 2007-12-24 | 2016-06-30
TIKAMGARH / TIKAMGARH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006070/WC/99165 — नवीन कूप निर्माण सुदिया पत्नि भगोने सौर तखा | Completed | 177000 | 93086 | 2008-05-07 | 2016-08-23
TIKAMGARH / TIKAMGARH | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006070/WC/99205 — सिचाई कूप निर्माण सगना पुत्री दसइंया सौर | Completed | 174000 | 125066 | 2008-02-06 | 2011-12-27
TIKAMGARH / TIKAMGARH | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1707006070/WC/99790 — कूप निर्माण कपिल धारा मकुन्‍दा सौर तखा | Completed | 174000 | 128463 | 2007-01-01 | 2008-09-27
TIKAMGARH / TIKAMGARH | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006070/WC/T81 — Karaundiya nala stapdam takha majra | Completed | 0 | 259705.9 | 2007-02-27 | 2008-07-10
TIKAMGARH / TIKAMGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1707006070/WC/Tkg3268 — पेयजल कूप हरिजन वस्‍ती करोदयाउ तखा | Completed | 153000 | 57335 | 2010-05-14 | 2014-03-04
TIKAMGARH / TIKAMGARH | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707006070/WH/3722 — सोकपिट निर्माण पेयजल कूप पालो का मुहल्‍ला | Completed | 12000 | 2562 | 2011-11-05 | 2011-11-25
TIKAMGARH / TIKAMGARH | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1707006070/WH/3723 — सोकपिट निर्माण पेयजल कूप देवी जी का मुहल्‍ला | Completed | 12000 | 2196 | 2011-11-05 | 2011-11-25
TIKAMGARH / TIKAMGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1707/RC/22012034153134 — GSB Jhansi Road to Takha Majana Road | Completed | 960000 | 328896 | 2011-04-11 | 2013-10-12