## Work List
Exported on: 2026-10-13 14:06:31
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: SUJARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
TIKAMGARH / TIKAMGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707006046/IF/375 — कपिलधारा कूप शातिवाई कामता रजक सुजारा | Completed | 233000 | 223958 | 2011-01-13 | 2015-04-25
TIKAMGARH / TIKAMGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006046/IF/IAY/612816 — Construction of IAY House -IAY REG. NO. MP1534594 | Completed | 15030 | 14196 | 2017-03-07 | 2019-05-22
TIKAMGARH / TIKAMGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006046/IF/IAY/612946 — Construction of IAY House -IAY REG. NO. MP1560336 | Completed | 15030 | 12028 | 2017-03-21 | 2019-06-06
TIKAMGARH / TIKAMGARH | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1707006079/AV/22012034390212 — SHANTIDHAM NIRMAN HARDOUL MUHALLA SIDDH BABA PAHADI KE PASS | Deleted | 245000 | 52664 | 2019-03-09
TIKAMGARH / TIKAMGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of SHG/Fed building for Groups / Construction of SHG/Federation Building for Groups | Construction of building/workshed for SHG | 1707006079/AV/22012034542340 — naveen go sala nirman gram panchayat sujara | Closed | 0 | 0 | 2020-10-02
TIKAMGARH / TIKAMGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1707006079/AV/22012034550685 — Gau sala nirman dharampura sujara | Closed | 0 | 0 | 2021-01-26
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1707006079/AV/22012034565715 — Gau sala nirman dharampura sujara | Closed | 0 | 0 | 2021-04-14
TIKAMGARH / TIKAMGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1707006079/AV/22012034644618 — SAMUDAYAK BHAWAN KA NIRMAN KARY HARDOL BABA MANDIR KE PASS SUJARA | Ongoing | 58000 | 57226 | 2023-10-08
TIKAMGARH / TIKAMGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1707006079/AV/22012034663954 — SHANTIDHAM NIRMAN KARY SUJARA | Approved | 357906.6 | 0 | 2024-10-02
TIKAMGARH / TIKAMGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1707006079/DP/22012034446667 — Peyjal koop nirman harijan basti sujara | Closed | 0 | 0 | 2019-06-01
TIKAMGARH / TIKAMGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1707006079/DP/22012034482495 — KATOOR TRENCH NIRMAN HANUMAN JI PAHADI PAR | Closed | 0 | 0 | 2019-08-24
TIKAMGARH / TIKAMGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1707006079/DP/22012034596895 — VASHUDHA VANDAN AMRIT VATIKA (75) PRIMARY SCHOOL SUJARA | Closed | 55847.4 | 0 | 2023-04-14
TIKAMGARH / TIKAMGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1707006079/DW/9993655849 — पेयजल कूप निर्माण सामान्य वस्ती सुजारा | Completed | 385000 | 53024 | 2015-12-19 | 2020-02-25
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1707006079/IF/22012034353193 — sadak kinare buchhropan gwalbaba se harpura seema tak | Completed | 335000 | 15078 | 2017-06-20 | 2020-01-14
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707006079/IF/22012034481257 — Khettalab sankar/karna rajak sujara | Closed | 310385.56 | 0 | 2019-01-26
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707006079/IF/22012034481262 — Khettalab manak biskarma sujara | Closed | 0 | 0 | 2019-01-26
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012034481825 — mendhbandhan/shukhrani/kamlapat ahirwar | Closed | 0 | 0 | 2019-06-01
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012034481826 — mendhbandhan premdularee/umrao ahirwar | Closed | 0 | 0 | 2019-06-01
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707006079/IF/22012034481827 — kapildhara koop harprasad/tijju soni sujara | Closed | 0 | 0 | 2019-06-01
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012034486236 — mendbandhan kanhaiya/parma ahirwar | Closed | 0 | 0 | 2019-06-01
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012034486240 — medhbandhan kannu/basanta ahirwar | Closed | 0 | 0 | 2019-06-01
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012034486241 — medhbandhan ajjudi/dayaram lodhi | Closed | 0 | 0 | 2019-06-01
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012034486243 — medhbandhan biharee/dayaram lodhi | Closed | 0 | 0 | 2019-06-01
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012034486244 — medhbandhan manak/dayaram lodhi | Closed | 0 | 0 | 2019-06-01
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012034486245 — medhbandhan mulayam/deepchandra lodhi | Closed | 0 | 0 | 2019-06-01
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707006079/IF/22012034502744 — KHET TALAB RAMBAGASH/ CHHAMADAR VISHAWKARMA | Closed | 0 | 0 | 2019-08-24
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707006079/IF/22012034502747 — KHET TALAB PREMDULAREE/ UMRAO AHIRWAR | Closed | 0 | 0 | 2019-08-24
TIKAMGARH / TIKAMGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012034581199 — khettalab shanti bbai /kamta rajak | Ongoing | 332572.21 | 23756 | 2020-07-25
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012034581202 — khettalab ppremdularee/umrao sujara | Closed | 332572.21 | 0 | 2020-01-26
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012034581204 — khettalab sapna/umrao ahirwar | Closed | 0 | 0 | 2020-01-26
TIKAMGARH / TIKAMGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1707006079/IF/22012035215105 — KHAKRI NIRMAN KARY MAEHNDRA LODHI | Physically Completed | 192484.06 | 180602.1 | 2024-03-15 | 2026-05-28
TIKAMGARH / TIKAMGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012035218942 — KHAKRI NIRMAN KARY GHANSHYAM LODHI | Physically Completed | 192484.06 | 93102 | 2024-03-15 | 2026-06-10
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012035219804 — KHAKRI NIRMAN BENIBAI LODHI SUJARA | Physically Completed | 144863.05 | 71933.99 | 2024-03-15 | 2026-06-22
TIKAMGARH / TIKAMGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1707006079/IF/22012035223990 — KHAKRI NIRMAN KARYA PHULCHANDRA LODHI DHARAMPURA | Physically Completed | 296786.01 | 176567.98 | 2024-03-15 | 2026-06-22
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707006079/IF/22012035430219 — Dug well richarge pit Balchandra Lodhi | Physically Completed | 26766.04 | 3915 | 2025-05-06 | 2026-05-27
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1707006079/IF/22012035430234 — Dug well richarge pit Shree Bai Lodhi | Physically Completed | 26766.04 | 25954.95 | 2025-05-06 | 2026-05-27
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1707006079/IF/22012035430248 — Dug well richarge pit Santosh Mishra | Physically Completed | 26766.04 | 12006 | 2025-05-06 | 2026-05-27
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1707006079/IF/22012035449226 — dug well recharge pit nirman jagdeesh lodhi | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1707006079/IF/22012035449248 — dug well recharge pit nirman rama lodhi | Physically Completed | 26766.04 | 25366.7 | 2025-05-06 | 2026-05-28
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1707006079/IF/22012035449293 — dug well recharge pit nirman laxman vishwakarma | Physically Completed | 26766.04 | 26433.54 | 2025-05-06 | 2026-05-28
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1707006079/IF/22012035450740 — dug well recharge pit nirman jaydesh lodhi | Deleted | 0 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1707006079/IF/22012035552294 — dug well recharge pit nirman natthu lodhi | Physically Completed | 26766.04 | 25845 | 2025-06-17 | 2026-05-28
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1707006079/IF/22012035552297 — dug well recharge pit nirman jaydesh lodhi | Closed | 26766.04 | 0 | 2025-05-31
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707006079/IF/22012035552301 — khet talab nirman mulayam lodhi | Closed | 198952.21 | 0 | 2025-05-31
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707006079/IF/22012035552307 — khet talab nirman ajuddi lodhi | Closed | 198952.21 | 0 | 2025-06-04
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707006079/IF/22012035552312 — khet talab nirman natthu lodhi | Closed | 199160.71 | 0 | 2025-06-04
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707006079/IF/22012035560283 — Kapildhara koop nirman lakhan Lodhi sujara | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2246148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2859247 | Completed | 15840 | 16426 | 2020-02-28 | 2020-06-20
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2284554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4049124 | Completed | 15840 | 12144 | 2019-08-17 | 2020-02-25
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2284923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4555384 | Completed | 15840 | 13200 | 2019-08-17 | 2020-05-08
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2284951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4602209 | Completed | 17100 | 17040 | 2019-08-17 | 2022-12-30
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2285004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4685816 | Completed | 15840 | 15374 | 2019-09-28 | 2020-06-20
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2285334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5105729 | Completed | 17100 | 16492 | 2019-08-17 | 2023-07-05
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2285485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5499309 | Completed | 17100 | 17012 | 2019-09-28 | 2022-12-21
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2285488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5505206 | Completed | 15840 | 15936 | 2019-11-03 | 2020-07-05
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2285616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5685710 | Completed | 15840 | 15956 | 2020-01-02 | 2020-06-20
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2305264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4646341 | Completed | 15840 | 14432 | 2019-09-28 | 2020-05-08
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2305273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4692274 | Completed | 15840 | 11616 | 2019-08-17 | 2020-05-08
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2305355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4061190 | Completed | 15840 | 14080 | 2019-08-17 | 2020-02-25
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2305678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4579932 | Completed | 15840 | 15262 | 2019-09-28 | 2020-08-02
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2305684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4640874 | Completed | 15840 | 14234 | 2019-09-28 | 2020-05-08
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2305688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4672262 | Completed | 15840 | 15084 | 2020-01-02 | 2020-06-20
TIKAMGARH / TIKAMGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/2305846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5468583 | Completed | 15840 | 15136 | 2019-08-17 | 2020-05-08
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3024209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4241353 | Ongoing | 23490 | 7874 | 2022-11-29
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3024302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4656383 | Completed | 17370 | 17177 | 2021-04-19 | 2022-05-13
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3026491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4640117 | Completed | 17370 | 17276 | 2021-04-19 | 2023-01-09
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3026598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4645190 | Completed | 17370 | 17009 | 2021-04-19 | 2022-01-05
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3027475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5094430 | Completed | 17370 | 17177 | 2021-04-19 | 2021-12-23
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3030347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4578167 | Completed | 17370 | 17276 | 2021-04-19 | 2023-01-09
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3030884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5510201 | Completed | 17370 | 16598 | 2021-06-01 | 2022-10-15
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3031466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5697390 | Completed | 17370 | 17061 | 2021-04-19 | 2023-01-10
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3060869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4620911 | Completed | 17370 | 16791 | 2021-06-01 | 2022-04-25
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3060983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4657170 | Completed | 17370 | 17370 | 2021-04-19 | 2022-01-12
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3061151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4684442 | Completed | 17370 | 16994 | 2021-10-25 | 2022-11-30
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3061268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4639685 | Completed | 17370 | 16791 | 2021-04-19 | 2022-02-10
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3061353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4648731 | Completed | 17370 | 16791 | 2021-05-04 | 2022-04-30
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3061355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4649205 | Completed | 17370 | 17177 | 2021-04-19 | 2022-01-05
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3061377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5094668 | Completed | 17370 | 16969 | 2021-04-19 | 2023-08-22
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3061413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4283031 | Ongoing | 23490 | 15889 | 2021-05-04
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3061415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4284534 | Completed | 17370 | 17177 | 2021-05-17 | 2022-05-20
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3061747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4575499 | Completed | 17370 | 16405 | 2021-04-19 | 2022-04-22
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3061751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4577192 | Completed | 17370 | 17057 | 2021-10-18 | 2024-08-04
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3062514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4642299 | Completed | 17370 | 17218 | 2021-05-04 | 2024-08-04
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3062519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4646113 | Completed | 17370 | 16984 | 2021-04-19 | 2022-05-26
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3062646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4602664 | Completed | 17370 | 16212 | 2021-04-19 | 2022-01-20
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3062660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5140986 | Completed | 17370 | 16196 | 2021-05-04 | 2024-08-04
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3063346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5519631 | Completed | 17370 | 17014 | 2021-04-19 | 2024-08-04
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3063465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5497943 | Completed | 17370 | 17349 | 2021-04-19 | 2024-08-07
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3063469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5499504 | Completed | 17370 | 16598 | 2021-06-01 | 2022-01-25
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3063666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5247750 | Completed | 17370 | 16366 | 2021-05-04 | 2022-09-25
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3064061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5103389 | Completed | 17370 | 17331 | 2021-04-19 | 2022-04-25
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3064165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4563024 | Completed | 17370 | 16791 | 2021-04-19 | 2022-04-25
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3064284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5491572 | Completed | 17370 | 16791 | 2021-04-19 | 2022-02-20
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3064285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5491591 | Completed | 17370 | 17358 | 2021-10-28 | 2022-08-30
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3064301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4216629 | Physically Completed | 17370 | 2652 | 2023-05-17 | 2024-11-21
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3064441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5161114 | Completed | 17370 | 17276 | 2021-04-19 | 2022-08-12
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3172111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5667812 | Completed | 17370 | 16984 | 2021-10-28 | 2022-05-26
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3187835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5158862 | Completed | 17370 | 16713 | 2021-10-28 | 2023-12-13
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3187836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5160438 | Completed | 17370 | 16945 | 2021-07-08 | 2022-08-10
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3188126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4667628 | Completed | 17370 | 17309 | 2021-10-19 | 2025-02-20
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3188830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5094844 | Completed | 17370 | 17292 | 2021-10-27 | 2022-09-01
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3189046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5489688 | Completed | 17370 | 16716 | 2021-10-27 | 2023-12-13
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3189047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5487013 | Completed | 17370 | 15475 | 2021-10-27 | 2026-07-16
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3189048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4648336 | Completed | 17370 | 17169 | 2022-02-14 | 2024-08-08
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3190430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4578972 | Completed | 17370 | 17225 | 2021-08-24 | 2026-07-16
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3265709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4640074 | Closed | 17370 | 0 | 2021-10-23
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/3411917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4664901 | Physically Completed | 17370 | 17282 | 2022-01-24 | 2024-11-21
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4003192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118598762 | Completed | 18360 | 18360 | 2022-07-17 | 2022-11-19
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4003193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118599109 | Completed | 18360 | 18156 | 2022-07-17 | 2023-05-25
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4131671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119720997 | Completed | 18360 | 18215 | 2022-07-06 | 2024-08-02
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4132893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118851124 | Completed | 18360 | 17581 | 2022-07-06 | 2026-07-16
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4132937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119376765 | Completed | 18360 | 18360 | 2022-07-06 | 2022-11-20
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4133443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117764772 | Completed | 18360 | 18360 | 2022-07-09 | 2022-11-20
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4582463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118848981 | Completed | 23490 | 21627 | 2024-10-04 | 2025-04-09
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4582478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118852646 | Completed | 21870 | 21627 | 2024-11-05 | 2025-04-03
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4706007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121947007 | Completed | 21870 | 21627 | 2024-10-04 | 2025-04-03
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4949240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117396735 | Completed | 23490 | 22344 | 2025-03-20 | 2025-11-09
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4949504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117764706 | Completed | 23490 | 22869 | 2025-03-20 | 2025-07-18
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4951918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118598862 | Completed | 23490 | 23049 | 2025-03-20 | 2025-11-09
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4952644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118848424 | Completed | 23490 | 22266 | 2025-03-20 | 2025-07-18
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4952646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118850216 | Completed | 23490 | 23229 | 2025-05-26 | 2025-11-08
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4952648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118850487 | Completed | 23490 | 22878 | 2025-03-23 | 2025-11-08
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4952825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119375613 | Completed | 23490 | 23049 | 2025-03-20 | 2025-11-08
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4952826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119376978 | Completed | 23490 | 23310 | 2025-03-20 | 2025-11-08
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4952828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119378607 | Completed | 23490 | 23049 | 2025-03-20 | 2025-12-09
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4953019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119526837 | Completed | 23490 | 23049 | 2025-03-20 | 2025-11-08
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/4953020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119526917 | Ongoing | 23490 | 21663 | 2025-09-16
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5345246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119720747 | Completed | 23490 | 22968 | 2025-09-18 | 2025-12-18
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5345247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119721133 | Completed | 23490 | 23490 | 2025-04-17 | 2025-11-09
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5345248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119721179 | Completed | 23490 | 23490 | 2025-05-22 | 2025-11-09
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5345249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119721381 | Ongoing | 23490 | 3654 | 2025-07-17
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5345253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117764499 | Ongoing | 23490 | 23490 | 2025-04-17
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5345254 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117764616 | Completed | 23490 | 23229 | 2025-05-26 | 2025-11-09
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5345678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119527393 | Ongoing | 23490 | 23490 | 2025-09-18
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5346708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119374141 | Ongoing | 23490 | 22629 | 2025-08-13
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5346710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119376304 | Ongoing | 23490 | 23229 | 2025-05-26
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5348061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121567174 | Completed | 23490 | 23229 | 2025-10-14 | 2025-12-18
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5348064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121578195 | Ongoing | 23490 | 23490 | 2025-10-07
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5348074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121947564 | Completed | 23490 | 23159 | 2025-05-22 | 2025-11-09
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5348349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117396019 | Completed | 23490 | 23229 | 2025-05-26 | 2025-11-09
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5351068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118599182 | Completed | 23490 | 22707 | 2025-05-22 | 2025-11-09
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5351072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118850353 | Completed | 23490 | 21663 | 2025-04-21 | 2025-11-09
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5351078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121575102 | Completed | 23490 | 23490 | 2025-04-17 | 2025-11-09
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5352383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119721631 | Completed | 23490 | 22968 | 2025-09-14 | 2025-12-18
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5352384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119721725 | Completed | 23490 | 22185 | 2025-09-18 | 2026-06-10
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5353628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121579381 | Ongoing | 23490 | 23229 | 2025-08-06
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5353970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118598531 | Completed | 23490 | 23490 | 2025-04-10 | 2025-11-09
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5355199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117396321 | Completed | 23490 | 23229 | 2025-04-17 | 2025-12-18
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5355900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119527201 | Completed | 23490 | 23490 | 2025-08-21 | 2026-01-27
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5355913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121577893 | Completed | 23490 | 23490 | 2025-04-17 | 2025-11-09
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5413456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119376121 | Completed | 23490 | 23229 | 2025-05-26 | 2026-07-16
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5414463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119527239 | Ongoing | 23490 | 21924 | 2025-08-13
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5415386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119721436 | Completed | 23490 | 23229 | 2025-07-28 | 2025-12-18
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5584502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119375111 | Completed | 23490 | 23490 | 2025-11-08 | 2026-01-19
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5584543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121947749 | Completed | 23490 | 23490 | 2025-05-26 | 2025-11-09
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5643037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119375398 | Ongoing | 23490 | 19575 | 2025-08-06
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5835416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132451671 | Completed | 23490 | 22707 | 2025-10-13 | 2026-01-19
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5835912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121578973 | Completed | 23490 | 23490 | 2025-10-14 | 2026-07-16
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/5836678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117764632 | Completed | 23490 | 23229 | 2025-10-13 | 2026-01-27
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/6059903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117764543 | Approved | 23490 | 0 | 2025-03-05
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/6062775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119721075 | Approved | 23490 | 0 | 2025-03-05
TIKAMGARH / TIKAMGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/855687 — Construction of IAY House -IAY REG. NO. MP1559575 | Completed | 17100 | 11586 | 2018-11-01 | 2020-09-20
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/860680 — Construction of IAY House -IAY REG. NO. MP1622747 | Completed | 15480 | 19040 | 2017-05-16 | 2018-12-03
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/942264 — Construction of IAY House -IAY REG. NO. MP2851551 | Completed | 15480 | 13844 | 2017-06-06 | 2019-06-06
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/942772 — Construction of IAY House -IAY REG. NO. MP2863586 | Completed | 15480 | 13808 | 2017-05-16 | 2019-06-06
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/942896 — Construction of IAY House -IAY REG. NO. MP2866619 | Completed | 15480 | 15344 | 2017-05-30 | 2018-08-20
TIKAMGARH / TIKAMGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707006079/IF/IAY/943898 — Construction of IAY House -IAY REG. NO. MP2890993 | Completed | 15480 | 14612 | 2017-05-30 | 2019-05-22
TIKAMGARH / TIKAMGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707006079/LD/22012034226533 — Medbandhan Dayaram/Deepchand Lodhi | Completed | 15000 | 11448 | 2015-06-20 | 2015-12-17
TIKAMGARH / TIKAMGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707006079/LD/22012034226548 — Medbandhan Sukrani/Kamlapat Ahirwar | Deleted | 15000 | 0 | 2015-06-20
TIKAMGARH / TIKAMGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707006079/LD/22012034232979 — कंटूर् ट्रेंच पोंगारया पहाड़ी सुजारा | Completed | 278000 | 192541 | 2015-12-05 | 2017-03-10
TIKAMGARH / TIKAMGARH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707006079/LD/22012034259805 — Medbandhan Nanebhai/Janki Rajak | Deleted | 0 | 0 | 2016-01-26
TIKAMGARH / TIKAMGARH | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1707006079/LD/22012034299739 — शांति धाम निर्माण-सुजारा | Closed | 245000 | 0 | 2016-11-01
TIKAMGARH / TIKAMGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1707006079/LD/22012034540876 — Charagah nirman dharampura sujara | Closed | 0 | 0 | 2021-01-26
TIKAMGARH / TIKAMGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1707006079/LD/22012034938359 — BOLDAR BALL POUNGRYA PAHADI | Physically Completed | 135338.84 | 93380.08 | 2024-03-15 | 2026-06-05
TIKAMGARH / TIKAMGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1707006079/LD/22012034949705 — PERIFERAL BUND KHEL MAIDAN SUJARA | Closed | 443431.36 | 0 | 2025-02-28
TIKAMGARH / TIKAMGARH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707006079/LD/3799423709 — Muktidham Nirman Dharampura | Completed | 359000 | 90268 | 2014-01-31 | 2016-08-15
TIKAMGARH / TIKAMGARH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1707006079/LD/3799423713 — Kidangan Nirman Madhyamik Shala Ke Peechey | Completed | 300000 | 279547 | 2014-02-21 | 2016-08-15
TIKAMGARH / TIKAMGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1707006079/PG/22012034312853 — khel meadan gwalbaba ke pas sujara | Completed | 353000 | 352675.83 | 2017-06-20 | 2020-05-21
TIKAMGARH / TIKAMGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006079/RC/22012034191905 — C C Road Nirman Nali Nirman Prathmik Shala Se Ma | Completed | 76130 | 74806 | 2013-11-15 | 2014-01-25
TIKAMGARH / TIKAMGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006079/RC/22012034196236 — C.C. Road Mukhya Marg se Pyare Lodhi ke Kuwan Tak | Completed | 48000 | 46882 | 2014-01-03 | 2014-04-25
TIKAMGARH / TIKAMGARH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006079/RC/22012034229701 — C.C. Road Rambagas Badai se Malkhu Ahirwar Tak Sujara | Completed | 150000 | 145172 | 2014-09-30 | 2015-03-05
TIKAMGARH / TIKAMGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006079/RC/22012034296970 — C.C. Road Bhatnagar ke Kuwa se Narsingh Mandir ki Or | Completed | 66000 | 66078 | 2016-01-23 | 2016-10-31
TIKAMGARH / TIKAMGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1707006079/RC/22012034373158 — sudur sadak | Closed | 0 | 0 | 2018-01-01
TIKAMGARH / TIKAMGARH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707006079/RC/22012034522126 — sudur sadak narshingdev se sujara bandh jeo pount tak | Closed | 0 | 0 | 2020-01-26
TIKAMGARH / TIKAMGARH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707006079/RC/22012034522127 — sudur sadak bhagirath lodhi ke ghar se dhasan nadi ki or sujara | Closed | 0 | 0 | 2020-01-26
TIKAMGARH / TIKAMGARH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707006079/RC/22012034522128 — sudur sampark sadak hardol baba dev sthan se riyata ghat tak sujara | Closed | 0 | 0 | 2020-01-26
TIKAMGARH / TIKAMGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707006079/RC/22012034547746 — sudur sadak kary narshing baba dev sthan se ban sujara geo pount tak sujara | Closed | 0 | 0 | 2020-10-02
TIKAMGARH / TIKAMGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707006079/RC/22012034547747 — sudur sadak hardol baba dev sthan se dhasan nadi ke riyata ghat tak sujara | Closed | 0 | 0 | 2020-10-02
TIKAMGARH / TIKAMGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707006079/RC/22012034547748 — sudur sadak nirman anandi ahirwar ke makan se shri hanuman mandir tak sujara | Closed | 0 | 0 | 2020-10-02
TIKAMGARH / TIKAMGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707006079/RC/22012034547749 — sudur sadak nirman bhagirath rajpoot ke makan se dhasan nadi ki or sujara | Closed | 0 | 0 | 2020-10-02
TIKAMGARH / TIKAMGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006079/RC/22012034549182 — C C ROAD & NALI NIRMAN GILOJI VASHAKAR KE GHAR SE SANTOSH MISHRA KE MAKAN KI OR | Completed | 33900 | 34010 | 2020-11-27 | 2021-03-15
TIKAMGARH / TIKAMGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006079/RC/22012034549533 — C C ROAD & NALI NIRMAN BALRAM CHADAR KE GHAR SE GILONJI VANSHKAR KE GHAR TAK | Physically Completed | 37200 | 33060 | 2020-11-27 | 2021-04-30
TIKAMGARH / TIKAMGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Mitti Murram Roads for Comm / Repair and maintenance of Mitti Murram Roads for Community | Repair & maint of Road | 1707006079/RC/22012034569339 — sudursampark sadak narshing dev mandir se jeo.pount sujara bandh tak | Closed | 0 | 0 | 2021-04-14
TIKAMGARH / TIKAMGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Mitti Murram Roads for Comm / Repair and maintenance of Mitti Murram Roads for Community | Repair & maint of Road | 1707006079/RC/22012034569340 — sudursampark sadak hardolbaba dev sthan se riyata ghat dhasan nadi tak sujara | Closed | 0 | 0 | 2021-04-14
TIKAMGARH / TIKAMGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Mitti Murram Roads for Comm / Repair and maintenance of Mitti Murram Roads for Community | Repair & maint of Road | 1707006079/RC/22012034569341 — sudursampark sadak nirman bhagirath rajpoot ke makan se dhasan nadi tak sujara | Closed | 0 | 0 | 2021-04-14
TIKAMGARH / TIKAMGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Mitti Murram Roads for Comm / Repair and maintenance of Mitti Murram Roads for Community | Repair & maint of Road | 1707006079/RC/22012034569342 — sudursampark sadak anandi ahirwar ke makan se hanuman ji mandir tak sujara | Closed | 0 | 0 | 2021-04-14
TIKAMGARH / TIKAMGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006079/RC/22012034576106 — C C ROAD SAH NALI NIRMAN BALRAM CHADAR KE GHAR SE BHATNAGAR KUA KI OR | Closed | 37200 | 0 | 2021-04-14
TIKAMGARH / TIKAMGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006079/RC/22012034585198 — NALI NIRMAN KARY HARIJAN BASTI SUJARA | Completed | 72000 | 97272 | 2021-10-02 | 2022-07-15
TIKAMGARH / TIKAMGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006079/RC/22012034611950 — C C ROAD SAH NALI NIRMAN KARY BALRAM CHADAR KE GHAR SE BHATNAGAR KUA KI OR | Closed | 0 | 0 | 2021-04-14
TIKAMGARH / TIKAMGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006079/RC/22012034611951 — C C ROAD SAH NALI NIRMAN KARY BALRAM CHADAR KE GHAR SE BHATNAGAR KUA KI OR | Closed | 37200 | 0 | 2021-04-14
TIKAMGARH / TIKAMGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006079/RC/22012034632849 — CC ROAD NIRMAN KANTU AHIRWAR KE GHAR SE KHUDA VANSHKAR KE GHAR TAK SUJARA | Completed | 14800 | 11492 | 2023-07-18 | 2025-05-06
TIKAMGARH / TIKAMGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707006079/RC/22012034665526 — CC ROAD NIRMAN BHAGIRATH LODHI KE GARIJ SE SIDHBABA KI OR | Physically Completed | 83000 | 81793 | 2023-10-08 | 2026-05-06
TIKAMGARH / TIKAMGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707006079/RS/22012034692894 — NALI NIRMAN KARY DEVI RAJA KE GHAR SE PRATHMIK SHALA BHAWAN TAK | Completed | 34500 | 30056 | 2023-09-17 | 2025-05-06
TIKAMGARH / TIKAMGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707006079/RS/22012034692895 — NALI NIRMAN KARY MADHMIK SHALA SE BAGAJ MATA KI OR | Completed | 34500 | 30277 | 2023-08-18 | 2025-05-06
TIKAMGARH / TIKAMGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707006079/RS/22012035118672 — NALI NIRMAN KARY RAMESH LODHI KE MAKAN SE SIDHBABA KI OR | Completed | 51000 | 48607 | 2024-01-30 | 2025-07-22
TIKAMGARH / TIKAMGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1707006079/WC/22012034553448 — Khettalab premdularee/ umrao Ahirwar sujara | Deleted | 0 | 0 | 2020-01-26
TIKAMGARH / TIKAMGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1707006079/WC/22012034553449 — Khettalab sapna/umrao Ahirwar Sujara | Deleted | 0 | 0 | 2020-01-26
TIKAMGARH / TIKAMGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1707006079/WC/22012034565591 — khettalab shanti bai/kamta rajak | Deleted | 0 | 0 | 2020-01-26
TIKAMGARH / TIKAMGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1707006079/WC/22012034565592 — khettalab premdularee/umrao ahirwar sujara | Deleted | 0 | 0 | 2020-01-26
TIKAMGARH / TIKAMGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1707006079/WC/22012034565593 — khettalab sapna/umrao ahirwar | Deleted | 0 | 0 | 2020-01-26
TIKAMGARH / TIKAMGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1707006079/WC/22012034666621 — khet talab nirman ragveer lodhi/dayaram sujara | Closed | 0 | 0 | 2021-04-14
TIKAMGARH / TIKAMGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707006079/WC/22012034718779 — CTR.SOKTA GADDA SAMANYA BASTI HENDPAMP KE PAS | Physically Completed | 14467.3 | 4246 | 2021-06-24 | 2026-06-06
TIKAMGARH / TIKAMGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707006079/WC/22012034718793 — CTR.SOKTA GADDA HANUMAN GEE MANDIR HENDPUMP KE PASS SUJARA | Physically Completed | 14467.3 | 5983 | 2021-06-24 | 2026-06-04
TIKAMGARH / TIKAMGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707006079/WC/22012034718803 — CTR.SOKTA GADDA BANSKAR BASTI HENDPUMP KE PASS SUJARA | Physically Completed | 14467.3 | 4825 | 2021-06-24 | 2026-06-10
TIKAMGARH / TIKAMGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707006079/WC/22012034718821 — CTR.SOKTA GADDA HARDOL BABA HENDPUMP KE PASS SUJARA | Physically Completed | 14467.3 | 4632 | 2021-06-24 | 2026-06-06
TIKAMGARH / TIKAMGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707006079/WC/22012034718841 — CTR.SOKTA GADDA KHEL KA MEDAN HENDPUMP KE PASS SUJARA | Physically Completed | 14467.3 | 3860 | 2021-06-24 | 2026-06-04
TIKAMGARH / TIKAMGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707006079/WC/22012034718850 — CTR.SOKTA GADDA SCHOOL KE HENDPUMP KE PASS SUJARA | Physically Completed | 14467.3 | 3474 | 2021-07-08 | 2026-06-04
TIKAMGARH / TIKAMGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707006079/WC/22012034718857 — CTR.SOKTA GADDA RAIKWAR BASTI HENDPUMP KE PASS SUJARA | Physically Completed | 14467.3 | 2316 | 2021-06-24 | 2026-06-04
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1707006079/WC/22012035264987 — DUGWELL RECHARGE PIT PAYJAL KOOP MADHMIK SHALA KE PASS | Physically Completed | 26766.04 | 24160.2 | 2025-04-27 | 2026-06-17
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1707006079/WC/22012035264992 — DUGWELL RECHARGE PIT PAYJAL KOOP SHANKAR JI KE PASS | Physically Completed | 26766.04 | 25465.2 | 2025-04-27 | 2026-06-17