## Work List
Exported on: 2026-10-19 09:30:16
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SUJARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
TIKAMGARH / TIKAMGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1707006079/AV/22012034644618 — SAMUDAYAK BHAWAN KA NIRMAN KARY HARDOL BABA MANDIR KE PASS SUJARA | Ongoing | 58000 | 0 | 2023-10-08
TIKAMGARH / TIKAMGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1707006079/AV/22012034663954 — SHANTIDHAM NIRMAN KARY SUJARA | Approved | 357906.6 | 0 | 2024-10-02
TIKAMGARH / TIKAMGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1707006079/IF/22012034581199 — khettalab shanti bbai /kamta rajak | Ongoing | 332572.21 | 0 | 2020-07-25
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1707006079/IF/22012035449226 — dug well recharge pit nirman jagdeesh lodhi | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707006079/IF/22012035560283 — Kapildhara koop nirman lakhan Lodhi sujara | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/3024209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4241353 | Ongoing | 27000 | 0 | 2022-11-29
TIKAMGARH / TIKAMGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/3061413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4283031 | Ongoing | 27000 | 0 | 2021-05-04
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/4953020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119526917 | Ongoing | 27000 | 0 | 2025-09-16
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/5345249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119721381 | Ongoing | 27000 | 0 | 2025-07-17
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/5345253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117764499 | Physically Completed | 23490 | 0 | 2025-04-17 | 2026-07-23
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/5345678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119527393 | Physically Completed | 23490 | 0 | 2025-09-18 | 2026-07-23
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/5346708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119374141 | Ongoing | 27000 | 0 | 2025-08-13
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/5346710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119376304 | Ongoing | 27000 | 0 | 2025-05-26
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/5348064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121578195 | Physically Completed | 23490 | 0 | 2025-10-07 | 2026-07-23
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/5353628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121579381 | Ongoing | 27000 | 0 | 2025-08-06
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/5414463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119527239 | Ongoing | 27000 | 0 | 2025-08-13
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/5643037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119375398 | Physically Completed | 27000 | 0 | 2025-08-06 | 2026-10-04
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6059903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117764543 | Approved | 27000 | 0 | 2025-03-05
TIKAMGARH / TIKAMGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6062775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119721075 | Ongoing | 27000 | 16800 | 2026-08-03
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6321973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119720961 | Approved | 27000 | 0 | 2026-03-16
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6322054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119720791 | Approved | 27000 | 0 | 2026-03-16
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6322146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119720852 | Approved | 27000 | 0 | 2026-03-16
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6322208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121575431 | Approved | 27000 | 0 | 2026-03-16
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6322746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121946665 | Approved | 27000 | 0 | 2026-03-16
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6323034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119721232 | Approved | 27000 | 0 | 2026-03-16
TIKAMGARH / TIKAMGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6323445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119720691 | Ongoing | 27000 | 0 | 2026-10-12
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6323536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121574433 | Approved | 27000 | 0 | 2026-03-16
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6330775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119721342 | Approved | 27000 | 0 | 2026-03-16
TIKAMGARH / TIKAMGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6330910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118598811 | Ongoing | 27000 | 0 | 2026-10-12
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6331354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119720899 | Approved | 27000 | 0 | 2026-03-16
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006079/IF/IAY/6331965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121579748 | Approved | 27000 | 0 | 2026-03-16