## Work List
Exported on: 2026-10-19 05:39:30
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SUDA DHARMPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
TIKAMGARH / TIKAMGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1707006080/AV/22012034634782 — khel maidan nirman kary suda dharmpura | Ongoing | 612966.39 | 0 | 2023-07-01
TIKAMGARH / TIKAMGARH | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1707006080/AV/YD/22012034666620 — shanti dham nirman lambu ke pass suda dharmpura | Ongoing | 347299.82 | 201695.72 | 2025-12-22
TIKAMGARH / TIKAMGARH | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1707006080/AV/YD/22012034666621 — shanti dham nirman imla baba mohalla | Ongoing | 347299.82 | 0 | 2025-11-13
TIKAMGARH / TIKAMGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Block Plantation of Forestry Trees in fields for Individual | Other Works | 1707006080/IF/22012035074356 — Catale shed nirman kary bati lodhi | Ongoing | 120093.47 | 0 | 2024-01-01
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1707006080/IF/22012035307049 — कपिल धारा कूप कमलेश यादव | New | 0 | 0 | 2024-10-02
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006080/IF/IAY/4562019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115131063 | Ongoing | 27000 | 16800 | 2024-10-07
TIKAMGARH / TIKAMGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006080/IF/IAY/4587760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120260077 | Ongoing | 27000 | 0 | 2024-10-07
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006080/IF/IAY/5843754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120837212 | Ongoing | 27000 | 0 | 2026-01-29
TIKAMGARH / TIKAMGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006080/IF/IAY/6079857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119956982 | Ongoing | 27000 | 16800 | 2026-07-28
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006080/IF/IAY/6322556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115025250 | Approved | 27000 | 0 | 2026-03-13
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006080/IF/IAY/6323045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120260418 | Approved | 27000 | 0 | 2026-03-13
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707006080/IF/IAY/6323386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117605836 | Approved | 27000 | 0 | 2026-03-13
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707006080/IF/YD/22012035524254 — Kapildhara koop nirman kamlesh yadav | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1707006080/IF/YD/22012035569421 — khet talab nirman ghamua kumhar | Ongoing | 198614.94 | 0 | 2025-06-16
TIKAMGARH / TIKAMGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1707006080/IF/YD/22012035574344 — khet talab nirman kishori ahirwar | Approved | 198614.94 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1707006080/IF/YD/22012035574347 — dug well recharge pit nirman achchhe adiwasi | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1707006080/LD/22012034939086 — booldalbal - chhakki ahirwar ke khet ke paas | New | 0 | 0 | 2024-01-25
TIKAMGARH / TIKAMGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1707006080/LD/VB/22012034961675 — बोल्डर चेक लंबू के पास suda | New | 0 | 0 | 2026-05-05
TIKAMGARH / TIKAMGARH | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1707006080/RC/VB/YD/22012034854899 — sudoor sadak mukhya marg se pal mohalla tak | Approved | 0 | 0 | 2026-08-15
TIKAMGARH / TIKAMGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006080/WC/VB/22012035329828 — बोल्डर चेक लंबू के पास suda | Deleted | 0 | 0 | 2026-05-05
TIKAMGARH / TIKAMGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006080/WC/VB/22012035329883 — BOLDER CHEK NIRMAN LAMBU PAHADI | Ongoing | 70698.95 | 3600.52 | 2026-08-06
TIKAMGARH / TIKAMGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006080/WC/VB/22012035329890 — BOLDER CHEK NIRMAN LAMBU PAHADI Bhag 2 | Ongoing | 70698.95 | 4200 | 2026-08-06
TIKAMGARH / TIKAMGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707006080/WC/VB/22012035329892 — BOLDER CHEK NIRMAN LAMBU PAHADI BHAG 3 | Ongoing | 70698.95 | 5100.2 | 2026-08-06
TIKAMGARH / TIKAMGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1707006080/WC/VB/22012035332190 — GABION NIRMAN KARY LAMBU KI TALAIYA KE PASS | Approved | 157720.28 | 0 | 2026-04-30
TIKAMGARH / TIKAMGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1707006080/WC/VB/22012035332193 — GABION NIRMAN KARY SEKRA BARE KE UPER | Approved | 157720.28 | 0 | 2026-04-30
TIKAMGARH / TIKAMGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1707006080/WC/VB/22012035333824 — GABION NIRMAN BAGAJ MATA KE PASS PURONIYA | Approved | 157720.28 | 0 | 2026-04-30
TIKAMGARH / TIKAMGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1707006080/WC/VB/22012035333825 — GABION NIRMAN BAGAJ MATA KE PASS PURONIYA PART 2 | Approved | 157720.28 | 0 | 2026-04-30
TIKAMGARH / TIKAMGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707006080/WC/VB/YD/22012035336256 — talaiya jeernoddhar karya pureniya | Approved | 0 | 0 | 2026-08-15
TIKAMGARH / TIKAMGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1707006080/WC/VB/YD/22012035336257 — boalder check lambu suda dharampura | Approved | 0 | 0 | 2026-08-15
TIKAMGARH / TIKAMGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707006080/WC/VB/YD/22012035336260 — naveen talab nirman hashri ke pass | Approved | 0 | 0 | 2026-08-15
TIKAMGARH / TIKAMGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1707006080/WC/VB/YD/22012035336263 — roof water harvesting aganwadi pureniya | Approved | 0 | 0 | 2026-08-15
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1707006080/WC/YD/22012035307611 — roof water harvesting madhyamik vidyalay pureniya | Ongoing | 184300.16 | 0 | 2025-12-20
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1707006080/WC/YD/22012035307614 — roof water harvesting samudaik bhavan | Ongoing | 184661.91 | 0 | 2025-12-19
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1707006080/WC/YD/22012035307619 — roof water harvesting aganwadi pureniya | Approved | 184369.4 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1707006080/WC/YD/22012035308014 — dug well recharge pit nirman peyjal koop ke pass | Approved | 25899.46 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1707006080/WC/YD/22012035310583 — Dug well recharge pit nirman peyjal koop khirka ke pass | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1707006080/WC/YD/22012035310585 — Dug well recharge pit nirman gaon ke peyjal koop ke pass | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1707006080/WC/YD/22012035317179 — Percolation tank nirman lambu ke pass suda dharmpura | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1707006080/WC/YD/22012035317186 — loose boalder nirman lambu pahadi 2 | Approved | 0 | 0 | 2025-04-14
TIKAMGARH / TIKAMGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone Boulder Gully Plug for Community | Boulder Check/Gully Plug | 1707006080/WC/YD/22012035317187 — loose boalder nirman bagaj mata ke pass | Approved | 0 | 0 | 2025-04-14