## Work List
Exported on: 2026-10-09 02:12:55
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: GOHANI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHATARPUR / GAURIHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1708001064/AV/22012034399552 — आंगनवाड्ी भवन निर्माण केन्‍द्र क्र. 03 | Ongoing | 180000 | 0 | 2019-08-22
CHHATARPUR / GAURIHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Line Plantation of Horticulture Trees for Community | Plantation | 1708001064/DP/22012034580432 — samudayik braksharopan kary maunibaba sthan ke pas | Ongoing | 572101.37 | 0 | 2023-08-12
CHHATARPUR / GAURIHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708001064/IF/22012035215310 — Khettalab Gokul/ shukriya prajapati | New | 0 | 0 | 2024-01-25
CHHATARPUR / GAURIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1708001064/IF/22012035266679 — पशु शेड निर्माण कार्य दीनानाथ / महाप्रसाद पाल | Ongoing | 128277.18 | 0 | 2025-02-19
CHHATARPUR / GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708001064/IF/22012035328986 — खेत तालाब निर्माण कार्य ईश्वरदीन / स्वामीदीन बसोर | Approved | 0 | 0 | 2025-04-02
CHHATARPUR / GAURIHAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1708001064/IF/22012035375359 — Jgsa koopricharge pit natthu/ lotan prajapati | Ongoing | 25899.46 | 0 | 2025-05-03
CHHATARPUR / GAURIHAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1708001064/IF/22012035375373 — JGSA2025 kup richarge pit shukhdew prajapati | Ongoing | 25899.46 | 0 | 2025-05-02
CHHATARPUR / GAURIHAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1708001064/IF/22012035385944 — Jgsa2025 Koop richarge pit ramprasad prajapati/ramasre | Approved | 0 | 0 | 2025-04-14
CHHATARPUR / GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1708001064/IF/22012035538139 — पशुशेड निर्माण कार्य कमलेश / भगवानदास शिवहरे | Approved | 0 | 0 | 2025-04-14
CHHATARPUR / GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708001064/IF/22012035632988 — एक बगिया मां के नाम कार्य रोशनी / आशीष मिश्रा | New | 0 | 0 | 2025-08-15
CHHATARPUR / GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708001064/IF/22012035632989 — एक बगिया मां के नाम कार्य रोशनी / आशीष मिश्रा | Ongoing | 269387.37 | 31972 | 2025-10-29
CHHATARPUR / GAURIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/4954991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120382978 | Ongoing | 27000 | 0 | 2025-03-20
CHHATARPUR / GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/5999799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102988200 | Ongoing | 27000 | 6600 | 2026-06-10
CHHATARPUR / GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/5999826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117459335 | Ongoing | 27000 | 0 | 2026-06-10
CHHATARPUR / GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/5999876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113900730 | Ongoing | 27000 | 0 | 2026-04-12
CHHATARPUR / GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/6000853 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145668829 | Ongoing | 27000 | 0 | 2026-04-12
CHHATARPUR / GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/6000855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145669266 | Ongoing | 27000 | 0 | 2026-04-12
CHHATARPUR / GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/6000856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145669280 | Ongoing | 27000 | 0 | 2026-04-12
CHHATARPUR / GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/6003109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113708734 | Ongoing | 27000 | 0 | 2026-04-12
CHHATARPUR / GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/6003138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124048108 | Ongoing | 27000 | 0 | 2026-06-10
CHHATARPUR / GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/6003270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113900810 | Ongoing | 27000 | 0 | 2026-06-10
CHHATARPUR / GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/6003503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126428081 | Ongoing | 27000 | 0 | 2026-06-10
CHHATARPUR / GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/6003777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126422534 | Ongoing | 27000 | 3300 | 2026-06-10
CHHATARPUR / GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/6070285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113727422 | Ongoing | 27000 | 10200 | 2026-09-04
CHHATARPUR / GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/6085384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124799834 | Approved | 27000 | 0 | 2026-03-20
CHHATARPUR / GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001064/IF/IAY/6098825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148181847 | Approved | 27000 | 0 | 2026-03-14
CHHATARPUR / GAURIHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708001064/RC/22012034844864 — सी सी रोड निर्माण मुन्नीलाल केवट के मकान से जयराम अहिरवार के मकान तक | Ongoing | 77000 | 0 | 2025-07-14
CHHATARPUR / GAURIHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708001064/RC/22012034844865 — सी सी रोड निर्माण मेवालाल श्रीवास के मकान से दुर्जन केवट के मकान तक | Ongoing | 77000 | 0 | 2025-07-14
CHHATARPUR / GAURIHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708001064/RC/22012034850292 — सीसी रोड सह नाली निर्माण कार्य सुघरा अनुरागी के मकान से महेश शुक्‍ला के मकान तक | Ongoing | 130000 | 0 | 2025-12-02
CHHATARPUR / GAURIHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708001064/RC/22012034850305 — सीसी रोड सह नाली निर्माण कार्य बारेलाल प्रजापति के मकान से मातादीन प्रजापति के मकान तक | Ongoing | 96000 | 0 | 2025-12-02
CHHATARPUR / GAURIHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1708001064/RS/22012034647632 — सामुदायिक स्वच्छता परिसर निर्माण कार्य महतेबाबा तालाब के पास | Ongoing | 44000 | 0 | 2022-03-26
CHHATARPUR / GAURIHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Horticulture -Community / Line Plantation of Horticulture Trees for Community | Plantation | 1708001064/WC/22012035097561 — अमृत वाटिका निर्माण कार्य देवी तैलीय के पास गौहानी | Ongoing | 54569.95 | 0 | 2023-11-02