## Work List
Exported on: 2026-10-05 01:15:00
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: ALIPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHATARPUR / NOWGOAN | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1708003017/AV/22012034659642 — नाली निर्माण कार्य चतुर्भुज प्रजापति के घर से कल्लू अहिरवार के घर तक | Physically Completed | 69000 | 0 | 2025-04-15 | 2026-08-03
CHHATARPUR / NOWGOAN | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1708003017/AV/22012034665876 — बाउन्ड्रीवॉल निर्माण कार्य आंगनबाड़ी केन्द्र क्रमांक 04 ग्राम पंचायत अलीपुरा | Physically Completed | 24000 | 0 | 2025-05-14 | 2026-08-03
CHHATARPUR / NOWGOAN | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1708003017/AV/22012034666375 — पेवर्स ब्लाक निर्माण कार्य खास कलम मन्दिर के पास ग्राम पंचायत अलीपुरा | Approved | 48000 | 0 | 2025-04-04
CHHATARPUR / NOWGOAN | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1708003017/AV/22012034666376 — टीन शेड निर्माण कार्य गौठान ग्राम पंचायत अलीपुरा | Approved | 94000 | 0 | 2025-04-04
CHHATARPUR / NOWGOAN | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1708003017/IF/22012034551370 — हितैशी कपिलधारा कूप निर्माण कार्य, रामदयाल/लाल्ले सौर जाॅबकार्ड नं0 738 ग्राम पंचायत अलीपुरा | Ongoing | 243792.43 | 0 | 2020-05-14
CHHATARPUR / NOWGOAN | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1708003017/IF/22012034551372 — हितैशी कपिलधारा कूप निर्माण कार्य, रामस्वरूप/पोटा अहिरवार जाॅबकार्ड नं0 143 ग्राम पंचायत अलीपुरा | Ongoing | 243792.43 | 0 | 2020-05-14
CHHATARPUR / NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1708003017/IF/22012035459232 — कपिलधारा कूप निर्माण कार्य श्री रामकिशोर, शिवनारायण, बगैरह तनय हरीराम ग्रा0पंचायत अलीपुरा | Approved | 0 | 0 | 2025-04-15
CHHATARPUR / NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003017/IF/22012035622839 — एक बगिया माँ के नाम श्रीमती रश्मि दुबे पति श्री विकास दुबे भू0 स्वामी सम्बंध पति ग्रा0अलीपुरा | Ongoing | 284704.22 | 65346.24 | 2025-10-25
CHHATARPUR / NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003017/IF/22012035639840 — एक बगिया माँ के नाम श्रीमती तारा देवी भदौरिया पति रामस्वरूप भदौरियाभू0 स्वामी सम्बंध पति ग्रा0अलीपुर | New | 0 | 0 | 2025-08-15
CHHATARPUR / NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003017/IF/22012035639882 — एक बगिया माँ के नाम श्रीमती तारा देवी भदौरिया पति रामस्वरूप भदौरियाभू0 स्वामी सम्बंध पति ग्रा0अलीपुर | Ongoing | 284704.22 | 68832 | 2025-11-20
CHHATARPUR / NOWGOAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/1142505 — Construction of IAY House -IAY REG. NO. MP-08-003-017-001/1655 | Approved | 27000 | 0 | 2016-03-31
CHHATARPUR / NOWGOAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/199717 — Construction of IAY House -IAY REG. NO. MP-08-003-017-001/0425 | Approved | 27000 | 0 | 2016-03-21
CHHATARPUR / NOWGOAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/201095 — Construction of IAY House -IAY REG. NO. MP-08-003-017-001/6722 | Approved | 27000 | 0 | 2016-03-31
CHHATARPUR / NOWGOAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/201096 — Construction of IAY House -IAY REG. NO. MP-08-003-017-001/8220 | Approved | 27000 | 0 | 2016-03-31
CHHATARPUR / NOWGOAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/201102 — Construction of IAY House -IAY REG. NO. MP-08-003-017-001/9136 | Approved | 27000 | 0 | 2016-03-31
CHHATARPUR / NOWGOAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/201104 — Construction of IAY House -IAY REG. NO. MP-08-003-017-001/425220 | Approved | 27000 | 0 | 2016-03-31
CHHATARPUR / NOWGOAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/201106 — Construction of IAY House -IAY REG. NO. MP-08-003-017-001/7119 | Approved | 27000 | 0 | 2016-03-31
CHHATARPUR / NOWGOAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/201112 — Construction of IAY House -IAY REG. NO. MP-08-003-017-001/8302 | Approved | 27000 | 0 | 2016-03-31
CHHATARPUR / NOWGOAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/203542 — Construction of IAY House -IAY REG. NO. MP-08-003-017-001/6676 | Approved | 27000 | 0 | 2016-03-31
CHHATARPUR / NOWGOAN | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/57073 — Construction of IAY House -IAY REG. NO. MP-08-003-017-001/6648 | Approved | 27000 | 0 | 2015-12-22
CHHATARPUR / NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5779812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126930431 | Physically Completed | 27000 | 300 | 2025-12-10 | 2026-09-22
CHHATARPUR / NOWGOAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5780227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126286332 | Approved | 27000 | 0 | 2025-02-17
CHHATARPUR / NOWGOAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5781769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126296392 | Approved | 27000 | 0 | 2025-02-17
CHHATARPUR / NOWGOAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5860655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126594710 | Approved | 27000 | 0 | 2025-02-25
CHHATARPUR / NOWGOAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5860814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125587143 | Approved | 27000 | 0 | 2025-03-18
CHHATARPUR / NOWGOAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5861055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126571819 | Approved | 27000 | 0 | 2025-02-17
CHHATARPUR / NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5893754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126944235 | Physically Completed | 27000 | 19500 | 2026-05-17 | 2026-10-01
CHHATARPUR / NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5893879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126958799 | Physically Completed | 27000 | 21300 | 2026-05-27 | 2026-10-01
CHHATARPUR / NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5894094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126581108 | Physically Completed | 27000 | 21300 | 2026-05-27 | 2026-10-01
CHHATARPUR / NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5894097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123298174 | Ongoing | 27000 | 21600 | 2026-06-09
CHHATARPUR / NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5909067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126945182 | Physically Completed | 27000 | 19500 | 2026-05-17 | 2026-10-01
CHHATARPUR / NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5913567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126960551 | Physically Completed | 27000 | 11500 | 2026-05-17 | 2026-09-22
CHHATARPUR / NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5928097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125614802 | Physically Completed | 27000 | 15300 | 2026-05-27 | 2026-09-22
CHHATARPUR / NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5977205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122715327 | Physically Completed | 27000 | 21300 | 2026-05-27 | 2026-10-01
CHHATARPUR / NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/5985908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123288832 | Ongoing | 27000 | 21600 | 2026-06-09
CHHATARPUR / NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/6083349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123295709 | Ongoing | 27000 | 18000 | 2026-07-18
CHHATARPUR / NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003017/IF/IAY/6089199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126933208 | Ongoing | 27000 | 18000 | 2026-07-18
CHHATARPUR / NOWGOAN | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708003017/RC/22012034842830 — सी0सी0रोड एवं नाली निर्माण श्री दुर्गा महाराज के घर से राम प्रकाश प्रजापति के घर तक ग्रापंचा.अलीपुरा | Physically Completed | 173000 | 0 | 2026-03-16 | 2026-08-03
CHHATARPUR / NOWGOAN | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708003017/RC/22012034844735 — सी0सी0रोड निर्माण कार्य श्री विनोद सेन के घर से बाबू रैकवार एवं संदीप के घर तक एवं जमुना बाल्मीक के | Physically Completed | 66000 | 0 | 2026-04-27 | 2026-08-03
CHHATARPUR / NOWGOAN | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708003017/RC/22012034850551 — सी0सी0रोड निर्माण कार्य मानिक कुशवाहा के घर से मनसुख कुशवाहा के घर तक ग्राम पंचायत अलीपुरा | Physically Completed | 230000 | 0 | 2026-01-17 | 2026-08-03
CHHATARPUR / NOWGOAN | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708003017/RC/22012034850552 — सी0सी0रोड निर्माण कार्य रविदास मंदिर से कलारी की ओर ग्राम पंचायत अलीपुरा | Physically Completed | 51000 | 0 | 2026-01-06 | 2026-08-03
CHHATARPUR / NOWGOAN | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1708003017/RS/22012034527695 — SLWM सामुदायिक नाडिप टांका निर्माण कार्य 12 नग ग्राम पंचायत अलीपुरा | Ongoing | 297909.27 | 0 | 2021-07-01
CHHATARPUR / NOWGOAN | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1708003017/RS/VB/YD/22012035140352 — Constr of NADEP Compost structure for 1 | Approved | 0 | 0 | 2026-08-15
CHHATARPUR / NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1708003017/WC/22012035297463 — डगवेल रिचार्ज निर्माण कार्य सार्वजनिक कुआ सौरयाना के पास ग्राम पंचायत अलीपुरा | Approved | 4000 | 0 | 2025-04-04
CHHATARPUR / NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708003017/WC/22012035297469 — रूफ वाटर हार्वेस्टिम निर्माण कार्य आंगनबाड़ी केन्द्र क्रमांक 04 में ग्राम पंचायत अलीपुरा | Approved | 18000 | 0 | 2025-04-04
CHHATARPUR / NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708003017/WC/22012035297472 — रूफ वाटर हार्वेस्टिम निर्माण कार्य प्राथमिक शाला भवन धर्मपुरा ग्राम पंचायत अलीपुरा | Approved | 18000 | 0 | 2025-04-04
CHHATARPUR / NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708003017/WC/22012035297477 — रूफ वाटर हार्वेस्टिम निर्माण कार्य शा0प्रा0शाला सौरयाना ग्राम पंचायत अलीपुरा | Approved | 18000 | 0 | 2025-04-04
CHHATARPUR / NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708003017/WC/22012035297480 — रूफ वाटर हार्वेस्टिम निर्माण कार्य शा0प्राथमिक शाला विपतपुरा ग्राम पंचायत अलीपुरा | Approved | 18000 | 0 | 2025-04-25
CHHATARPUR / NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708003017/WC/22012035297483 — रूफ वाटर हार्वेस्टिम निर्माण कार्य आंगनबाड़ी केन्द्र क्रमांक 05 ग्राम पंचायत अलीपुरा | Approved | 18000 | 0 | 2025-04-04
CHHATARPUR / NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708003017/WC/22012035297488 — रिचार्ज निर्माण कार्य प्रभू ढ़ीमर के मकान के पास ग्राम पंचायत अलीपुरा | Approved | 4000 | 0 | 2025-04-04