## Work List
Exported on: 2026-10-21 07:13:47
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: MALPURA
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHATARPUR / CHHATARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1708004041/IF/22012034608872 — NRLM PASHU SHED NIRMAN KARYA SMT. KAMLI/ACHCHHE LAL AHIRWAR | Physically Completed | 101804.91 | 360 | 2020-09-30 | 2020-10-27
CHHATARPUR / CHHATARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1708004041/IF/22012034608901 — NRLM PASHU SHED NIRMAN KARYA SMT. MANTI/RAGHUNATH YADAV | Physically Completed | 101804.91 | 180 | 2020-09-30 | 2020-10-27
CHHATARPUR / CHHATARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Poultry Shelter for Individuals / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1708004041/IF/22012034614004 — NRLM PASHUSHED NIRMAN KARYA RAJKUWAR PATHAK W/O JAGDESH PATHAK | Physically Completed | 101804.91 | 360 | 2020-09-30 | 2020-10-27
CHHATARPUR / CHHATARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Poultry Shelter for Individuals / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1708004041/IF/22012034614006 — NRLM PASHUSHED NIRMAN KARYA ROOPA AHIRWAR W/O KHUMAN AHIRWAR | Physically Completed | 101804.91 | 360 | 2020-09-30 | 2020-10-27
CHHATARPUR / CHHATARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1708004041/IF/22012034654216 — mad badhan nirrman karya jagannath ahirwar | Physically Completed | 76587.49 | 27864 | 2021-03-08 | 2022-01-22
CHHATARPUR / CHHATARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1708004041/IF/22012034654221 — mad badha nirman karya narendra tiwari | Physically Completed | 76587.49 | 144 | 2021-03-08 | 2022-01-22
CHHATARPUR / CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plntation Horti-TreesIndividual / Wasteland Block Plantation of Horticulture Trees for Individuals | Plantation | 1708004041/IF/22012034673010 — MED BADHAN KARYA NAVAL GANGELE S/O MATHURA PRASAD GANGELE MALPURA | Physically Completed | 76587.49 | 17100 | 2021-04-12 | 2022-01-22
CHHATARPUR / CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Line Plantation Forstry Trees-Individual / Wasteland Line Plantation of Forestry Trees for Individuals | Plantation | 1708004041/IF/22012034674181 — MED BADHAN KARYA sukiya kushwaha s/o ramlal kushwaha malpura | Physically Completed | 76587.49 | 10368 | 2021-04-12 | 2022-01-22
CHHATARPUR / CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Line Plantation Forstry Trees-Individual / Wasteland Line Plantation of Forestry Trees for Individuals | Plantation | 1708004041/IF/22012034674194 — MED BADHAN KARYA BABULAL TIWARI KHANDERA | Physically Completed | 76587.49 | 1140 | 2021-04-12 | 2022-01-22
CHHATARPUR / CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Line Plantation Forstry Trees-Individual / Wasteland Line Plantation of Forestry Trees for Individuals | Plantation | 1708004041/IF/22012034674222 — MED BADHAN KARYA KAILASH PRASAD TIWARI | Physically Completed | 76587.49 | 4560 | 2021-04-05 | 2022-01-22
CHHATARPUR / CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plntation Horti-TreesIndividual / Wasteland Block Plantation of Horticulture Trees for Individuals | Plantation | 1708004041/IF/22012034674246 — MED BADHAN KARYA KAMTA AHIRWAR S/O SUKKA AHIRWAR MALPURA | Physically Completed | 76587.49 | 9120 | 2021-04-12 | 2022-01-22
CHHATARPUR / CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Line Plantation Forstry Trees-Individual / Wasteland Line Plantation of Forestry Trees for Individuals | Plantation | 1708004041/IF/22012034675279 — MED BADHAN KARYA MITHALA DEVI TIWARI W/O KASHIPARASAD TIWARI KHNDEWRA | Physically Completed | 76587.49 | 2280 | 2021-04-12 | 2022-01-22
CHHATARPUR / CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1708004041/IF/22012034767206 — MED BADHAN NIRMAN KARYA BHAGWATI AHIRWAR GP MALPURA | Physically Completed | 73060.06 | 45222 | 2021-06-07 | 2022-01-22
CHHATARPUR / CHHATARPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line-coast Plntation-Farm Forstry Trees-Individual / Along the coast Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1708004041/IF/22012035139891 — NANDAN PHALODHYAN KARYA KAILASH PRASAD TIWARI | Physically Completed | 123681.2 | 120178.78 | 2023-10-04 | 2026-06-02
CHHATARPUR / CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004041/IF/22012035292250 — कपिलधारा कूप निर्माण कार्य शंकर लाल अहिरवार | Physically Completed | 425773.05 | 369357.36 | 2025-02-21 | 2026-04-23
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1708004041/IF/22012035524629 — KHATTALAB NIRMANKRYA GOVERDHAN GANGELE GP MALPURA | Physically Completed | 55865.38 | 26942 | 2025-05-23 | 2026-05-03
CHHATARPUR / CHHATARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004041/IF/9993679330 — IAY MISSION BHAGBANDAS SEN | Physically Completed | 14310 | 1908 | 2015-10-08 | 2020-12-18
CHHATARPUR / CHHATARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004041/RC/22012034671245 — C.C. ROAD NIRMAN NALI SAHIT DUPEDI BABBA JU SE RNU PATHAK KE GHAR KI OR | Physically Completed | 75000 | 30498 | 2024-01-24 | 2026-06-04
CHHATARPUR / CHHATARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004041/RC/22012034835279 — सी. सी. रोड निर्माण कार्य शकूरचन्‍द्र अहिरवार के घर से मोहन अहिरवार के घर की ओर | Physically Completed | 27000 | 20412 | 2025-02-03 | 2026-05-03
CHHATARPUR / CHHATARPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004041/RS/22012034440277 — SBM SHOUCHALAY NIRMAN KARY PARSHRAM TIWARI | Physically Completed | 12000 | 12000 | 2019-03-12 | 2021-01-19
CHHATARPUR / CHHATARPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004041/RS/22012034440278 — SBM SHOUCHALAY NIRMAN KARY DHARMJEET VISHWAKARMA | Physically Completed | 12000 | 12000 | 2019-03-12 | 2021-01-19
CHHATARPUR / CHHATARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1708004041/RS/22012035134574 — नाली निर्माण कार्य रतन कुशवाहा के घर से प्रा0 शाला मलपुरा | Physically Completed | 37496 | 27923.5 | 2024-12-29 | 2026-04-23
CHHATARPUR / CHHATARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708004041/WC/22012034562039 — KHEAT TALAAB NIRAMAN LEELA VISHWAKARMAN KHANDEVERA | Physically Completed | 318851.21 | 13764 | 2020-08-05 | 2020-11-03
CHHATARPUR / CHHATARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708004041/WC/22012034587316 — KHET TALAAB NIRMAN KARYA TANTU AHIRWAR GP MALPURA | Physically Completed | 332962.02 | 165868 | 2020-12-31 | 2022-01-18
CHHATARPUR / CHHATARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708004041/WC/22012034610712 — KHET TALAAB NIRMAN KARYA VIHARI AHIRWAR KHANDEWRA | Physically Completed | 332962.02 | 13680 | 2021-02-10 | 2021-10-28
CHHATARPUR / CHHATARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1708004041/WC/22012034626223 — KHET TALAB NIRMAN GORELAL AHIRWAR KHANDEWRA | Physically Completed | 332962.02 | 3420 | 2021-04-12 | 2022-01-22
CHHATARPUR / CHHATARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1708004041/WC/22012034728354 — ROOF WATER HARVESTING STURCTURE M. S. GP MALPURA | Physically Completed | 22173.14 | 193 | 2021-05-31 | 2022-01-18
CHHATARPUR / CHHATARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1708004041/WC/22012034728369 — ROOF WATER HARVESTING STURCTURE P. S. GP MALPURA | Physically Completed | 22173.14 | 193 | 2021-05-31 | 2022-01-18
CHHATARPUR / CHHATARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1708004041/WC/22012034728383 — ROOF WATER HARVESTING STURCTURE AGANVADI BHAVAN GP MALPURA | Physically Completed | 22173.14 | 193 | 2021-05-31 | 2022-01-18
CHHATARPUR / CHHATARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1708004041/WC/22012034728409 — ROOF WATER HARVESTING STURCTURE P. S. KHANDEWRA | Physically Completed | 22173.14 | 193 | 2021-05-31 | 2022-01-18
CHHATARPUR / CHHATARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1708004041/WC/22012034728420 — ROOF WATER HARVESTING STURCTURE AGANVADI BHAVAN GP KHANDEWRA | Physically Completed | 22173.14 | 193 | 2021-05-31 | 2022-01-18
CHHATARPUR / CHHATARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1708004041/WC/22012035123286 — MINI PERCOLATION TANK KARYA PURANI TALIYA KE PAAS KHANDEVRA | Physically Completed | 489864.85 | 294056.25 | 2024-04-09 | 2026-05-20
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1708004041/WC/22012035296078 — SAMUDAYAK SOKPIT NIRMAN PRATHMIK SHALA KE PASS | Physically Completed | 12000 | 11845.02 | 2025-05-05 | 2026-04-28
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708004041/WC/22012035298677 — SARVAJANIK KHET TALAB NIRMAN GAUSHALA KE AAGE KE OOR KHANDEVRA | Physically Completed | 433814.94 | 142162.3 | 2025-05-23 | 2026-06-29
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004041/WC/22012035312073 — एनीकट निर्माण कार्य कुड़ी घाट नाला अंजनी मंदिर के पास | Physically Completed | 76383 | 69948 | 2025-06-26 | 2026-05-03
CHHATARPUR / CHHATARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1708004041/WH/22012034450686 — TALAB GHAT NIRMAN & VISTARIKARAN KARYA MALPURA | Physically Completed | 50000 | 45162 | 2021-11-22 | 2022-01-24