## Work List
Exported on: 2026-10-02 08:46:57
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: DHAMCHI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHATARPUR / CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708004049/IF/22012035258797 — NANDAN FALUDHYAN KARY MUKESH AHIRWAR | Approved | 0 | 0 | 2024-06-18
CHHATARPUR / CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Bio-drainage Plantation for Individual | Plantation | 1708004049/IF/22012035258808 — NANDAN FALUDHYAN KARY HARJU PAL | Approved | 0 | 0 | 2024-06-18
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1708004049/IF/22012035458569 — khet talab jagdamba yadav | Ongoing | 199573.29 | 0 | 2025-05-07
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1708004049/IF/22012035458634 — khet talab sheela bai banskar | Ongoing | 199573.29 | 0 | 2025-05-07
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1708004049/IF/22012035458686 — khet talab bali pal | Ongoing | 199573.29 | 0 | 2025-05-07
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1708004049/IF/22012035581991 — nandan fal uddhyan pan raja wo mulayam | Approved | 0 | 0 | 2025-05-01
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708004049/IF/22012035603696 — एक बगिया मॉं के नाम श्रीमती पान राजा पति श्री मुलायम सिंह (भूमि स्वावमी मुलायम सिंह पति) | Ongoing | 284216.45 | 12561.96 | 2025-09-07
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708004049/IF/22012035603729 — एक बगिया मॉं के नाम श्रीमती भूरी बाई अहिरवार पति उत्तम अहिरवार (भूमि स्वामी उत्तम अहिरवार पति) | Ongoing | 284007.13 | 0 | 2025-09-07
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708004049/IF/22012035604151 — एक बगिया मॉं के नाम श्रीमती प्रवेश राजा पति अर्जुन सिंह परमार (भूमि स्वामी अर्जुन सिंह परमार पति) | Ongoing | 284216.45 | 12961.96 | 2025-09-11
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708004049/IF/22012035604197 — एक बगिया मॉं के नाम श्रीमती मल्लू पाल पति कमलापत पाल (भूमि स्वामी कमलापत पाल पति) | Ongoing | 284216.45 | 0 | 2025-09-07
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708004049/IF/22012035604235 — एक बगिया मॉं के नाम श्रीमती राजकुमारी पाल पति हरजू पाल (भूमि स्वामी हरजू पाल पति) | Ongoing | 284216.45 | 0 | 2025-09-05
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/1030615 — Construction of IAY House -IAY REG. NO. MP2374913 | Ongoing | 27000 | 0 | 2026-03-16
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5332327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122842040 | Physically Completed | 23490 | 0 | 2025-05-06 | 2026-08-09
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5899518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122933976 | Ongoing | 27000 | 0 | 2026-03-16
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5899579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124189485 | Physically Completed | 27000 | 6300 | 2026-03-16 | 2026-09-27
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5899646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122935914 | Physically Completed | 27000 | 11400 | 2026-03-16 | 2026-09-13
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5899670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117633406 | Ongoing | 27000 | 0 | 2026-03-16
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5899672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120586480 | Physically Completed | 27000 | 4200 | 2026-03-16 | 2026-09-13
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5899774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117842648 | Ongoing | 27000 | 6000 | 2026-03-16
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5899815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122872943 | Ongoing | 27000 | 8400 | 2026-03-16
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5899853 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117160721 | Physically Completed | 27000 | 12000 | 2026-03-16 | 2026-09-20
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5899916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117628268 | Ongoing | 27000 | 0 | 2026-03-16
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5899978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122870478 | Ongoing | 27000 | 8400 | 2026-03-16
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5899980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117633219 | Ongoing | 27000 | 4200 | 2026-03-16
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5899981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117633310 | Ongoing | 27000 | 0 | 2026-03-16
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5899982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117633359 | Ongoing | 27000 | 0 | 2026-03-16
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5900005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117628604 | Ongoing | 27000 | 0 | 2026-03-09
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5900028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118121277 | Ongoing | 27000 | 0 | 2026-03-09
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5900109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119688679 | Ongoing | 27000 | 0 | 2026-03-09
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5900136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125810389 | Ongoing | 27000 | 0 | 2026-03-09
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5900273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125813389 | Ongoing | 27000 | 0 | 2026-03-09
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5900285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117860748 | Ongoing | 27000 | 8100 | 2026-03-09
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/5900296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124184560 | Ongoing | 27000 | 8100 | 2026-03-09
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/790330 — Construction of IAY House -IAY REG. NO. MP1814372 | Ongoing | 27000 | 0 | 2026-03-09
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/791831 — Construction of IAY House -IAY REG. NO. MP1926750 | Ongoing | 27000 | 0 | 2026-03-09
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/794748 — Construction of IAY House -IAY REG. NO. MP2144525 | Ongoing | 27000 | 0 | 2026-03-09
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708004049/IF/IAY/797891 — Construction of IAY House -IAY REG. NO. MP2380978 | Ongoing | 27000 | 0 | 2026-03-09
CHHATARPUR / CHHATARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Dev of Silvipasture Grassslands for Community / Raising of Fodder Cultivation for Community | Grass Land Development | 1708004049/LD/22012034533390 — CHARAGAAH VIKASH KARYA GAUSHALA KE PAAS GRAM KATRA | Ongoing | 1459575.64 | 0 | 2021-01-28
CHHATARPUR / CHHATARPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708004049/RC/22012034837709 — सी. सी. रोड निर्माण कार्य प्रा0 शाला से सांसद चौपाल तक | Ongoing | 129592 | 0 | 2025-04-16
CHHATARPUR / CHHATARPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1708004049/RC/22012034842517 — SUDOR SADAK NIRMAN KARY PANCHYAT BHAWAN SE JAMUNIYAPURWA TAK DHAMCHI | Ongoing | 889000 | 0 | 2025-05-15
CHHATARPUR / CHHATARPUR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708004049/RC/22012034849856 — सीसी रोड निर्माण कार्य फोर लाईन (कल्लू यादव के मकान) से धामची की ओर धामची | Ongoing | 150000 | 1305.7 | 2026-05-16
CHHATARPUR / CHHATARPUR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708004049/RC/22012034849858 — सीसी रोड निर्माण कार्य तिजवा रैकवार के घर से मैन रोड तक (झिरनपुरवा) धामची | Ongoing | 158000 | 1649.73 | 2026-05-14
CHHATARPUR / CHHATARPUR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Groups / Construction of Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1708004049/RS/22012035135235 — NALI NIRMAN KARYA FOUR LINE SE SARVAJANIK KOOP KATARA TAK DHAMCHI | Ongoing | 73000 | 0 | 2026-05-26
CHHATARPUR / CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1708004049/WC/22012035052992 — GABION NIRMN KARY GANDHINDHI NAGAR NALA NO-2 | Ongoing | 145115.15 | 0 | 2024-03-17
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708004049/WC/22012035309645 — NAVEEN TALAB NIRMAN KARYA RAM LAXMAN KE PASS TEEKAR DHAMCHI | Approved | 0 | 0 | 2025-04-14
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1708004049/WC/22012035313284 — parcolation tank nirman kary seela bai ke pass | Approved | 0 | 0 | 2025-04-01
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1708004049/WC/22012035313289 — samudayik khet talab seela bai ke pass | Approved | 0 | 0 | 2025-04-01
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708004049/WC/22012035326185 — NAVEEN TALAB NIRMAN KARY MOTE GANDHINAGAR KE PASS DHAMACHI | Approved | 0 | 0 | 2025-10-02
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708004049/WC/22012035326188 — NAVEN TALAB NIRMAN KARY GAUSHALA KE PASS KATRA DHAMCHI | Approved | 0 | 0 | 2025-10-02