## Work List
Exported on: 2026-09-27 10:09:11
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BRAJPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHATARPUR / CHHATARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1708004077/AV/22012034660298 — Khel medan nirmad H.S.School brajpura | Approved | 261110.41 | 0 | 2024-08-16
CHHATARPUR / CHHATARPUR | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1708004077/AV/22012034664788 — ANGANWADI BHAWAN NIRMAN KARY KINDRA NO 2 BRAJPURA | Ongoing | 99000 | 5700 | 2026-08-01
CHHATARPUR / CHHATARPUR | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1708004077/AV/VB/YD/22012034669470 — Constr of CmpOnd wall for gov schools madhyamik shala | New | 0 | 0 | 2026-05-05
CHHATARPUR / CHHATARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1708004077/DP/VB/22012034630832 — braksharopan karya pragteswar balaji dham parisar grampanchayat Brajpura | Approved | 0 | 0 | 2026-06-05
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1708004077/IF/22012035490339 — JGSA dugwell recharge pit nirmad hitesi koop paradise ahirwar ke pas grampanchayat brajpura | Approved | 22007.92 | 0 | 2025-04-14
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708004077/IF/22012035594212 — एक बगिया माँ के नाम श्रीमती रति पटेल पत्नी लखन पटेल (भूस्वामी श्री लखन पटेल पति) | Ongoing | 284038.6 | 0 | 2025-08-27
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708004077/IF/22012035594213 — एक बगिया माँ के नाम दीप कुमारी पटेल पत्नी श्री कैलाश पटेल (भूस्वामी श्री हरगोविन्द पटेल ससुर) | Ongoing | 284038.6 | 0 | 2025-08-27
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708004077/IF/22012035596621 — एक बगिया मॉं के नाम श्रीमती रामकुंवर पटेल पति भगवत पटेल (भूस्वामी श्री रामकृपाल पटेल ससुर) | Ongoing | 283820.78 | 0 | 2025-09-03
CHHATARPUR / CHHATARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/44783 — Construction of IAY House -IAY REG. NO. MP-08-004-077-001/13696 | Approved | 27000 | 0 | 2015-11-30
CHHATARPUR / CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1708004077/LD/22012034588714 — muktidham nirman karya jabaran ki puliya ke pass | Ongoing | 329608.4 | 0 | 2023-06-15
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1708004077/WC/22012035265865 — मिनी पर्कोलेशन टैंक निर्माण जवाहर नाला पर ग्राम पंचायत बृजपुरा | Approved | 199464.32 | 0 | 2025-04-14
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708004077/WC/22012035288761 — ROOF WATER HARVESTING ANGANWADI BHAWAN | Approved | 11000 | 0 | 2025-04-04