## Work List
Exported on: 2026-10-04 08:50:11
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KADWAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHATARPUR / CHHATARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1708004082/AV/22012034660911 — गोठान निर्माण कार्य बछरौनिया कदवा | Approved | 100000 | 0 | 2024-08-16
CHHATARPUR / CHHATARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1708004082/IF/22012034974465 — KAPIL DHARA KOOP NIRMAN KARYA BHUMAANIDEEN YADAV | Ongoing | 402078.01 | 0 | 2023-02-09
CHHATARPUR / CHHATARPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Raising of Nursery for Individuals / Raising of Nursery for Individuals | Nursery Development | 1708004082/IF/22012035160761 — NANDAN PHALODHYAN KARYA POORAN LAL YADAV | Ongoing | 133212.69 | 0 | 2023-10-10
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708004082/IF/22012035405733 — khet talab nirman karya munnibai yadav | Ongoing | 398366.23 | 0 | 2025-05-24
CHHATARPUR / CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708004082/IF/22012035405850 — Dugwell recharge pit nirman karya Bhagwandas yadav | Approved | 25899.46 | 0 | 2025-04-01
CHHATARPUR / CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004082/IF/IAY/5935605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124299925 | Ongoing | 27000 | 14700 | 2026-06-03
CHHATARPUR / CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004082/IF/IAY/5938761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125342549 | Ongoing | 27000 | 20100 | 2026-06-10
CHHATARPUR / CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004082/IF/IAY/5939977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119676089 | Ongoing | 27000 | 5100 | 2026-04-22
CHHATARPUR / CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004082/IF/IAY/5940289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124304983 | Ongoing | 27000 | 18300 | 2026-06-03
CHHATARPUR / CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004082/IF/IAY/5979844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124536260 | Physically Completed | 27000 | 9300 | 2026-05-06 | 2026-08-30
CHHATARPUR / CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708004082/IF/IAY/5982030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124458250 | Ongoing | 27000 | 18600 | 2026-06-03
CHHATARPUR / CHHATARPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708004082/IF/IAY/628584 — Construction of IAY House -IAY REG. NO. MP1571743 | Approved | 27000 | 0 | 2017-02-08
CHHATARPUR / CHHATARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708004082/IF/IAY/72507 — Construction of IAY House -IAY REG. NO. MP-08-004-082-002/14634 | Approved | 27000 | 0 | 2015-10-09
CHHATARPUR / CHHATARPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1708004082/RS/22012035138320 — NALI NIRMAN KARYA ARJUN KE GHAR SE LEELA DHAR SEN KE GHAR KE OOR KANDWA | Approved | 78000 | 0 | 2025-04-14
CHHATARPUR / CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708004082/WC/22012035113361 — Sarvjanik koop nirman kary raipura | Ongoing | 573702.48 | 0 | 2024-03-16
CHHATARPUR / CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1708004082/WC/22012035147888 — MINI PERCOLATION TANK KARYA BAHERA NALA KE PAAS | Ongoing | 346535.73 | 0 | 2023-12-24
CHHATARPUR / CHHATARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1708004082/WC/22012035226488 — खेत तालाब निर्माण कार्य खजरी के खेत के पास | Approved | 0 | 0 | 2024-10-02
CHHATARPUR / CHHATARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708004082/WC/22012035251458 — सार्वजनिक कूप निर्माण कार्य मक्तिधाम राईपुरा | Approved | 0 | 0 | 2025-01-25
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708004082/WC/22012035282315 — PARCULATION TANK NIRMAN KARYA JORAN NALA RAIPURA | Approved | 0 | 0 | 2025-04-01
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1708004082/WC/22012035301395 — Dugwell recharge pit nirman karya sarvjanik koop toriya muhalla | Ongoing | 25899.46 | 0 | 2025-05-25
CHHATARPUR / CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1708004082/WC/22012035301399 — Dugwell recharge pit nirman karya sarvjanik koop raipura | Ongoing | 25899.46 | 0 | 2025-05-25
CHHATARPUR / CHHATARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004082/WC/VB/22012035332101 — Bolder Check dam Nirman Karya Ramdeen ke khet ke pass Kadwan | Approved | 0 | 0 | 2026-07-15
CHHATARPUR / CHHATARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004082/WC/VB/22012035332105 — Bolder Check dam Nirman Karya Manju ke khet ke pass Kadwan | Approved | 0 | 0 | 2026-07-15
CHHATARPUR / CHHATARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004082/WC/VB/22012035332111 — Bolder Check dam Nirman Karya kharga ke khet ke pass Kadwan | Approved | 0 | 0 | 2026-07-15
CHHATARPUR / CHHATARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004082/WC/VB/22012035332112 — Bolder Check dam Nirman Karya Battiya ke khet ke pass Kadwan | Approved | 0 | 0 | 2026-07-15
CHHATARPUR / CHHATARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004082/WC/VB/22012035332114 — Bolder Check dam Nirman Karya Jouvab Nala bariya ke pass Kadwan | Approved | 0 | 0 | 2026-07-15