## Work List
Exported on: 2026-10-26 08:56:27
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: VISHWA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHATARPUR / BADA MALEHARA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1708006018/AV/22012034638794 — शान्तिधाम निर्माण कार्य आदिवासी मरघट | Physically Completed | 330972.38 | 0 | 2023-12-22 | 2026-09-11
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708006018/IF/22012035422746 — खेत तालाब निर्माण कार्य हितग्राही मूलक सल्ला लोधी/मुलायम लोधी लघु सीमांक | Ongoing | 147621.16 | 0 | 2025-05-06
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708006018/IF/22012035559794 — JGSA -2025 हितेषी खेत तालाब निर्माण कार्य हनमत अहिरवार/दमरा अहिरवार ग्राम पंचायत विश्वा | Ongoing | 147621.16 | 0 | 2025-12-06
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006018/IF/IAY/4934353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100002957 | Ongoing | 27000 | 0 | 2025-05-10
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006018/IF/IAY/4934355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100002966 | Ongoing | 27000 | 0 | 2025-08-07
CHHATARPUR / BADA MALEHARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Bio-drainage Plantation for Community | Plantation | 1708006018/LD/22012034593970 — हितेषी नंदन फलोद्यान निर्माण कार्य जयराम दुबे/सीताराम दुबे | Ongoing | 160765.64 | 0 | 2023-08-24
CHHATARPUR / BADA MALEHARA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708006018/RC/22012034599026 — सी सी रोड निर्माण कार्य हज्जू अहिरवार के मकान से माध्यमिक शाला की ओर ग्राम पंचायत विश्वा Lenth 100 M | Ongoing | 67000 | 0 | 2021-11-25
CHHATARPUR / BADA MALEHARA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708006018/RC/22012034848354 — सी सी रोड निर्माण कार्य घनश्याम के मकान से नारायण सिंह के मकान तक ग्राम पंचायत विश्वा | Ongoing | 48000 | 0 | 2026-03-18
CHHATARPUR / BADA MALEHARA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708006018/RC/22012034848357 — सी सी रोड एवं नाली निर्माण कार्य सूर्यप्रकाश चौबे के मकान से सटोला अहिरवार के मकान तक एवं वीरन लोधी | Ongoing | 54000 | 0 | 2026-03-18
CHHATARPUR / BADA MALEHARA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1708006018/RS/22012035139533 — नाली निर्माण कार्य हरप्रसाद विश्वकर्मा के मकान से फूटन नाला तक ग्राम पंचायत विश्वा | Approved | 48000 | 0 | 2026-03-18
CHHATARPUR / BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708006018/WC/22012035228692 — सार्वजनिक खेत तालाब धुर पासी हार निर्माण कार्य ग्राम पंचायत विश्वा | Ongoing | 300577.13 | 0 | 2025-03-04
CHHATARPUR / BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708006018/WC/22012035228694 — सार्वजनिक खेत तालाब निर्माण कार्य मवया हार ग्राम पंचायत विश्वा | Ongoing | 383080.04 | 0 | 2025-03-04
CHHATARPUR / BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708006018/WC/22012035254836 — सार्वजनिक खेत तालाब निर्माण कार्य -महेंद्र सिंह के खेत के पास विश्वा | Approved | 0 | 0 | 2025-01-24
CHHATARPUR / BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708006018/WC/22012035254839 — सार्वजनिक खेत तालाब निर्माण कार्य -हनमत अहिरवार के क्खेत के पास विश्वा | Approved | 0 | 0 | 2025-01-24