## Work List
Exported on: 2026-09-13 22:06:29
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PARTAPPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHATARPUR / BADA MALEHARA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1708006064/AV/22012034391171 — शान्तिधाम निर्माण कार्य कुड़ी घाट प्रतापपुरा ग्राम पंचायत प्रतापपुरा खसरा नं0 ४१५ | Ongoing | 257000 | 0 | 2019-03-10
CHHATARPUR / BADA MALEHARA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1708006064/AV/6873 — Aanganbadi Bhavan Nirmaan Partappura | Ongoing | 180000 | 0 | 2017-01-30
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1708006064/IF/22012035377325 — हितेषी खेत तालाब निर्माण कार्य बारेलाल /भग्गू अहिरवार पात्रता एस0सी0 | Approved | 0 | 0 | 2025-04-14
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1708006064/IF/22012035377429 — हितेषी खेत तालाब निर्माण कार्य शिवरतन /भगवान दास तिवारी पात्रता बी0पी0एल0 | Approved | 0 | 0 | 2025-04-14
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1708006064/IF/22012035377511 — हितेषी खेत तालाब निर्माण कार्य सरजू /दुर्गा प्रसाद पात्रता लघु सीमांत कृषक | Approved | 0 | 0 | 2025-04-14
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1708006064/IF/22012035377771 — हितेषी खेत तालाब निर्माण कार्य विनोद /किशोरी लाल उपाध्याय पात्रता लघु सीमांत कृषक | Approved | 0 | 0 | 2025-04-14
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006064/IF/22012035608537 — एक बगिया माँ के नाम रजनी पाण्डेय/ अशोक भू स्वामी (सम्बन्ध पति) ग्राम गोपालपुरा पंचायत प्रतापपुरा | Ongoing | 275925.18 | 0 | 2025-12-30
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006064/IF/22012035608538 — एक बगिया माँ के नाम कल्पना उपाध्याय/निरंजन उपाध्याय भू स्वामी (सम्बन्ध पति) ग्राम पंचायत प्रतापपुरा | Ongoing | 275923.76 | 0 | 2025-09-07
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006064/IF/22012035618420 — एक बगिया माँ के नाम गिरजा बाई उपाध्याय/रिखीराम उपाध्याय भू स्वामी (सम्बन्ध पति) ग्रा गोपालपुरा पंचा | Ongoing | 275923.76 | 0 | 2025-09-20
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006064/IF/22012035621272 — एक बगिया माँ के नाम कृष्णा उपाध्याय/कैलाश उपाध्याय भू स्वामी (सम्बन्ध पति) ग्रा गोपालपुरा पंचा प्रता | Ongoing | 275923.76 | 0 | 2025-09-24
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006064/IF/22012035633265 — एक बगिया माँ के नाम कमला उपाध्याय/ रामप्रसाद उपाध्याय भू स्वामी (सम्बन्ध पति) ग्राम गोपालपुरा पंचायत | Ongoing | 275925.18 | 0 | 2025-12-06
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006064/IF/22012035647213 — एक बगिया माँ के नाम देवले राजा बुंदेला/हुकुम सिंह भू स्वामी (सम्बन्ध पति) ग्राम गोपालपुरा पंचायत प्र | New | 0 | 0 | 2025-08-14
CHHATARPUR / BADA MALEHARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/2321344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3726763 | Ongoing | 27000 | 0 | 2020-06-15
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/5484797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117763443 | Ongoing | 27000 | 0 | 2025-04-29
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/5730164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106795903 | Ongoing | 27000 | 0 | 2025-08-18
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/5768577 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106796357 | Ongoing | 27000 | 0 | 2025-09-03
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/5783343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115162106 | Ongoing | 27000 | 0 | 2025-09-03
CHHATARPUR / BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/5998806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150423923 | Ongoing | 27000 | 0 | 2026-05-07
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/5998807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150426685 | Approved | 27000 | 0 | 2026-02-18
CHHATARPUR / BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/6027336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147610080 | Ongoing | 27000 | 0 | 2026-04-08
CHHATARPUR / BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/6028298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121517998 | Ongoing | 27000 | 0 | 2026-04-08
CHHATARPUR / BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/6028597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120615622 | Ongoing | 27000 | 0 | 2026-04-08
CHHATARPUR / BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/6028793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106796167 | Ongoing | 27000 | 0 | 2026-05-07
CHHATARPUR / BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/6069496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106796404 | Ongoing | 27000 | 0 | 2026-07-11
CHHATARPUR / BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/6080367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120616138 | Ongoing | 27000 | 0 | 2026-06-04
CHHATARPUR / BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/6081163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121518028 | Approved | 27000 | 0 | 2026-02-18
CHHATARPUR / BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/6100545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150423079 | Ongoing | 27000 | 0 | 2026-06-04
CHHATARPUR / BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708006064/IF/IAY/6100546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150424947 | Ongoing | 27000 | 0 | 2026-05-07
CHHATARPUR / BADA MALEHARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708006064/RC/22012034822752 — सी सी रोड निर्माण कार्य हनुमान मंदिर से पाठक के घर तक एवं पाठक के घर से माता प्रांगण तक ग्राम पंचायत | Approved | 29000 | 0 | 2024-06-08
CHHATARPUR / BADA MALEHARA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708006064/RC/22012034842351 — सी सी रोड निर्माण कार्य झल्लू राजा के मकान से सरदार सिंह के मकान की और ग्राम गोपालपुरा ग्रपं प्रतापप | Approved | 15000 | 0 | 2025-04-14
CHHATARPUR / BADA MALEHARA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708006064/RC/22012034850611 — सी सी रोड निर्माण कार्य हनुमान मंदिर से पराधीन मिश्रा की और ग्राम पंचायत प्रतापपुरा | Approved | 36000 | 0 | 2025-04-14
CHHATARPUR / BADA MALEHARA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708006064/RC/22012034850612 — सी सी रोड निर्माण कार्य बलदाऊ प्रसाद के घर से पिपला तिगैला की और ग्राम पंचायत प्रतापपुरा | Ongoing | 54000 | 0 | 2026-01-09
CHHATARPUR / BADA MALEHARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1708006064/RS/22012035129453 — नाली निर्माण कार्य भूमानिया रजक के घर से नदी घाट तक ग्राम पंचायत प्रतापपुरा | Approved | 44000 | 0 | 2024-06-08