## Work List
Exported on: 2026-09-08 00:45:18
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JHARKUWAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHATARPUR / BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1708008058/DP/22012034611854 — Fruit Forest furtaal har patna gram panchayat jharkuwa | Ongoing | 1212729.72 | 0 | 2024-11-12
CHHATARPUR / BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708008058/IF/22012035658345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123226221 | Physically Completed | 23000 | 0 | 2026-02-04 | 2026-07-24
CHHATARPUR / BIJAWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708008058/IF/22012035658351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125404303 | Ongoing | 23000 | 0 | 2026-06-08
CHHATARPUR / BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708008058/IF/22012035658357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126091249 | Physically Completed | 23000 | 0 | 2026-02-01 | 2026-07-24
CHHATARPUR / BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708008058/IF/22012035659112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126694560 | Physically Completed | 23000 | 0 | 2026-02-01 | 2026-07-24
CHHATARPUR / BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708008058/IF/22012035659114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126344296 | Ongoing | 23000 | 0 | 2026-02-01
CHHATARPUR / BIJAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708008058/IF/IAY/4552289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113964474 | Ongoing | 27000 | 0 | 2025-03-27
CHHATARPUR / BIJAWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708008058/IF/IAY/4596819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123245840 | Ongoing | 27000 | 0 | 2025-03-27
CHHATARPUR / BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708008058/IF/IAY/4929150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126091709 | Ongoing | 27000 | 0 | 2025-08-07
CHHATARPUR / BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708008058/IF/IAY/5159116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126337735 | Physically Completed | 23490 | 0 | 2025-04-02 | 2026-08-16
CHHATARPUR / BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708008058/IF/IAY/5230512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125307712 | Ongoing | 27000 | 0 | 2025-08-01
CHHATARPUR / BIJAWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708008058/IF/IAY/5771523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126109802 | Physically Completed | 23490 | 2100 | 2025-11-04 | 2026-07-24
CHHATARPUR / BIJAWAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708008058/WC/22012034560597 — सार्बजनिक खेत तालाब निर्माण कार्य नथ्थू गौंड के खेत के पास झरकुवा | Ongoing | 362781.43 | 0 | 2020-07-13
CHHATARPUR / BIJAWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708008058/WC/22012035017044 — Ctr percolation tank Dashrath gun Ke khet ke pass | Ongoing | 356733.99 | 0 | 2023-03-23
CHHATARPUR / BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708008058/WC/22012035254047 — बोल्‍डर चैक डेम निर्माण कार्य पटना क्रमांक - 1 | Approved | 0 | 0 | 2025-01-25
CHHATARPUR / BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708008058/WC/22012035254049 — बोल्‍डर चैक डेम निर्माण कार्य पटना क्रमांक - 2 | Approved | 0 | 0 | 2025-01-25
CHHATARPUR / BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708008058/WC/22012035254051 — बोल्‍डर चैक डेम निर्माण कार्य पटना क्रमांक - 3 | Approved | 0 | 0 | 2025-01-25
CHHATARPUR / BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708008058/WC/22012035254054 — बोल्‍डर चैक डेम निर्माण कार्य पटना क्रमांक - 4 | Approved | 0 | 0 | 2025-01-25
CHHATARPUR / BIJAWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708008058/WC/22012035254055 — बोल्‍डर चैक डेम निर्माण कार्य पटना क्रमांक - 5 | Approved | 0 | 0 | 2025-01-25