## Work List
Exported on: 2026-10-25 13:30:57
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: DEOGAON
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PANNA / AJAIGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709001028/IF/22012035361055 — खेत तालाब निर्माण कार्य मंगल पिता बाबूलाल पटेल बिमतहा ग्रा.पं. देवगांव | Physically Completed | 124365.44 | 76605 | 2025-05-01 | 2026-06-15
PANNA / AJAIGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709001028/IF/22012035361058 — खेत तालाब निर्माण कार्य रामशरण पिता सुखनंदन अहिरवार ग्रा.पं. देवगांव | Physically Completed | 199000.13 | 150333 | 2025-04-30 | 2026-05-14
PANNA / AJAIGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709001028/IF/22012035361062 — खेत तालाब निर्माण कार्य रामेश्वर पिता जगन्नाथ पटेल ग्रा.पं. देवगांव | Physically Completed | 199000.13 | 120579 | 2025-04-30 | 2026-06-15
PANNA / AJAIGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1709001028/IF/22012035417630 — JGSA 2025 Recharge structure kapildhara koop Mahaprasad Sen 1709001028/IF/431 GP Deogaon | Physically Completed | 27000.29 | 24641 | 2025-05-04 | 2026-05-08
PANNA / AJAIGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1709001028/IF/22012035417664 — JGSA 2025 Recharge structure kapildhara koop Maiyadeen 1709001028/IF/1456 | Physically Completed | 27000.29 | 26651.96 | 2025-05-24 | 2026-05-08
PANNA / AJAIGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709001028/IF/22012035501952 — खेत तालाब निर्माण कार्य राजाभइया पिता शिवराम अहिरवार ग्रा.पं. देवगांव | Physically Completed | 124517.6 | 76734 | 2025-06-07 | 2026-06-15
PANNA / AJAIGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1709001028/IF/22012035502796 — JGSA 2025 Recharge structure Beba Rajrani GP Devgaon | Physically Completed | 27000.29 | 26908.04 | 2025-05-24 | 2026-05-12
PANNA / AJAIGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001028/IF/IAY/2649899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4480036 | Physically Completed | 17100 | 16524 | 2024-08-06 | 2024-11-21
PANNA / AJAIGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001028/IF/IAY/3456751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5419314 | Physically Completed | 17370 | 17322 | 2023-07-04 | 2024-11-21
PANNA / AJAIGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1709001028/RC/22012034615787 — Sudoor Sampark Road KarShala Se Sajoj Mishra Ke Purwa Tak Kishanpur GP Devgaon JP Ajaigarh | Physically Completed | 1384473.72 | 913461 | 2022-11-21 | 2026-06-15