## Work List
Exported on: 2026-09-02 05:28:19
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: VISHRAMGANJ
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PANNA / AJAIGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1709001032/AV/22012034537780 — बाउंड्री वाल निर्माण कार्य अरामगंज रेस्ट हॉउस के सामने आरामगंज | Completed | 74000 | 76000 | 2020-10-06 | 2021-06-17
PANNA / AJAIGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1709001032/AV/22012034545638 — बाउंड्री वाल निर्माण कार्य अरामगंज पुराना पंचायत भवन से चबूतरा तक | Completed | 20000 | 19950 | 2020-12-25 | 2021-06-17
PANNA / AJAIGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1709001032/AV/22012034582109 — डाइनिंग टेबल अरेन्जमेन्ट वर्क प्राथमिक शाला आरामगंज | Completed | 20236.77 | 20045 | 2021-09-09 | 2021-12-25
PANNA / AJAIGARH | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1709001032/AV/22012034617543 — आंगनवाड़ी भवन निर्माण कार्य आरामगंज | Ongoing | 500000 | 95183 | 2022-04-26
PANNA / AJAIGARH | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1709001032/DP/03 — व़क्षारोपण मुख्‍य सडक से लौकहा पुरवा तक विश्रामगंज | Completed | 308000 | 201311.4 | 2007-07-01 | 2012-02-15
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1709001032/DP/116 — शांती धाम विश्रामगंज | Completed | 493000 | 96395 | 2011-01-12 | 2012-04-03
PANNA / AJAIGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1709001032/DP/22012034483728 — निर्मलनीर कूप | Closed | 0 | 0 | 2019-07-15
PANNA / AJAIGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1709001032/DP/22012034494775 — फसल सुरक्षा खखरी निर्माण कार्य | Closed | 0 | 0 | 2020-05-20
PANNA / AJAIGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1709001032/DP/22012034495605 — फसल सुरक्षा खखरी निर्माण कार्य बरम बाबा घाट से कहुआ घाट की और आरामगंज | Closed | 0 | 0 | 2020-05-20
PANNA / AJAIGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1709001032/DP/22012034537064 — ma ki bagiya prathamik shala aramganj | Completed | 33403.31 | 13260 | 2021-11-23 | 2023-06-03
PANNA / AJAIGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1709001032/DP/22012034601457 — Vasudha vandan amrit vatika vishram ganj | Ongoing | 55645.2 | 4409 | 2024-01-04
PANNA / AJAIGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1709001032/DP/22012034626058 — Community plantation panchayat parisar aramanganj gp vishramganj | Approved | 202471.49 | 0 | 2024-06-08
PANNA / AJAIGARH | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1709001032/DP/55 — व्रक्षारोपण कार्य आंगनबाडी केन्‍द्र में विश्रामगंज | Completed | 137000 | 13911 | 2009-09-06 | 2012-04-03
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1709001032/DP/80 — व़क्षारोपण कार्य स्‍कूल परिसर से अरामगंज | Completed | 481000 | 114783 | 2010-05-28 | 2012-04-03
PANNA / AJAIGARH | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | 1709001032/FP/61 — नाला सफाई ढकनपरुवा नाला से मरिया कोंदर के घर तक | Completed | 496000 | 230336 | 2011-05-16 | 2012-04-03
PANNA / AJAIGARH | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | 1709001032/FP/62 — नाला सफाई गुरैयापुरवा से श्‍याम कोंदर के घर तक | Completed | 496000 | 60268 | 2011-05-20 | 2012-04-03
PANNA / AJAIGARH | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | 1709001032/FP/63 — नाला सफाई एवं गहरीकरण मरिया कोंदर के घर के सामने | Completed | 496000 | 223870 | 2011-05-16 | 2012-04-03
PANNA / AJAIGARH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/01339 — भूमिशिल्‍प कल्‍लू पिता जवाहर कोंदर | Completed | 69000 | 14105 | 2011-07-01 | 2012-04-03
PANNA / AJAIGARH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/014 — नवीन कूप निर्माण श्रीमती रूपमती पति बाबूलाल कोंदर विश्रामगंज | Completed | 125000 | 157291.09 | 2008-01-18 | 2009-08-09
PANNA / AJAIGARH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/015 — नवीन कून निर्माण कार्य कडोरे पिता बारे कोंदर विश्रामगंज | Completed | 125000 | 230021.95 | 2007-12-26 | 2008-12-22
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/0872 — मेंड्बंधान बच्‍चू/फुसूआ | Completed | 27000 | 18500 | 2010-06-18 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/1011 — मेड बंधान सुन्‍दर / पक्‍कू कौदर विश्रामगंज | Completed | 27000 | 24300 | 2010-10-22 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/1219 — कपिलधारा कूप सह मेडबंधान मईयादीन /बाबू कोंदर | Completed | 251000 | 284311 | 2011-02-01 | 2012-08-20
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/1220 — कपिलधारा कूप सह मेडबंधान दादूराम/दुर्जन कोंदर | Completed | 246000 | 349979 | 2011-02-01 | 2012-08-20
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/1221 — कपिलधारा कूप सह मेडबंधान कामता/साधू कोंदर | Completed | 245000 | 282408 | 2011-02-01 | 2012-08-08
PANNA / AJAIGARH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/1338 — भूमिशिल्‍प बाबूलाल पिता राम प्रसाद कोंदर | Completed | 84000 | 20691 | 2011-06-20 | 2012-04-03
PANNA / AJAIGARH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/1339 — भूमिशिल्‍प कल्‍लू पिता जवाहर कोंदर | Deleted | 0 | 0 | 2011-04-01
PANNA / AJAIGARH | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/1340 — भूमिशिल्‍प छोटेलाल पिता लटोरा कोंदर | Completed | 33000 | 14696 | 2011-09-01 | 2012-01-09
PANNA / AJAIGARH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/14 — नवीन कूप निर्माण बाबूलाल पिता रामप्रसाद कोंदर विश्रामगंज | Completed | 170000 | 52182 | 2008-01-06 | 2009-04-13
PANNA / AJAIGARH | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/15 — नवीन कूप निर्माण किशोरा/ श्री सूरा कोंदर | Completed | 125000 | 272187.03 | 2008-01-19 | 2008-12-22
PANNA / AJAIGARH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/16 — नवीन कूप निर्माण कार्य लखनलाल पिता कन्‍हैया कोंदर विश्रामगंज | Completed | 161000 | 225439.76 | 2008-04-28 | 2009-08-09
PANNA / AJAIGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1709001032/IF/22012034316933 — नाडिप् टाका दशरथ / सुम्मी गौड़ | Closed | 12000 | 0 | 2017-01-31
PANNA / AJAIGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1709001032/IF/22012034316987 — नाडिप् टाका परामलाल /प्यारेलाल कोंदर | Closed | 12000 | 0 | 2017-01-31
PANNA / AJAIGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1709001032/IF/22012034317042 — नाडिप् टाका श्यामलाल /पंचा कोदर | Closed | 12000 | 0 | 2016-10-02
PANNA / AJAIGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1709001032/IF/22012034317056 — नाडिप् टाका आनंदी /गनेशा कोंदर | Closed | 12000 | 0 | 2017-01-31
PANNA / AJAIGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1709001032/IF/22012034317060 — नाडिप् टाका भारतलाल /झल्लू कोंदर | Closed | 12000 | 0 | 2016-10-02
PANNA / AJAIGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1709001032/IF/22012034317066 — नाडिप् टाका रामस्वरूप /बुद्धू कोंदर | Closed | 12000 | 0 | 2016-10-02
PANNA / AJAIGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/22012034318769 — कपिल धारा कूप निर्माण सह खेत तालाब निर्माण कार्य मलखान/सुन्दर कोंदर | Closed | 230000 | 0 | 2017-02-13
PANNA / AJAIGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/22012034327967 — कपिलधारा कूप सह खेत तालाब निर्माण कार्य मरिया/तेजा कोंदर | Closed | 230000 | 0 | 2017-01-26
PANNA / AJAIGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/22012034327979 — कपिलधारा कूप सह खेत तालाब निर्माण कार्य गोबिंदा/बाबू कोंदर | Closed | 230000 | 0 | 2017-01-26
PANNA / AJAIGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/22012034327988 — कपिलधारा कूप सह खेत तालाब निर्माण कार्य जग्गू/तेजा कोंदर | Closed | 230000 | 0 | 2017-03-20
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1709001032/IF/22012034341824 — बृक्षारोपण कार्य मुख्य सड़क बब्बू बसोर के घर से विश्रामगंज तक | Completed | 335000 | 8256 | 2017-06-09 | 2018-10-24
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1709001032/IF/22012034352475 — बृक्षारोपण कार्य गुरैयापुरवा नाला से बसंता कोंदर के पुरवा तक | Completed | 335000 | 7224 | 2017-06-18 | 2018-10-24
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1709001032/IF/22012034352484 — बृक्षारोपण कार्य जुग्गू खाँ के घर से रूपकिशोर कोंदर के पुरवा तक | Completed | 335000 | 10320 | 2017-06-18 | 2018-10-24
PANNA / AJAIGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/22012035277949 — koop nirman karay daya ram kader / baldu vishramganj | Physically Completed | 378899.92 | 264274.98 | 2025-02-11 | 2026-06-25
PANNA / AJAIGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/22012035326987 — खेत तालाब निर्माण कार्य दयाराम पिता बल्दू ग्राम पंचायत आरामगंज | Ongoing | 199614.07 | 71703 | 2025-05-09
PANNA / AJAIGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1709001032/IF/22012035472342 — डक वेल रिचार्ज पिट निर्माण कार्य दयाराम कोंदर ग्राम पंचायत आरामगंज | Physically Completed | 27010.31 | 26649 | 2025-05-09 | 2026-06-25
PANNA / AJAIGARH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/438 — कपिलधारा कूप निर्माण कार्य जगदीश पिता पंचा कोंदर विश्रामगंज | Completed | 154000 | 118006.26 | 2009-02-21 | 2009-07-28
PANNA / AJAIGARH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/439 — कपिलधारा कूप निर्माण कार्य प्‍यारेलाल पिता चोखा पाल विश्रामगंज | Completed | 154000 | 111115.74 | 2009-03-06 | 2010-03-29
PANNA / AJAIGARH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/440 — कपिलधारा कूप निर्माण कार्य बच्‍चु पिता फुसुआ कोंदर विश्रामगंज | Completed | 154000 | 172958.97 | 2009-02-21 | 2010-10-25
PANNA / AJAIGARH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/441 — कपिलधारा कूप निर्माण कार्य देवीदीन पिता मैयादीन पाल विश्राम्रगंज | Completed | 154000 | 145208.76 | 2009-02-24 | 2010-10-25
PANNA / AJAIGARH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/442 — कपिलधारा कूप निर्माण कार्य मलखान पिता कंधी कोंदर विश्रामगंज | Completed | 154000 | 132143.53 | 2009-02-21 | 2010-10-25
PANNA / AJAIGARH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/443 — कपिलधारा कूप निर्माण कार्य क्रपाई पिता बुद्वद्वू गोड विश्रामगंज | Completed | 154000 | 100199.62 | 2009-02-21 | 2009-07-28
PANNA / AJAIGARH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/444 — कपिलधारा कूप निर्माण कार्य हीरालाल पिता सन्‍तू कोंदर विश्रामगंज | Completed | 154000 | 137789 | 2009-02-21 | 2010-10-25
PANNA / AJAIGARH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/445 — कपिलधारा कूप निर्माण कार्य कल्‍लू पिता जवाहर कोंदर विश्रामगंज | Completed | 154000 | 152790.86 | 2009-02-21 | 2010-09-06
PANNA / AJAIGARH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/446 — कपिलधारा कूप निर्माण कार्य रामलाल पिता कल्‍लू कोंदर विश्रामगंज | Completed | 154000 | 149039.96 | 2009-02-21 | 2009-07-28
PANNA / AJAIGARH | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/449 — निर्मलनीर कपिलधारा कूप निर्माण कार्य विश्रामगंज | Completed | 169000 | 149593 | 2009-02-27 | 2010-04-07
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/671 — नवीन कूप निर्माण मुन्‍नीलाल पिता श्री बन्‍सू अहिरवार विश्रामगंज | Completed | 177000 | 83356 | 2010-11-10 | 2012-04-03
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/672 — नवीन कूप निर्माण चुन्‍नूलाल पिता बन्‍सू अहिरवार विश्रामगंज | Completed | 177000 | 233564 | 2010-12-01 | 2012-04-03
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/673 — नवीन कूप निर्माण बसोरा पिता सूरा कोंदर विश्रामगंज | Completed | 177000 | 209443 | 2010-06-02 | 2012-06-18
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/674 — नवीन कूप निर्माण आशाराम पिता हजारी कोंदर विश्रामगंज | Completed | 177000 | 277210 | 2010-11-10 | 2012-04-03
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/877 — भूमि शिल्‍प लखन / कन्‍हैया कौंदर विश्रामगंज | Completed | 27000 | 24500 | 2010-06-20 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/939 — भूमि शिल्‍प आशाराम / हजारी कौंदर | Completed | 27000 | 5100 | 2010-08-03 | 2011-09-01
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/940 — मेड बंधान छोटेलाल कोंदर | Completed | 27000 | 7300 | 2010-08-03 | 2011-09-01
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/941 — मेड बंधान चुन्‍नीलाल पिता बंसू अहिरवार | Completed | 27000 | 27000 | 2010-08-03 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/971 — भूमि शिल्‍प किशोरा/सूरा कोंदर | Completed | 27000 | 27000 | 2010-07-01 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/972 — भूमि शिल्‍प हीरालाल के खेत से | Completed | 27000 | 9800 | 2010-08-08 | 2011-09-01
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926704825 — भूमिशिल्‍प मथुरिया पिता कन्‍हैया कोंदर | Completed | 32000 | 29227 | 2014-03-05 | 2014-09-28
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926704830 — भूमिशिल्‍प जुगराज पिता बारेलाल कोंदर | Completed | 42000 | 37530 | 2014-03-05 | 2015-09-30
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926704839 — भूमिशिल्‍प भावनीदीन पिता माधव कोंदर | Completed | 16000 | 13998 | 2014-03-05 | 2014-10-01
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926704844 — भूमिशिल्‍प राजाराम पिता भरोसा कोंदर | Completed | 58000 | 51837 | 2014-03-05 | 2016-08-17
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926704847 — भूमिशिल्‍प झल्‍लू पिता मरिया कोंदर | Completed | 56000 | 46968 | 2014-03-05 | 2014-09-28
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926704850 — भूमिशिल्‍प रज्‍जू पिता पक्‍कू कोंदर | Completed | 7500 | 5568 | 2014-03-05 | 2015-06-14
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926704855 — भूमिशिल्‍प देवीदीन पिता गुल्‍ले कोंदर | Completed | 28000 | 25773 | 2014-03-05 | 2014-09-28
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926704859 — भूमिशिल्‍प जीवालाल पिता सरिया कोदर | Completed | 28000 | 25842 | 2014-03-05 | 2015-06-17
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/9926705499 — कपिलधारा कूप निर्माण किशोरा पिता मनोहरा | Completed | 328000 | 323406 | 2014-03-05 | 2018-10-31
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/9926705503 — कपिलधारा कूप निर्माण कल्‍ला पिता हल्‍काई कोंदर | Deleted | 328000 | 0 | 2014-03-05
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/9926705507 — कपिलधारा कूप निर्माण जीवालाल पिता सरिया कोंदर | Completed | 328000 | 56169 | 2014-03-05 | 2018-12-12
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926713994 — पशुशेड निर्माण झल्‍लू पिता मरिया कोंदर | Completed | 87000 | 83189 | 2014-03-05 | 2018-06-27
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926713998 — भूमिशिल्‍प किशोरी बाई पति हरीलाल कोंदर | Completed | 38000 | 34722 | 2014-03-05 | 2014-09-28
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926714004 — पशुशेड निर्माण नन्‍दकिशोर पिता भालू बर्मन | Completed | 87000 | 85084 | 2014-03-05 | 2018-04-20
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926714082 — पशुशेड निर्माण बाबूलाल पिता भवानदीन विश्‍वकर्मा | Completed | 87000 | 79861.69 | 2014-03-05 | 2018-06-27
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926714102 — पशुशेड निर्माण कार्य बब्‍बू पिता परसदवा बसोर | Completed | 87000 | 82460.69 | 2014-03-05 | 2018-06-27
PANNA / AJAIGARH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926714106 — पशुशेड निर्माण कार्य कल्‍ला पिता हल्‍काई कोंदर | Completed | 87000 | 86429 | 2014-03-05 | 2018-06-27
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9926743141 — भूमिशिल्‍प बाबूलाल पिता सुल्‍ला कोंदर | Completed | 45000 | 32916 | 2014-07-21 | 2015-09-30
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9926743142 — भूमिशिल्‍प कलाबाई पति रामदास कोंदर | Completed | 53000 | 46185 | 2014-07-21 | 2015-09-30
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9926743154 — भूमिशिल्‍प धासी पिता मैकू कोंदर | Completed | 60000 | 34482 | 2014-07-21 | 2015-06-17
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9926743157 — भूमिशिल्‍प लच्‍छू पिता दुर्जा कोंदर | Completed | 63000 | 59004 | 2014-07-21 | 2015-09-30
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9926743180 — भूमिशिल्‍प मरिया पति अयोध्‍या कोंदर | Completed | 46000 | 42081 | 2014-07-21 | 2015-09-30
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9926743182 — भूमिशिल्‍प विन्‍द्रावन पिता कल्‍लू कोंदर | Completed | 21000 | 19468 | 2014-07-21 | 2014-10-04
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/9926743185 — भूमिशिल्‍प रामकिशोर पिता गेदूआ कोंदर | Completed | 24000 | 21509 | 2014-07-21 | 2014-09-28
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9926743190 — भूमिशिल्‍प शिवराम पिता दरबारी कोंदर | Completed | 23000 | 20881 | 2014-07-21 | 2014-10-02
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926746046 — भूमिशिल्प केशर बेवा प्यारे कोन्दर | Deleted | 57000 | 0 | 2014-04-26
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926746048 — भूमिशिल्प मूलचन्द्र पिता बादल कोन्दर | Deleted | 40000 | 0 | 2014-04-28
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926746360 — भूमिशिल्प गेदुआ पिता हल्कुआ कोन्दर | Deleted | 28000 | 0 | 2014-04-28
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926746370 — भूमिशिल्प भुगिया पिता खितैया कोन्दर | Deleted | 46000 | 0 | 2014-04-28
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9926746377 — भूमिशिल्प बुद्धू पिता फुसुआ कोन्दर | Deleted | 53000 | 0 | 2014-04-28
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993647228 — भूमिशिल्प गोरेलाल पिता बल्द्आ कोन्दर | Completed | 30000 | 26091 | 2014-09-22 | 2015-09-20
PANNA / AJAIGARH | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1709001032/IF/9993649245 — भूमिशिल्‍प पक्‍कू पिता हजारी कोंदर | Deleted | 63000 | 0 | 2014-04-28
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993695652 — भूमिशिल्‍प निर्माण कार्य लूटर पिता पक्‍कू कोंदर | Closed | 21000 | 0 | 2015-12-14
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993695672 — भूमिशिल्‍प निर्माण कार्य किशोरा पिता मनोहरा कोंदर | Completed | 78000 | 51516 | 2015-12-20 | 2016-08-17
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993695698 — भूमिशिल्‍प निर्माण कार्य क्रपाल पिता प्‍यारे कोंदर | Completed | 13000 | 9858 | 2015-12-20 | 2016-10-09
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993695703 — भूमिशिल्‍प निर्माण कार्य हरिलाल पिता बारेलाल | Closed | 64000 | 0 | 2015-12-14
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993695906 — भूमिशिल्‍प निर्माण कार्य परमलाल पिता बारेलाल | Closed | 85000 | 0 | 2015-12-14
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993695913 — भूमिशिल्‍प निर्माण कार्य जयकुमार पिता सुंदर लाल कोंदर | Deleted | 28000 | 0 | 2016-02-07
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993695915 — भूमिशिल्‍प निर्माण कार्य दीना पिता तेजा कोंदर | Completed | 33000 | 24804 | 2015-12-20 | 2016-08-17
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993696495 — भूमिशिल्‍प दीनदयाल पिता प्‍यारे कोंदर | Completed | 26000 | 11289 | 2015-12-20 | 2016-08-17
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993696498 — भूमिशिल्‍प आनंदी लाल पिता गनेशा कोंदर | Completed | 65000 | 24804 | 2016-02-05 | 2016-02-22
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993696507 — भूमिशिल्‍प जगदीश प्रसाद पिता पंचा | Closed | 36000 | 0 | 2015-12-16
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993696593 — भूमिशिल्‍प प्रेमाबाई पति दीनदयाल कोंदर | Completed | 38000 | 9540 | 2016-02-06 | 2016-02-22
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993696862 — भूमिशिल्‍प रूपकिशोर पिता मंगी कोंदर | Closed | 14000 | 0 | 2015-12-17
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993696864 — भमिशिल्‍प निर्माण घसिया पिता दीना कोंदर | Completed | 51000 | 32436 | 2015-12-22 | 2016-08-17
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993696868 — भमिशिल्‍प निर्माण कार्य गोविन्‍दा पिता बाबू कोंदर | Completed | 37000 | 28461 | 2015-12-22 | 2016-02-07
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993696873 — भमिशिल्‍प निर्माण कार्य कल्‍ला पिता हल्‍काई कोंदर | Closed | 64000 | 0 | 2015-12-17
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1709001032/IF/9993696892 — भूमिशिल्‍प रामक्रपाल पिता दरबारी कोंदर | Completed | 27000 | 11004 | 2015-12-29 | 2016-08-17
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/9993702802 — कपिल धारा कूप निर्माण छोटे लाल पिता लटोरा कोदंर | Completed | 363000 | 292704 | 2016-01-10 | 2018-12-07
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709001032/IF/9993728088 — कपिल धारा कूप निर्माण मलखान पिता सुन्दर कोंदर | Closed | 0 | 0 | 2016-01-26
PANNA / AJAIGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/117262 — Construction of IAY House -IAY REG. NO. MP-09-001-032-001/14635 | Completed | 14310 | 13946 | 2016-10-21 | 2017-11-16
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/117265 — Construction of IAY House -IAY REG. NO. MP-09-001-032-001/14655 | Approved | 23490 | 0 | 2016-01-07
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/1175973 — Construction of IAY House -IAY REG. NO. MP2269197 | Completed | 15480 | 15528 | 2017-12-26 | 2018-06-06
PANNA / AJAIGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/123383 — Construction of IAY House -IAY REG. NO. MP-09-001-032-001/16520 | Completed | 14310 | 13924 | 2016-06-24 | 2017-11-25
PANNA / AJAIGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/288815 — Construction of IAY House -IAY REG. NO. MP1711491 | Completed | 15030 | 15361 | 2017-01-24 | 2018-08-11
PANNA / AJAIGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/289119 — Construction of IAY House -IAY REG. NO. MP2218803 | Completed | 15030 | 15420 | 2017-01-24 | 2018-02-10
PANNA / AJAIGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/289120 — Construction of IAY House -IAY REG. NO. MP2219317 | Completed | 15030 | 15450 | 2017-01-24 | 2018-02-22
PANNA / AJAIGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/291372 — Construction of IAY House -IAY REG. NO. MP1642480 | Completed | 15030 | 15360 | 2017-01-24 | 2018-01-31
PANNA / AJAIGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3228216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4145176 | Completed | 17370 | 15956 | 2021-09-17 | 2023-11-13
PANNA / AJAIGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3228217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4144867 | Completed | 17370 | 12862 | 2021-09-17 | 2024-07-12
PANNA / AJAIGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3228231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4135964 | Completed | 17370 | 17211 | 2024-03-05 | 2024-07-08
PANNA / AJAIGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3228305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4156731 | Completed | 17370 | 17211 | 2023-11-07 | 2024-07-08
PANNA / AJAIGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3228306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4153272 | Completed | 17370 | 17370 | 2021-09-17 | 2021-12-10
PANNA / AJAIGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3228393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4386006 | Physically Completed | 17370 | 16524 | 2024-09-06 | 2024-11-27
PANNA / AJAIGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3228819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4355814 | Completed | 17370 | 17211 | 2024-03-05 | 2024-07-08
PANNA / AJAIGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3228963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5588869 | Completed | 17370 | 17253 | 2024-05-29 | 2024-07-08
PANNA / AJAIGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3228987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4312430 | Completed | 17370 | 17340 | 2022-07-15 | 2022-11-23
PANNA / AJAIGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3229023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4158002 | Completed | 17370 | 17370 | 2021-09-17 | 2021-12-10
PANNA / AJAIGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3229367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4769567 | Completed | 17370 | 9326 | 2021-09-17 | 2024-07-12
PANNA / AJAIGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3259958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4023801 | Completed | 17370 | 17340 | 2022-07-22 | 2023-01-04
PANNA / AJAIGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3261358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4165995 | Completed | 17370 | 16643 | 2022-07-07 | 2023-06-03
PANNA / AJAIGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3270558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4997887 | Completed | 17370 | 15912 | 2022-07-15 | 2023-02-26
PANNA / AJAIGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/3708276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100943525 | Physically Completed | 23490 | 21114 | 2024-11-09 | 2025-06-05
PANNA / AJAIGARH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/38408 — Construction of IAY House -IAY REG. NO. MP-09-001-032-001/13007 | Completed | 14310 | 14006 | 2016-05-20 | 2017-11-25
PANNA / AJAIGARH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/38409 — Construction of IAY House -IAY REG. NO. MP-09-001-032-001/14650 | Approved | 23490 | 0 | 2015-10-08
PANNA / AJAIGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/4533979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100943098 | Completed | 21870 | 21384 | 2024-10-21 | 2025-02-11
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/740020 — Construction of IAY House -IAY REG. NO. MP2230885 | Completed | 15030 | 15480 | 2017-05-31 | 2018-02-05
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/740026 — Construction of IAY House -IAY REG. NO. MP2230943 | Completed | 15030 | 15480 | 2017-05-24 | 2018-01-26
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/741050 — Construction of IAY House -IAY REG. NO. MP2257307 | Completed | 15030 | 15480 | 2017-05-24 | 2018-02-22
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/741580 — Construction of IAY House -IAY REG. NO. MP2274117 | Completed | 15030 | 15480 | 2017-06-26 | 2018-02-05
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/742229 — Construction of IAY House -IAY REG. NO. MP2292517 | Completed | 15030 | 15480 | 2017-06-09 | 2018-02-22
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/745948 — Construction of IAY House -IAY REG. NO. MP2399680 | Completed | 15030 | 15480 | 2017-06-26 | 2018-02-05
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/746161 — Construction of IAY House -IAY REG. NO. MP2406117 | Completed | 15030 | 15480 | 2017-05-24 | 2018-01-26
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/746173 — Construction of IAY House -IAY REG. NO. MP2406519 | Completed | 15030 | 15480 | 2017-06-16 | 2018-01-16
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/749177 — Construction of IAY House -IAY REG. NO. MP2509018 | Completed | 15030 | 15480 | 2017-07-03 | 2018-01-26
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/750998 — Construction of IAY House -IAY REG. NO. MP2578064 | Completed | 15030 | 15480 | 2017-06-09 | 2018-01-26
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/765040 — Construction of IAY House -IAY REG. NO. MP3193112 | Completed | 15030 | 14448 | 2017-10-07 | 2018-02-14
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/765919 — Construction of IAY House -IAY REG. NO. MP3231966 | Completed | 15030 | 15480 | 2017-06-26 | 2018-01-16
PANNA / AJAIGARH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001032/IF/IAY/767016 — Construction of IAY House -IAY REG. NO. MP3282443 | Completed | 15030 | 15480 | 2017-05-24 | 2018-02-05
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/137 — भूमि शिल्‍प मनोहर पिता तेजा कोंदर विश्रामगंज | Completed | 27000 | 26800 | 2010-05-10 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/138 — भूमि शिल्‍प गरीब दास पिता करंजू कोंदर विश्रामगंज | Completed | 27000 | 25696 | 2010-05-10 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/146 — मेड बंधान मुन्‍नीलाल के खेत में | Completed | 27000 | 25500 | 2010-07-12 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/147 — मेड बंधान मरिया कोंदर | Completed | 27000 | 21600 | 2010-07-01 | 2011-09-01
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/148 — मेड बंधान कडोरे कोंदर | Completed | 27000 | 27000 | 2010-07-15 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/149 — मेड बंधान कल्‍लू कोंदर | Completed | 27000 | 2700 | 2010-06-24 | 2012-04-03
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/150 — मेड बंधान बसोरा कोंदर | Completed | 27000 | 16400 | 2010-07-01 | 2011-09-01
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/151 — मेड बंधान मलखान कोंदर | Completed | 27000 | 25000 | 2010-07-01 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/152 — मेड बंधान दादूराम कोंदर | Completed | 27000 | 23400 | 2010-07-01 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/153 — मेड बंधान सुन्‍दर कोंदर के खेत में | Completed | 27000 | 26620 | 2010-06-24 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/159 — मेड वंधान कार्य रामलाल पिता कल्‍लू कोदर | Completed | 27000 | 26000 | 2010-07-20 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/160 — भूमि शिल्‍प कार्य क्रपाई पिता वुदधू | Completed | 27000 | 25200 | 2010-07-01 | 2010-12-21
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/166 — क्रीडागन मैदान विश्रामगंज | Completed | 493000 | 472022 | 2010-10-18 | 2013-02-26
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1709001032/LD/172 — भूमिशिल्‍प रूपवती पति बाबूलाल कोंदर | Completed | 27000 | 3300 | 2010-09-13 | 2011-09-01
PANNA / AJAIGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1709001032/LD/22012034298427 — शांती धाम आरामगंज | Completed | 245000 | 9519 | 2017-02-04 | 2019-02-25
PANNA / AJAIGARH | 2010-2011 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1709001032/OP/40 — निर्मलनीर कूप निर्माण आरामगंज | Completed | 214000 | 238088 | 2010-12-10 | 2016-07-27
PANNA / AJAIGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1709001032/PG/22012034305608 — खेल मैदान विश्रामगंज | Deleted | 353000 | 0 | 2017-04-21
PANNA / AJAIGARH | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/07 — सी सी रोड पान्‍डेयपुरवा मुख्‍य मार्ग से पान्‍डेयपुरवा तक | Completed | 495000 | 449533.59 | 2007-08-14 | 2007-12-30
PANNA / AJAIGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034177052 — सी0सी0 रोडएवंनालीनिर्माणमुख्‍यसडकसेसुदरकेघरतक | Completed | 68000 | 68092 | 2013-08-26 | 2014-02-28
PANNA / AJAIGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034177054 — सी0सी0रोडएवंनालीनिर्माणकिशोराकेघरसेठाकुरदीनकेघरतक | Completed | 100000 | 99466 | 2013-08-26 | 2013-11-20
PANNA / AJAIGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1709001032/RC/22012034205577 — जी0एस0बी रोड निर्माण मुख्‍यसडक से दीनदयाल के घर तक | Completed | 455000 | 370854 | 2014-03-05 | 2016-05-31
PANNA / AJAIGARH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034207155 — सी0सी0एवं नाली निर्माण बगलन पुरवा पंचमलाल के घर से | Completed | 126000 | 120307 | 2014-03-05 | 2014-07-02
PANNA / AJAIGARH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034227152 — सी सी सह नाली निर्माण आदिवासी मोहल्‍ला बाबूलाल के | Completed | 139000 | 102726 | 2014-09-15 | 2014-10-05
PANNA / AJAIGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1709001032/RC/22012034309043 — जी एस बी रोड निर्माण दीनदयाल कोंदरके घर से चौपड़ा खोल की ओर | Closed | 0 | 0 | 2016-01-26
PANNA / AJAIGARH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1709001032/RC/22012034309045 — जी एस बी रोड निर्माण बच्चू के घर से चौपड़ खोल की ओर | Closed | 0 | 0 | 2016-01-26
PANNA / AJAIGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034311465 — सीसी सह नाली निर्माण मिठाईलाल के मकान से गोविन्दा कोरी के मकान तक | Completed | 156000 | 78936 | 2016-04-29 | 2017-10-10
PANNA / AJAIGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1709001032/RC/22012034323773 — जी एस बी रोड निर्माण मझपुरवा से पहाड़ की और | Closed | 0 | 0 | 2017-01-26
PANNA / AJAIGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1709001032/RC/22012034323788 — जी एस बी मुख्य सड़क से बंगलनपुरवा | Closed | 0 | 0 | 2017-01-26
PANNA / AJAIGARH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034331177 — सी.सी.रोड सह नाली निर्माण टाईया के घर से बसंता कोंदर के घर तक | Completed | 8025000 | 80160 | 2017-03-15 | 2017-03-28
PANNA / AJAIGARH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034344238 — सी सी रोड एवं नाली निर्माण दीनदयाल के घर से दादूराम कोंदर के घर तक | Completed | 535000 | 80152 | 2017-07-17 | 2018-02-06
PANNA / AJAIGARH | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034374682 — सी सी रोड सह नाली निर्माण ई कक्ष के सामने आरामगंज | Completed | 64000 | 63504 | 2019-03-01 | 2019-09-15
PANNA / AJAIGARH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034476791 — सी सी रोड एवं नाली निर्माण कार्य ई पंचायत कक्ष से रेस्ट हाऊस की ओर | Completed | 79000 | 78144 | 2019-09-29 | 2019-12-13
PANNA / AJAIGARH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034482993 — सी सी एवं नाली निर्माण बाबूलाल विश्वकर्मा के माकन से निर्मल नीर कूप की और आरामगंज | Completed | 78300 | 78144 | 2019-12-11 | 2020-04-23
PANNA / AJAIGARH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034512023 — सी सी रोड निर्माण कार्य | Closed | 0 | 0 | 2019-08-15
PANNA / AJAIGARH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034512380 — सी. सी. रोड नाली निर्माण कार्य अराम गंज रेस्ट हाउस से बब्बो बसोर के घर के और | Completed | 42300 | 42240 | 2020-01-25 | 2020-04-23
PANNA / AJAIGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034598512 — सी. सी रोड निर्माण कार्य प्राथमिक शाला आरामगंज | Completed | 75000 | 91993 | 2021-11-24 | 2023-01-04
PANNA / AJAIGARH | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034665477 — Cc road nirman kary rest house se ramkishore ke makan tak naveen basti gp vishramganj | Completed | 107000 | 93372.5 | 2024-01-04 | 2024-11-04
PANNA / AJAIGARH | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/22012034822903 — CC road nirman kary naveen basti aramganj gp vishramganj | Completed | 81405 | 80919 | 2024-08-16 | 2024-11-26
PANNA / AJAIGARH | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1709001032/RC/223 — G.S.B रोड निर्माण कार्य किशोरा के घर से नदी की ओर विश्रामगंज | Completed | 497000 | 406551.06 | 2009-12-11 | 2010-06-26
PANNA / AJAIGARH | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1709001032/RC/302 — जी एस बी रोड निर्माण पाण्‍डेपुरवा ठाकुरबाबा से नरिया तक | Completed | 384000 | 314900 | 2010-06-09 | 2012-04-03
PANNA / AJAIGARH | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1709001032/RC/337 — GSB रोड ठाकुर बाबा से पाण्‍उे पुरवा स्‍कूल तक | Completed | 299000 | 313196 | 2010-10-03 | 2012-04-03
PANNA / AJAIGARH | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1709001032/RC/342 — G.S.B रोड स्‍टापडेम गुरैयापुरवा से श्‍याम कोंदर के घर तक | Completed | 380000 | 397948 | 2010-11-25 | 2012-04-03
PANNA / AJAIGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1709001032/RC/388 — GSB रोड निर्माण श्‍याम के मकान से तलवा तक | Completed | 415000 | 432210 | 2011-04-04 | 2014-07-02
PANNA / AJAIGARH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1709001032/RC/389 — GSB रोड निर्माण कुइया खोल से तलवा तक | Completed | 415000 | 426186 | 2011-05-11 | 2014-02-26
PANNA / AJAIGARH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709001032/RC/437 — सीसी एवं नाली निर्माण् मुन्‍नी लाल के मकान से लल्‍ | Completed | 159000 | 162104 | 2012-12-10 | 2012-12-27
PANNA / AJAIGARH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1709001032/RS/22012034498803 — सार्बजनिक शौचालय निर्माण कार्य इ -पंचायत कक्ष भवन के पास आरामगंज | Completed | 80000 | 43464 | 2020-10-27 | 2023-06-03
PANNA / AJAIGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1709001032/RS/22012034528180 — samudayik shokpit nirmad karya aramganj me 2 nag | Completed | 33008.74 | 31586 | 2021-11-09 | 2024-08-05
PANNA / AJAIGARH | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/12 — स्‍टापडेम निर्माण कार्यै धडकनपुरवा नाला विश्रामगंज | Completed | 499000 | 470711.36 | 2008-01-16 | 2010-05-07
PANNA / AJAIGARH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1709001032/WC/22012034382377 — नविन तालाब आरामगंज | Closed | 0 | 0 | 2017-07-15
PANNA / AJAIGARH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1709001032/WC/22012034438452 — तालाब निर्माण | Closed | 0 | 0 | 2019-01-26
PANNA / AJAIGARH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1709001032/WC/22012034438460 — तालाब निर्माण | Closed | 0 | 0 | 2019-01-26
PANNA / AJAIGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1709001032/WC/22012034516292 — लघु सार्वजानिक तालाब कुड़रा नाला आरामगंज | Closed | 330632.17 | 0 | 2019-10-02
PANNA / AJAIGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1709001032/WC/22012034518128 — लघु सार्वजनिक तालाब कुड़रा नाला आरामगंज | Completed | 299636.9 | 239712 | 2020-01-30 | 2021-03-10
PANNA / AJAIGARH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1709001032/WC/22012034529255 — सार्वजनिक खेत तालाब निर्माण कार्य हल्काई कोंदर के खेत के पास | Completed | 280224.09 | 209100 | 2020-03-17 | 2021-04-19
PANNA / AJAIGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1709001032/WC/22012034548512 — सावेजनिक खेत तालाब कछरा नाला आरामगंज | Completed | 259806.87 | 212610 | 2020-06-12 | 2021-08-08
PANNA / AJAIGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/22012034569935 — बोल्डर चेक डेम निर्माण कार्य गुदाहा नाला में १० नग आरामगंज | Completed | 422428.34 | 415260 | 2020-08-18 | 2021-02-17
PANNA / AJAIGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1709001032/WC/22012034586269 — बोल्डर चैक डैम निर्माण कार्य 10 नग रिपटा नाला से कहुआ घाट की ओर आरामगंज | Completed | 399533.35 | 398250 | 2020-12-01 | 2021-09-18
PANNA / AJAIGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/22012034588512 — बोल्डर चेक डेम निर्माण कार्य १० नंग रपटा नाला से कहुआ घाट की ओर अरामगंज | Closed | 0 | 0 | 2020-09-10
PANNA / AJAIGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1709001032/WC/22012034595350 — सावर्जनिक खेत तालाब निर्माण कार्य गुदाहा नाला के पास आरामगंज | Closed | 0 | 0 | 2020-10-02
PANNA / AJAIGARH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1709001032/WC/22012034596083 — सार्वजानिक खेत तालाब निर्माड कार्य गुडः नाला के पास आरामगंज | Completed | 258928.2 | 228970 | 2020-12-11 | 2021-08-08
PANNA / AJAIGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/22012034665656 — बोल्डर चैक डैम निर्माण कार्य 20 नग सकरा नाला आरामगंज | Completed | 823592.25 | 822162 | 2021-05-06 | 2021-12-25
PANNA / AJAIGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1709001032/WC/22012034665687 — सामुदायिक परकोलेशन टैंक निर्माण कार्य खित्ते कोंदर के खेत के पास | Completed | 831489.03 | 830571 | 2021-05-06 | 2024-11-04
PANNA / AJAIGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1709001032/WC/22012034729088 — Roop top rain water harvesting in school Aramganj | Closed | 0 | 0 | 2021-04-14
PANNA / AJAIGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1709001032/WC/22012034729090 — Roop top rain water harvesting in school Aramganj | Completed | 23722.67 | 24796 | 2021-06-17 | 2021-12-25
PANNA / AJAIGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1709001032/WC/22012034729115 — Roop top rain water harvesting in E panchyat kaksha Aramganj | Closed | 0 | 0 | 2021-04-14
PANNA / AJAIGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1709001032/WC/22012034729162 — Roop top rain water harvesting in E Panchyat kaksha Aramganj | Completed | 23722.67 | 22182 | 2021-06-25 | 2022-05-02
PANNA / AJAIGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/22012034779652 — bolder check dam nirman kary 20nag dadiya nala aramganj | Completed | 788843.13 | 680856 | 2021-08-08 | 2024-11-04
PANNA / AJAIGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/22012034779653 — bolder check dam nirman kary 20nag dadiya nala aramganj | Closed | 0 | 0 | 2021-04-14
PANNA / AJAIGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/22012034779655 — bolder check dam nirman kary 20nag dadiya nala aramganj | Closed | 0 | 0 | 2021-04-14
PANNA / AJAIGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/22012034928805 — Stop dam nirman kary chaupda khol nala vishramganj | Completed | 1498999.77 | 1483342 | 2022-04-16 | 2023-10-07
PANNA / AJAIGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/22012034928809 — Stop dam nirman kary aramganj kahuwa ghat nala vishramganj | Completed | 1498999.86 | 1479740 | 2022-04-16 | 2023-07-06
PANNA / AJAIGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1709001032/WC/22012034965002 — Amrit sarover yojanatargat naveen talab nirman kary dadiyan ke khait ke pass | Completed | 1322000 | 1321650 | 2022-05-15 | 2023-07-06
PANNA / AJAIGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/22012035197149 — check dam cum rapta nirman kary sakra nala aramganj | Completed | 100000 | 96825 | 2024-03-17 | 2025-02-13
PANNA / AJAIGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/22012035231351 — बोल्डर चेक डैम निर्माण कार्य २० नग हरदोई घाट के पास ग्राम पंचायत आरामगंज | Physically Completed | 499232.85 | 354758.4 | 2024-12-18 | 2026-05-08
PANNA / AJAIGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/22012035231352 — बोल्डर चेक डैम निर्माण कार्य २० नग भाटिया के पास नाला में ग्राम पंचायत आरामगंज | Physically Completed | 499232.85 | 402575.4 | 2024-12-15 | 2026-05-08
PANNA / AJAIGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1709001032/WC/22012035259709 — रिचार्ज पिट दयाराम पिता बल्दू ग्राम पंचायत आरामगंज | Deleted | 0 | 0 | 2025-04-01
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1709001032/WC/377 — लघु तालाब निर्माण कछरा आरामगंज | Completed | 75000 | 54000 | 2010-07-13 | 2012-04-03
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1709001032/WC/378 — लघू तलाब अरामगंज | Completed | 75000 | 55200 | 2010-07-13 | 2012-04-03
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1709001032/WC/397 — बावडी जीर्णोदार निर्माण कार्य | Completed | 495000 | 230786 | 2010-06-26 | 2012-04-03
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/421 — नवीन पुलिया निर्माण जी एसवी रोड ठाकुर बाबा से पाण्‍डंेयपुरवा स्‍कूल तक | Completed | 94000 | 99699.72 | 2010-11-13 | 2012-04-03
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Staggered Trench / Construction of Staggered Trench for Community | Construction of Trench | 1709001032/WC/427 — बोल्‍टर चेक डेम ढरकनपुरवा नाला | Completed | 423000 | 137100 | 2010-11-20 | 2012-04-03
PANNA / AJAIGARH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001032/WC/451 — चैक डेम निर्माण कार्य बगलन पुरवा नाला विश्रामगंज | Deleted | 479000 | 0 | 2011-01-26
PANNA / AJAIGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1709/WC/22012034780262 — TALAB NIMARN KARYA BEET VISHRAMGANJ B KACH KRAMANK P 318 | Completed | 550000 | 549474 | 2021-07-07 | 2022-05-09