## Work List
Exported on: 2026-08-15 18:19:02
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: CHHTAINI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PANNA / AJAIGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1709001060/DP/22012034600736 — Vasudha Vandan pushker stopdam marramat ke passamrit vatika nale ke kinare gp chatteni jp ajaigarh | Ongoing | 55852.42 | 0 | 2023-10-04
PANNA / AJAIGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1709001060/IF/22012035326097 — RECHARGE PIT NIRMAN TETA PRAJAPTI/MEKU PRAJAPATI CHHATENI | Approved | 0 | 0 | 2025-04-01
PANNA / AJAIGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1709001060/IF/22012035410765 — डग वेल रिचार्ज पिट निर्माण कार्य टटा प्रजापति ग्राम पंचायत छतैनी | Approved | 0 | 0 | 2025-04-14
PANNA / AJAIGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1709001060/IF/22012035499416 — डग वेल रिचार्ज पिट निर्माण कार्य राजा भैया लोध पिता राम असरे ग्राम पंचायत छतैनी | New | 0 | 0 | 2025-04-14
PANNA / AJAIGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709001060/IF/22012035563908 — खेत तालाब निर्माण कार्य बाबू पल के खेत में ग्राम पंचायत छतैनी | Approved | 0 | 0 | 2025-04-14
PANNA / AJAIGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709001060/IF/22012035613211 — एक बगिया माँ के नाम गीता पाल /बाला प्रशाद पाल 4277379 ग्राम पंचायत छतैनी | Ongoing | 149083.46 | 0 | 2025-09-15
PANNA / AJAIGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709001060/IF/22012035613515 — एक बगिया माँ के नाम गीता पल/बाला पल 4277379 ग्राम पंचायत छतैनी | New | 0 | 0 | 2025-08-16
PANNA / AJAIGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001060/IF/IAY/117198 — Construction of IAY House -IAY REG. NO. MP-09-001-060-001/12034 | Ongoing | 23490 | 0 | 2026-08-06
PANNA / AJAIGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001060/IF/IAY/123378 — Construction of IAY House -IAY REG. NO. MP-09-001-060-001/12097 | Ongoing | 23490 | 0 | 2026-08-06
PANNA / AJAIGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001060/IF/IAY/2229011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1493346 | Approved | 23490 | 0 | 2019-07-07
PANNA / AJAIGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001060/IF/IAY/3635896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4578670 | Approved | 23490 | 0 | 2022-01-16
PANNA / AJAIGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001060/IF/IAY/3643885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3078638 | Approved | 23490 | 0 | 2022-02-04
PANNA / AJAIGARH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709001060/IF/IAY/3643936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3135114 | Approved | 23490 | 0 | 2022-02-03
PANNA / AJAIGARH | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1709001060/RC/02 — पहुच मार्ग निर्माण कार्य खदिया से सिल्‍हाई रोड | Ongoing | 451000 | 0 | 2007-09-11
PANNA / AJAIGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1709001060/WC/22012035244205 — construction of under ground dykes kandhara nala chayani | Approved | 0 | 0 | 2024-10-02
PANNA / AJAIGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1709001060/WC/22012035249221 — परकुलेसन टैंक निर्माण कार्य राजा लोध के खेत के पास ग्राम पंचायत छतैनी 3 | Approved | 0 | 0 | 2025-01-27
PANNA / AJAIGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709001060/WC/22012035254356 — बोल्डर चेक डैम निर्माण कार्य कल्लू के खेत के पास छतैनी | Approved | 0 | 0 | 2025-01-27
PANNA / AJAIGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1709001060/WC/22012035259588 — रिचार्ज पिट जयपाल लोध ग्राम पंचायत छतैनी | New | 0 | 0 | 2025-04-01
PANNA / AJAIGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1709001060/WC/22012035313000 — डग वेल रिचार्ज पिट निर्माण कार्य सार्वजनिक कूप महेश कोरी के खेत के पास ग्राम पंचायत छतैनी | Approved | 27010.31 | 0 | 2025-04-14
PANNA / AJAIGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1709001060/WC/22012035313002 — डग वेल रिचार्ज पिट निर्माण कार्य गजहां बाबा कूप के पास ग्राम पंचायत छतैनी | Approved | 27010.31 | 0 | 2025-04-14
PANNA / AJAIGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1709001060/WC/22012035313626 — NAYA TALAB NIRMAN PIPARAHI GRAM PANCHAYAT CHHATENI | Ongoing | 2377000 | 0 | 2025-06-16