## Work List
Exported on: 2026-10-02 08:46:56
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: RICHHOUDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PANNA / GUNOR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1709003052/AV/22012034448041 — puliya nirman gadhaghat naalaa gram richaudi | Ongoing | 1477000 | 0 | 2019-03-05
PANNA / GUNOR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Stabilization Pond for Community / Construction of Stabilisation Pond for Community | Construction of Tank | 1709003052/AV/22012034548496 — ghaat nirman richaudi talab | Ongoing | 1498624.51 | 0 | 2021-02-25
PANNA / GUNOR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Avenue Plantation for Community | Plantation | 1709003052/DP/22012034599996 — Basudha Bandhan Vatika Nirman Karya Talab me | Ongoing | 101609.01 | 0 | 2023-09-10
PANNA / GUNOR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003052/IF/22012034591361 — Niji khet me phalodyan karya lachhi bai patel | Ongoing | 115360 | 0 | 2020-08-27
PANNA / GUNOR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709003052/IF/22012035092610 — कूप निर्माण कार्य कल्लू बाई पटेल / इंदु पटेल | Ongoing | 282131.39 | 0 | 2023-06-24
PANNA / GUNOR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1709003052/IF/22012035125138 — Med Bandhan Nirman Karya Shyam Bai Soni / Ramlakhan Soni | Ongoing | 49717.8 | 0 | 2023-10-08
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709003052/IF/22012035328976 — koop nirman karya gangaram patel / gore lal | Approved | 0 | 0 | 2025-04-01
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709003052/IF/22012035328981 — koop nirman karya lallu lal patel / seetaram | Approved | 0 | 0 | 2025-04-01
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709003052/IF/22012035328988 — koop nirman karya rakesh patel / rajkishor | Approved | 0 | 0 | 2025-04-01
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1709003052/IF/22012035428027 — jal ganga 2025 dugwell richarge pit karya ramesh / rampratap vishwakarma | Approved | 0 | 0 | 2025-04-14
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1709003052/IF/22012035428080 — jal ganga 2025 dugwell richarge pit karya suneeta bai /prathvi patel | Approved | 0 | 0 | 2025-04-14
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1709003052/IF/22012035428105 — jal ganga 2025 dugwell richarge pit karya sibuwa/ mulaiya | Approved | 0 | 0 | 2025-04-14
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1709003052/IF/22012035428166 — jal ganga 2025 dugwell richarge pit karya phakira / ramnath | Approved | 0 | 0 | 2025-04-14
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1709003052/IF/22012035464368 — Jal ganga 2025 recharge pit Ramesh/ ramsahay vishkarma | Approved | 0 | 0 | 2025-04-10
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1709003052/IF/22012035464379 — Jal ganga 2025 dugwell recharge pit suneeta / prathvi patel | Approved | 25899.46 | 0 | 2025-04-10
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1709003052/IF/22012035464389 — Jal ganga 2025 dugwell recharge pit sibua/mulaiya | Approved | 25899.46 | 0 | 2025-04-10
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1709003052/IF/22012035464399 — Jalganga 2025 dugwell recharge pit phakira/ramnath | Approved | 25899.46 | 0 | 2025-04-10
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1709003052/IF/22012035464411 — Jalganga 2025 dugwell recharge pit shreekant dwivedi | Approved | 25899.46 | 0 | 2025-04-10
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1709003052/IF/22012035464421 — Jal ganga 2025 dugwell recharge pit kalicharan patel | Approved | 25899.46 | 0 | 2025-04-10
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1709003052/IF/22012035464452 — Jal ganga 2025 dugwell recharge pit Sooraj/ramsahay vishkarma | Approved | 25899.46 | 0 | 2025-04-10
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709003052/IF/22012035523404 — koop nirman karya betalal patel / rajaram | Approved | 0 | 0 | 2025-04-14
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709003052/IF/22012035523428 — koop nirman karya suraj prasad patel / nanhe lal | Approved | 0 | 0 | 2025-04-14
PANNA / GUNOR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709003052/IF/IAY/197372 — Construction of IAY House -IAY REG. NO. MP-09-003-052-001/10741 | Approved | 27000 | 0 | 2015-11-18
PANNA / GUNOR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003052/IF/IAY/3239708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4551403 | Approved | 27000 | 0 | 2020-11-24
PANNA / GUNOR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003052/IF/IAY/4630630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128835639 | Ongoing | 27000 | 3000 | 2024-10-15
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003052/IF/IAY/5458991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126790849 | Ongoing | 27000 | 0 | 2025-05-01
PANNA / GUNOR | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1709003052/WC/22012035127177 — Samudyik coop ( nirmal neer) nirman karya Chopra ke pass Richhoudi | Ongoing | 611165.48 | 0 | 2023-08-16
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003052/WC/22012035255176 — boldar chack dem nirman karya kishun lal ke khet ke pas nala par | Approved | 243162.1 | 0 | 2024-10-02
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003052/WC/22012035255177 — boldar chack dem nirman karya muneema ke khet ke paas nala me | Approved | 244162.1 | 0 | 2024-10-02
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003052/WC/22012035255178 — boldar chack dem nirman karya puliya ke paas nala me | Approved | 243162.1 | 0 | 2024-10-02
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003052/WC/22012035255186 — boldar chack dem nirman karya rambahadur ke khet ke paas nala me | Ongoing | 249099.8 | 0 | 2025-06-04
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003052/WC/22012035255189 — boldar chack dem nirman karya pooran dahar ke pas nala me | Ongoing | 244162.1 | 0 | 2025-06-04
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003052/WC/22012035255190 — boldar chack dem nirman karya talaiya ke paas nala me | Ongoing | 244162.1 | 0 | 2025-06-04
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003052/WC/22012035255191 — boldar chack dem nirman karya bhalu ke khet ke paas nala me | Ongoing | 244162.1 | 0 | 2025-06-04
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003052/WC/22012035255192 — boldar chack dem nirman karya patwan ghat ke pas nala me | Approved | 244162.1 | 0 | 2024-10-02
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003052/WC/22012035255193 — boldar chack dem nirman karya bharat ke kachhara paas nala me | Approved | 243162.1 | 0 | 2024-10-02
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003052/WC/22012035255328 — boldar Check Dam nirman karya bade bageecha ke paas nala me | Approved | 244162.1 | 0 | 2024-10-02
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003052/WC/22012035255722 — Boulder check dam richhoda | Approved | 0 | 0 | 2025-01-26