## Work List
Exported on: 2026-10-04 20:33:51
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: HAHIRA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PANNA / GUNOR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1709003064/DP/22012034607236 — Nirmal Neer Nirman karya Shanti dham ke pass Harira | Ongoing | 547514.08 | 0 | 2023-10-09
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003064/IF/22012035323769 — Jal Ganga Samvardhan KHET TALAB NIRMAN KARYA PREM LAL/MANGAL LODHI | Approved | 199091.16 | 0 | 2025-04-02
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003064/IF/22012035323773 — Jal Ganga Samvardhan KHET TALAB NIRMAN KARYA KAMAL PRSAD/MANGAL LODHI | Approved | 199788.78 | 0 | 2025-04-02
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003064/IF/22012035323778 — Jal Ganga Samvardhan KHET TALAB NIRMAN KARYA GANGA/SITARAM KUSHWAHA | Approved | 199091.16 | 0 | 2025-04-02
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003064/IF/22012035324834 — Jal Ganga Samvardhan Khet Talab nirman Karya Khillu Lodhi/Sukadu | Approved | 197474.38 | 0 | 2025-04-07
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003064/IF/22012035538450 — KHET TALAB NIRMAN KARYA LAXMAN LODHI/BENI PRASAD LODHI | Approved | 199172.6 | 0 | 2025-04-14
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003064/IF/22012035538461 — KHET TALAB NIRMAN KARYA VISHNU PRASAD/RAJENDRA PRASAD | Approved | 199672.6 | 0 | 2025-04-14
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709003064/IF/22012035538466 — KHET TALAB NIRMAN KARYA SURESH/MULAI DHIMAR | Approved | 199642.6 | 0 | 2025-04-14
PANNA / GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003064/IF/IAY/6034447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121350871 | Ongoing | 27000 | 8100 | 2026-04-22
PANNA / GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003064/IF/IAY/6034695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125772611 | Ongoing | 27000 | 12600 | 2026-05-28
PANNA / GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003064/IF/IAY/6035700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126314963 | Ongoing | 27000 | 16500 | 2026-06-24
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003064/IF/IAY/6036699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126673028 | Ongoing | 27000 | 12300 | 2026-03-18
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003064/IF/IAY/6036773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121758097 | Approved | 27000 | 0 | 2026-01-23
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003064/IF/IAY/6036839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128489441 | Ongoing | 27000 | 0 | 2026-03-18
PANNA / GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003064/IF/IAY/6243908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126521310 | Ongoing | 27000 | 0 | 2026-07-31
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003064/WC/22012035204875 — बोल्डर चेक डेम निर्माण कार्य नत्थू लोधी के खेत पास हरीरा | Approved | 120068.75 | 0 | 2024-06-08
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003064/WC/22012035210022 — बोल्डर चेक डेम निर्माण कार्य शांतिधाम के पास हरीरा | Approved | 147910.65 | 0 | 2024-06-08
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003064/WC/22012035210145 — बोल्डर चेक डेम निर्माण कार्य नट बाबा पास हरीरा | Approved | 0 | 0 | 2024-06-08
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003064/WC/22012035210149 — बोल्डर चेक डेम निर्माण कार्य राजेंद्र द्विवेदी के खेत पास उमरी | New | 0 | 0 | 2024-06-08
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1709003064/WC/22012035210422 — Perculation Tank Nirman Karya Sukhendra ke khet paas Harira | Approved | 0 | 0 | 2024-06-08
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1709003064/WH/22012034941068 — टगर तालाब गहरीकरण निर्माण कार्य | Approved | 0 | 0 | 2024-04-04