## Work List
Exported on: 2026-10-05 01:19:00
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SINGHAURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PANNA / GUNOR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1709003079/AV/22012034665985 — खेल मैदान कार्य पण्डवन प्रयाग परिसर ग्राम पंचायत सिंघोरा | Approved | 620924.23 | 0 | 2025-04-15
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1709003079/DP/22012034630076 — Samudayik Plantation Karya Hanuman Ji Chabutara Ke Pass Singhoura | Approved | 0 | 0 | 2025-04-01
PANNA / GUNOR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1709003079/IF/22012034602059 — niji khet me phalodhan hitgrahi monoj mishra pita murlidhar | Ongoing | 115360 | 0 | 2021-04-22
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1709003079/IF/22012035431995 — Jal Ganga 2025 Dugwell Recharge Manoj Mishra SINGHAURA | Approved | 25899.46 | 0 | 2025-04-15
PANNA / GUNOR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003079/IF/IAY/4046551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128740692 | Ongoing | 27000 | 0 | 2022-06-25
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003079/IF/IAY/5136396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127674625 | Ongoing | 27000 | 0 | 2025-07-21
PANNA / GUNOR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003079/IF/IAY/5143383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128725831 | Approved | 27000 | 0 | 2025-03-06
PANNA / GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003079/IF/IAY/5693519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128736802 | Ongoing | 27000 | 6300 | 2026-08-01
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003079/IF/IAY/5694594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131825093 | Ongoing | 27000 | 0 | 2025-07-21
PANNA / GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003079/IF/IAY/5744070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128736262 | Ongoing | 27000 | 0 | 2026-04-08
PANNA / GUNOR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003079/IF/IAY/5747333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127625334 | Ongoing | 27000 | 0 | 2025-09-28
PANNA / GUNOR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003079/IF/IAY/5747356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128737231 | Approved | 27000 | 0 | 2025-03-06
PANNA / GUNOR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003079/IF/IAY/5748596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127631742 | Approved | 27000 | 0 | 2025-03-06
PANNA / GUNOR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003079/IF/IAY/5749493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127632394 | Approved | 27000 | 0 | 2025-03-06
PANNA / GUNOR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709003079/IF/IAY/5866220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128740319 | Physically Completed | 27000 | 0 | 2026-04-08 | 2026-09-27
PANNA / GUNOR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1709003079/WC/22012035205262 — GABION STRUCTURE NIRMAN KARYA PRATHMIK SHALA KE SAMNE SINGHOURA | Approved | 0 | 0 | 2024-06-08
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1709003079/WC/22012035279132 — Jal Ganga 2025 Dugwell Recharge kushwaha mohhalla ke pas | New | 0 | 0 | 2025-04-15
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1709003079/WC/22012035279138 — Jal Ganga 2025 Dugwell Recharge kushwaha mohhalla ke pas singhaura | Approved | 0 | 0 | 2025-04-15
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Borewell for Community | Well Recharge | 1709003079/WC/22012035280837 — Jal Ganga 2025 Dugwell Recharge aadiwasi mohhalla ke pas singhaura | Approved | 0 | 0 | 2025-04-15
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Borewell for Community | Well Recharge | 1709003079/WC/22012035280841 — Jal Ganga 2025 Dugwell Recharge harijan basti ke pas singhaura | Approved | 0 | 0 | 2025-04-15
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Borewell for Community | Well Recharge | 1709003079/WC/22012035280843 — Jal Ganga 2025 Dugwell Recharge ms shcool ke pas singhaura | Approved | 0 | 0 | 2025-04-15
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Borewell for Community | Well Recharge | 1709003079/WC/22012035280852 — Jal Ganga 2025 Dugwell Recharge sarvjanik koop kher mata ke pas singhaura | Approved | 0 | 0 | 2025-04-15
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003079/WC/22012035315691 — बोल्डर चेक डेम निर्माण कार्य मरघट नाला भरत परौहा के खेत के पास सिंधौरा | Approved | 0 | 0 | 2025-04-01
PANNA / GUNOR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709003079/WC/22012035315692 — बोल्डर चेक डेम निर्माण कार्य मिढासन नाला रामस्वरूप पडरहा के खेत के पास सिंधौरा | Approved | 0 | 0 | 2025-04-01