## Work List
Exported on: 2026-10-11 19:51:37
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: UNCHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PANNA / SHAHNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1709005004/DP/22012034615183 — Raidass Cabutra ke Pass- Nirmal neer Ahirwar Muhalla | Ongoing | 587429.61 | 0 | 2024-03-24
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1709005004/IC/22012034891007 — ऊँचा-सार्वजनिक सिंचाई कूप निर्माण -राम आसरे तिवारी के खेत के पास | Approved | 598004.74 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709005004/IF/22012035220684 — uncha-kapildhara koop-kushamrani/laxman rai | Ongoing | 358404.3 | 0 | 2024-03-17
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line-coast Plntation-Farm Forstry Trees-Individual / Line Plantation of Forestry Trees for Individual | Plantation | 1709005004/IF/22012035239321 — Plantation niramn karya kallu/babulal ahirwar | Ongoing | 115425.87 | 0 | 2024-11-27
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035243525 — UNCHA Berkcharopan Hakka/Johareya Ahirwar | New | 0 | 0 | 2024-06-08
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035243526 — UNCHA Berkcharopan Hakka/Johareya Ahirwar | New | 0 | 0 | 2024-06-08
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035243527 — UNCHA Berkcharopan Hakka/Johareya Ahirwar | New | 0 | 0 | 2024-06-08
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035243609 — UNCHA Berkcharopan Hakka/Johareya Ahirwar | New | 0 | 0 | 2024-06-08
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035243613 — UNCHA Berkcharopan Hakka/Johareya Ahirwar | New | 0 | 0 | 2024-06-08
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035243622 — UNCHA Berkcharopan Hakka/Johareya Ahirwar | New | 0 | 0 | 2024-06-08
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035243623 — UNCHA Berkcharopan Hakka/Johareya Ahirwar | New | 0 | 0 | 2024-06-08
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035243632 — UNCHA Berkcharopan Hakka/Johareya Ahirwar | New | 0 | 0 | 2024-06-08
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035243641 — UNCHA Berkcharopan Hakka/Johareya Ahirwar | New | 0 | 0 | 2024-06-08
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line-coast Plntation-Farm Forstry Trees-Individual / Line Plantation of Forestry Trees for Individual | Plantation | 1709005004/IF/22012035245091 — Uncha Plantation nirman karya Sarman/laxmi khare | Ongoing | 119923.37 | 0 | 2025-03-03
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035253153 — UNCHA Berkcharopan Kanchadi/Jalam Lodhi | New | 0 | 0 | 2024-06-08
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035253406 — UNCHA Berkcharopan RAMSANEEHI/HARGOVIND LODHI | Approved | 0 | 0 | 2024-06-08
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709005004/IF/22012035326620 — ऊंचा-कूप निर्माण छिद्दीलाल पिता बाबूलाल लोधी | Ongoing | 420383.53 | 0 | 2025-05-02
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709005004/IF/22012035327628 — ऊंचा-कूप निर्माण जवाहर पिता मोहन लोधी | Ongoing | 420383.53 | 0 | 2025-05-18
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035368434 — ऊँचा-खेत तालाब निर्माण-डरे/ मिहिलाल राय | Approved | 199737.61 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035368451 — ऊँचा-खेत तालाब निर्माण-रामलखन/मुरारी | Ongoing | 199737.61 | 0 | 2025-06-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035424594 — ऊँचा-खेत तालाब निर्माण -सजना/जवाहर लोधी | Approved | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709005004/IF/22012035561050 — ऊँचा-कपिल धारा कूप निर्माण कार्य-कमलेश/गुबंदी | Approved | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005004/IF/22012035661538 — uncha khet talab nirman berend/ramsanehi lodhi | Approved | 0 | 0 | 2026-01-26
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/118131 — Construction of IAY House -IAY REG. NO. MP-09-005-004-001/1074 | Ongoing | 27000 | 0 | 2025-06-13
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/118134 — Construction of IAY House -IAY REG. NO. MP-09-005-004-001/1086 | Ongoing | 27000 | 0 | 2025-06-30
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/4764005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121443460 | Ongoing | 27000 | 0 | 2025-09-28
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/4768332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123420811 | Ongoing | 27000 | 0 | 2024-12-14
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/4778421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126840235 | Ongoing | 27000 | 0 | 2024-12-14
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/4804237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143432736 | Ongoing | 27000 | 0 | 2025-03-07
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/4859396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126857189 | Ongoing | 27000 | 0 | 2025-03-07
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/4859880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127210549 | Ongoing | 27000 | 0 | 2025-02-19
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/5009601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121587298 | Ongoing | 27000 | 0 | 2025-04-01
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/5012835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123434501 | Ongoing | 27000 | 0 | 2025-04-01
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/5087276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128272036 | Physically Completed | 23490 | 0 | 2025-04-01 | 2026-07-26
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/5501212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126870742 | Ongoing | 27000 | 0 | 2025-06-16
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/5639256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126844669 | Ongoing | 27000 | 0 | 2025-06-06
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/5764141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126849243 | Ongoing | 27000 | 0 | 2025-09-02
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/5765040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126850706 | Ongoing | 27000 | 0 | 2025-09-02
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/5807584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123412135 | Ongoing | 27000 | 0 | 2025-09-16
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/5878091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127176474 | Ongoing | 27000 | 0 | 2026-03-02
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/6012512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127238925 | Ongoing | 27000 | 0 | 2026-04-04
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/6018494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126853451 | Ongoing | 27000 | 0 | 2026-04-04
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/6021192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126876340 | Ongoing | 27000 | 0 | 2026-04-04
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/6230322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127147246 | Ongoing | 27000 | 12600 | 2026-06-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/6230624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127190581 | Ongoing | 27000 | 0 | 2026-06-01
PANNA / SHAHNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/79599 — Construction of IAY House -IAY REG. NO. MP-09-005-004-001/935 | Approved | 27000 | 0 | 2015-12-11
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/79600 — Construction of IAY House -IAY REG. NO. MP-09-005-004-001/936 | Ongoing | 27000 | 0 | 2025-07-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/79602 — Construction of IAY House -IAY REG. NO. MP-09-005-004-001/917 | Ongoing | 27000 | 0 | 2025-07-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709005004/IF/IAY/79603 — Construction of IAY House -IAY REG. NO. MP-09-005-004-001/946 | Ongoing | 27000 | 0 | 2025-06-30
PANNA / SHAHNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1709005004/WC/22012035100448 — Gp-Uncha work greviyan Nirman Graha Nala pr 01 | Ongoing | 953334.65 | 0 | 2023-09-21