## Work List
Exported on: 2026-10-20 04:30:30
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BAMHOURI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PANNA / SHAHNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1709005010/AV/22012034602300 — नवीन पंचायत भवन निर्मान कार्य नागपुरा मुहल्ला ग्राम बम्हौरी ग्राम पंचायत बम्हौरी | Ongoing | 1000000 | 0 | 2021-11-17
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Unskilled wage for Bio gas plant for community / Construction of Biogas Plant for Community | Bio-gas plant | 1709005010/AV/22012034658754 — वृक्षारोपण कार्य _ कैलाश विश्वकर्मा / रामरतन ग्राम पंचायत बम्होरी | Ongoing | 115509.72 | 0 | 2024-10-30
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Unskilled wage for Bio gas plant for community / Construction of Biogas Plant for Community | Bio-gas plant | 1709005010/AV/22012034661028 — शांति धाम धुवगटा के पास ग्राम बम्हौरी | New | 0 | 0 | 2024-10-02
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Unskilled wage for Bio gas plant for community / Construction of Biogas Plant for Community | Bio-gas plant | 1709005010/AV/22012034661030 — शांति धाम स्कूल के आगे ग्राम पोनिया | New | 0 | 0 | 2024-10-02
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1709005010/DP/22012034626894 — वृक्षारोपण कार्य _ चाहना विश्वकर्मा / अजय ग्राम पंचायत बम्होरी | Ongoing | 115509.72 | 0 | 2024-10-29
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plntation-Biodrainage-Wastelands for comm / Bio-drainage Plantation for Community | Plantation | 1709005010/DP/22012034626895 — वृक्षारोपण कार्य _ मुरारी पटेल/ मट्टू ग्राम पंचायत बम्होरी | New | 0 | 0 | 2024-06-08
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1709005010/IF/22012034841225 — फलोद्यान निर्माण कार्य _ चरन पटेल / हरप्रसाद ग्राम बम्होरी | Ongoing | 117912.51 | 0 | 2024-10-04
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Agro Forestry Block Plantation for Individual | Plantation | 1709005010/IF/22012035253530 — वृक्षारोपण कार्य _ शालिग्राम पटेल/ भिल्लू पटेल पंचायत बम्होरी | Ongoing | 115509.72 | 0 | 2024-10-04
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Line Plantation of Forestry Trees for Individual | Plantation | 1709005010/IF/22012035253814 — वृक्षारोपण कार्य _ मुरारी पटेल / मट्टू ग्राम पंचायत बम्होरी | Ongoing | 115509.72 | 0 | 2024-10-04
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709005010/IF/22012035277968 — Kapil Dhara Koop Nirman kary Bhola Patel / Sukka Gram Bamhouri | Approved | 0 | 0 | 2024-10-10
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709005010/IF/22012035280082 — Kapil Dhara Koop Nirman kary Kailash Vishwakarma/ Ramratan Gram Bamhouri | Approved | 420610.69 | 0 | 2024-10-02
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709005010/IF/22012035280086 — Kapil Dhara Koop Nirman kary Hakki Bai Ahirwar/ Rakku Gram Bamhouri | Approved | 431860.81 | 0 | 2024-10-02
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709005010/IF/22012035280094 — Kapil Dhara Koop Nirman kary Lakhan Patel / Brandravan Gram Bamhouri | Approved | 0 | 0 | 2024-10-02
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709005010/IF/22012035280095 — Kapil Dhara Koop Nirman kary Brajesh Sahu / Ramratan Gram Bamhouri | Approved | 0 | 0 | 2024-10-02
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005010/IF/22012035330047 — KHET TALAB NIRMAN KARY LOKPAL DIMHA GRAM Bamhouri | Ongoing | 199707.85 | 0 | 2025-04-25
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709005010/IF/22012035420269 — Kapil Dhara Koop Nirman kary Parasram Patel / Shankar Gram Bamhouri | Approved | 434521.46 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709005010/IF/22012035454944 — Kapil Dhara Koop Nirman kary Ramcharan Patel/ khutti Gram Bamhouri | New | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709005010/IF/22012035455032 — Kapil Dhara Koop Nirman kary Ramcharan Patel/ Khutti Gram Bamhouri | Ongoing | 434792.85 | 0 | 2025-05-20
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005010/IF/22012035539367 — KHET TALAB NIRMAN KARY PHARASRAM /SHANKAR PATEL GRAM BAMHOURI | Approved | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005010/IF/22012035559942 — KHET TALAB NIRMAN KARY NARAYAN PATEL /KASHIRAM GRAM BAMHOURI | Approved | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/1740275 — Construction of IAY House -IAY REG. NO. MP3600011 | Approved | 27000 | 0 | 2018-04-22
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/4923816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127526091 | Ongoing | 27000 | 0 | 2025-03-07
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5083867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126872884 | Ongoing | 27000 | 0 | 2025-04-02
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5479706 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125754856 | Ongoing | 27000 | 0 | 2025-04-19
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5643531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127506961 | Ongoing | 27000 | 0 | 2025-07-19
PANNA / SHAHNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/57988 — Construction of IAY House -IAY REG. NO. MP-09-005-010-001/2789 | Approved | 27000 | 0 | 2015-11-02
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5931966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126517652 | Ongoing | 27000 | 4500 | 2026-05-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5932081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127234208 | Ongoing | 27000 | 0 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5932293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125553248 | Physically Completed | 27000 | 4500 | 2026-05-01 | 2026-09-27
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5932427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125555116 | Ongoing | 27000 | 0 | 2026-05-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5932430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127494033 | Ongoing | 27000 | 0 | 2026-04-14
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5932452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126281005 | Ongoing | 27000 | 4500 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5932573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126492258 | Ongoing | 27000 | 0 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5932592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127967720 | Ongoing | 27000 | 0 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5932710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126898819 | Ongoing | 27000 | 4200 | 2026-05-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5932798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127315670 | Ongoing | 27000 | 0 | 2026-06-06
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5932837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127534313 | Ongoing | 27000 | 0 | 2026-05-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5932870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127866695 | Physically Completed | 27000 | 0 | 2026-06-06 | 2026-10-18
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5932880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127741672 | Ongoing | 27000 | 0 | 2026-09-10
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5933116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127518869 | Ongoing | 27000 | 0 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5933308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127968558 | Ongoing | 27000 | 0 | 2026-06-06
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5933403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125551820 | Ongoing | 27000 | 3300 | 2026-05-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5933451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126488235 | Ongoing | 27000 | 7500 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5933632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129552957 | Ongoing | 27000 | 0 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5933716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126508584 | Ongoing | 27000 | 5700 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5933806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127236409 | Ongoing | 27000 | 1200 | 2026-04-14
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5933810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126280064 | Ongoing | 27000 | 0 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5933895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131397973 | Physically Completed | 27000 | 0 | 2026-04-14 | 2026-10-11
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5934032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127276869 | Ongoing | 27000 | 0 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5934218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126042509 | Ongoing | 27000 | 5700 | 2026-04-14
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5934245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127522294 | Ongoing | 27000 | 0 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5934307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125527031 | Physically Completed | 27000 | 2400 | 2026-04-14 | 2026-10-11
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5934379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128080024 | Approved | 27000 | 0 | 2026-01-17
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5934381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125526540 | Ongoing | 27000 | 1500 | 2026-04-14
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5934661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127505874 | Ongoing | 27000 | 0 | 2026-06-06
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5934782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127534932 | Ongoing | 27000 | 13500 | 2026-06-06
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5934834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126887038 | Ongoing | 27000 | 7500 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5934845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127184204 | Ongoing | 27000 | 0 | 2026-09-10
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5934864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128781858 | Ongoing | 27000 | 0 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5934944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127465706 | Ongoing | 27000 | 1800 | 2026-04-14
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5935025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126524403 | Ongoing | 27000 | 4200 | 2026-05-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5935058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127317480 | Ongoing | 27000 | 4800 | 2026-05-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5935061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127536261 | Ongoing | 27000 | 0 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5935101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127438927 | Ongoing | 27000 | 9600 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5935216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126281582 | Ongoing | 27000 | 9000 | 2026-05-01
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5935248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129551874 | Ongoing | 27000 | 4500 | 2026-04-14
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5935268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126847936 | Ongoing | 27000 | 0 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5948874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127465333 | Ongoing | 27000 | 3300 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5948883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127493609 | Ongoing | 27000 | 4500 | 2026-09-26
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5950078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126280430 | Ongoing | 27000 | 9000 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5950350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127515425 | Ongoing | 27000 | 0 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5950360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127538983 | Ongoing | 27000 | 0 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5951430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127521023 | Ongoing | 27000 | 4800 | 2026-05-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5951600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131385791 | Ongoing | 27000 | 0 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5952085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126534089 | Ongoing | 27000 | 8700 | 2026-05-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5952278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128783622 | Physically Completed | 27000 | 900 | 2026-04-14 | 2026-09-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5953530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127096600 | Physically Completed | 27000 | 0 | 2026-05-03 | 2026-09-27
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5953531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127097405 | Ongoing | 27000 | 0 | 2026-06-07
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5953649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127535007 | Ongoing | 27000 | 0 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5954037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130924512 | Ongoing | 27000 | 0 | 2026-07-04
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5954438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127504173 | Ongoing | 27000 | 0 | 2026-06-07
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5954562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127517951 | Ongoing | 27000 | 0 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5955442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126537269 | Ongoing | 27000 | 4800 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5956291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127239388 | Physically Completed | 27000 | 4500 | 2026-04-14 | 2026-09-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5956720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127519425 | Ongoing | 27000 | 4800 | 2026-06-07
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5957069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126086182 | Ongoing | 27000 | 0 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5959205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126086985 | Ongoing | 27000 | 0 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5959272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126877210 | Ongoing | 27000 | 0 | 2026-04-14
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5959274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126881871 | Ongoing | 27000 | 4500 | 2026-06-07
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5959284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126900070 | Ongoing | 27000 | 12000 | 2026-06-07
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5959596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127938779 | Ongoing | 27000 | 0 | 2026-05-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5959813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127901152 | Ongoing | 27000 | 12600 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5959815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126507359 | Ongoing | 27000 | 4800 | 2026-05-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5960970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127256529 | Physically Completed | 27000 | 2700 | 2026-05-20 | 2026-09-27
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5961270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127895282 | Ongoing | 27000 | 0 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5962297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126504693 | Ongoing | 27000 | 0 | 2026-09-10
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5962300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126510809 | Ongoing | 27000 | 0 | 2026-06-07
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5962335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127494429 | Physically Completed | 27000 | 5700 | 2026-04-14 | 2026-09-27
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5962574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126585423 | Physically Completed | 27000 | 5700 | 2026-04-14 | 2026-10-11
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5963518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131387644 | Ongoing | 27000 | 0 | 2026-10-13
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5963891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125538128 | Ongoing | 27000 | 5700 | 2026-04-14
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5965942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126873715 | Ongoing | 27000 | 4800 | 2026-09-23
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5966210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127248832 | Ongoing | 27000 | 0 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/5966502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127897511 | Ongoing | 27000 | 0 | 2026-09-10
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6060508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127767994 | Ongoing | 27000 | 0 | 2026-09-09
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6061220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127311353 | Approved | 27000 | 0 | 2026-01-17
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6061227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127327663 | Ongoing | 27000 | 9000 | 2026-05-20
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6062155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126492851 | Ongoing | 27000 | 0 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6062842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126875473 | Ongoing | 27000 | 4500 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6062847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126584532 | Ongoing | 27000 | 4500 | 2026-05-03
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6065876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118544143 | Physically Completed | 27000 | 4500 | 2026-05-03 | 2026-09-27
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6230827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127541352 | Ongoing | 23490 | 9000 | 2026-09-10
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6230828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129552748 | Ongoing | 27000 | 0 | 2026-10-13
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6265542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126518396 | Ongoing | 27000 | 0 | 2026-10-13
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6266980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127322751 | Ongoing | 27000 | 0 | 2026-10-13
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6267457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127493109 | Approved | 27000 | 0 | 2026-01-17
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6267795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127437258 | Approved | 27000 | 0 | 2026-01-17
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6285874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127768217 | Ongoing | 27000 | 0 | 2026-10-13
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6285876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125554234 | Approved | 27000 | 0 | 2026-01-17
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6288747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127310496 | Ongoing | 27000 | 0 | 2026-10-13
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6291936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126510048 | Approved | 27000 | 0 | 2026-01-17
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6335857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127537820 | Approved | 27000 | 0 | 2026-01-17
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6335967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127201913 | Approved | 27000 | 0 | 2026-05-22
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6336003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127265124 | Approved | 27000 | 0 | 2026-01-17
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6336206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126541104 | Approved | 27000 | 0 | 2026-01-17
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6384321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126668688 | Ongoing | 27000 | 0 | 2026-10-13
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6386286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128187001 | Approved | 27000 | 0 | 2026-05-13
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005010/IF/IAY/6398014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126882278 | Ongoing | 27000 | 0 | 2026-10-13
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709005010/WC/22012035200541 — ग्रेवियन निर्माण कार्य बिहारी अहिरवार/ अमना ग्राम बम्हौरी | Approved | 196074.78 | 0 | 2024-06-06
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709005010/WC/22012035200542 — ग्रेवियन निर्माण कार्य पित्ता पटेल/ लटोरा ग्राम बम्हौरी | Approved | 196955.26 | 0 | 2024-06-06
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709005010/WC/22012035200545 — ग्रेवियन निर्माण कार्य रामदास साहु/ नंदी ग्राम बम्हौरी | Approved | 197280.73 | 0 | 2024-06-06
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709005010/WC/22012035248309 — Bolder Chaik Drem Nirman Kary Kher Mata vala nala Bamhouri | Approved | 149868.82 | 0 | 2025-01-26
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709005010/WC/22012035248313 — Bolder Chaik Drem Nirman Kary Bamhouri Talaiya ke pas Bamhouri | Approved | 149368.82 | 0 | 2025-01-26
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1709005010/WC/22012035252483 — PARCULETION TANK NIRMAN KARY SANTOSH KE KHET KE PAS | Approved | 199926.75 | 0 | 2025-01-26