## Work List
Exported on: 2026-09-09 14:35:49
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SATWA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PANNA / SHAHNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1709005012/DP/22012034613233 — निर्मलनीर निर्माण कार्य- शांती धाम पास , ग्राम अर्जुनपुरा | Ongoing | 565702.92 | 0 | 2024-03-16
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709005012/IF/22012035276638 — Kapil Dhara Koop Nirman Kary Baliram Patel / Bhaluwa Gram Satwa | Approved | 0 | 0 | 2024-10-03
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709005012/IF/22012035276646 — Kapil Dhara Koop Nirman Kary Avadh Lal / Shankar Patel | Approved | 0 | 0 | 2024-10-03
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709005012/IF/22012035276658 — Kapil Dhara Koop Nirman Kary Lallu Raja / Lokpal Singh Gram satwa | Approved | 0 | 0 | 2024-10-03
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709005012/IF/22012035276662 — Kapil Dhara Koop Nirman Kary Devraj Singh / Indra Pal Singh Gram Satwa | Approved | 0 | 0 | 2024-10-03
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709005012/IF/22012035276665 — Kapil Dhara Koop Nirman Kary Vrandravan | Approved | 0 | 0 | 2024-10-03
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709005012/IF/22012035332004 — व्यकितगत खेत तालाब निर्माण कार्य - मुन्ना राजा / नारायन सिह ग्राम रानीपुरा | Approved | 248372.05 | 0 | 2025-04-02
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1709005012/IF/22012035332163 — Kapil Dhara Koop Nirman Kary Devraj Singh / Indrapal Singh Gram Satwa | Approved | 433382.58 | 0 | 2025-04-02
PANNA / SHAHNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1709005012/IF/22012035349117 — SATWA JGSA Recharg structure kapildhara koop 1709005012/IF/1000060397 ग्यानी अहिरवार | Approved | 25899.46 | 0 | 2025-04-02
PANNA / SHAHNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1709005012/IF/22012035349226 — SATWA JGSA Recharg structure kapildhara koop 1709005012/IF/9993696484 देवीलाल अहिरवार | Approved | 25899.46 | 0 | 2025-04-02
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709005012/IF/22012035367228 — व्यकितगत खेत तालाब निर्माण कार्य - जीतेंद्र सिह / राघवेंद्र सिह | Approved | 199941.75 | 0 | 2025-04-02
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/4584583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120001167 | Ongoing | 27000 | 0 | 2024-10-24
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/4584584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120001320 | Ongoing | 27000 | 0 | 2024-10-24
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/4623668 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127321614 | Ongoing | 27000 | 0 | 2024-10-23
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/4626372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127523205 | Approved | 27000 | 0 | 2024-11-12
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/4921602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126533011 | Ongoing | 27000 | 0 | 2025-03-18
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/4922406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127332032 | Ongoing | 27000 | 0 | 2025-03-18
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/5472525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128043079 | Ongoing | 27000 | 0 | 2025-05-06
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/5519940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130679295 | Ongoing | 27000 | 0 | 2025-08-01
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/5670243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128526942 | Ongoing | 27000 | 0 | 2025-08-01
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/5761059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120633332 | Physically Completed | 23490 | 0 | 2025-10-31 | 2026-08-02
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/5761097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128516087 | Ongoing | 27000 | 0 | 2025-11-02
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/5763203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126531257 | Ongoing | 27000 | 0 | 2025-09-02
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/5763757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125121969 | Physically Completed | 27000 | 0 | 2025-11-02 | 2026-09-06
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005012/IF/IAY/5860401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127893652 | Ongoing | 27000 | 0 | 2026-06-17
PANNA / SHAHNAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709005012/RC/22012034843107 — सी सी रोड निर्माण कार्य नल पास से शांती धाम तक ग्राम अर्जुनपुरा | New | 0 | 0 | 2025-05-14
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1709005012/WC/22012035255182 — बोल्डर चेक डेम निर्माण कार्य - भजिया नाला पर रब्बी यादव खेत पास, ग्राम भजिया | Approved | 280621.95 | 0 | 2025-01-25
PANNA / SHAHNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1709005012/WC/VB/22012035331139 — टॉप रूफ रैन वाटर हार्वेस्टिंग सामुदायक भवन बिलहा सटवा | Approved | 30861.94 | 0 | 2026-07-15
PANNA / SHAHNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1709005012/WC/VB/22012035331140 — टॉप रुफ वाटर हार्वेस्टिंग सामुदायिक स्वच्छता परिसर बिल्हा सटवा | Ongoing | 30861.94 | 17100 | 2026-08-11
PANNA / SHAHNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1709005012/WC/VB/22012035331141 — Top Roof Water Harvesting Aganwadi bhavan Mandirpura Satwa | Approved | 30861.94 | 0 | 2026-07-15