## Work List
Exported on: 2026-10-22 07:33:41
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PHATEPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PANNA / SHAHNAGAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1709005016/AV/22012034544411 — PHTEPUR-SAMUDAYIK GOUSHALA JODHPUR | Ongoing | 3804449.17 | 0 | 2021-01-31
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1709005016/IC/22012034890174 — boldar chek dem dudhariya nala | New | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1709005016/IC/22012034890176 — boldar chek dem dudhariya nala seja bare khet pass phatepur | New | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1709005016/IF/22012034318294 — Kapildharakoopkeshrani/parshulakhanchouri | Ongoing | 200000 | 0 | 2017-02-04
PANNA / SHAHNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Well for Individual | Construction of Well | 1709005016/IF/22012034327631 — kapil dhara koop imrat /ralli lakhanchouri | Ongoing | 200000 | 0 | 2017-03-19
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1709005016/IF/22012035310593 — Khet Talab Nirman Binod Singh /Rajaram Makkepala | New | 0 | 0 | 2025-01-25
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005016/IF/22012035310615 — Khet Talab Nirman Keshrani/parsu Lakhanchouri | New | 0 | 0 | 2025-01-25
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005016/IF/22012035310619 — Khet Talab Nirman Imrat /Ralli Lakhanchouri | New | 0 | 0 | 2025-01-25
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1709005016/IF/22012035342586 — Khet Talab nirman binod singh makkepala | New | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005016/IF/22012035342670 — Khet Talab nirman deelan singh tulsiram ghutehi | New | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1709005016/IF/22012035342804 — Khet Talab nirman prem Singh lakhanchouri | New | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1709005016/IF/22012035342854 — Khet Talab NIRMAN KARAN SINGH Parsu Singh | New | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1709005016/IF/22012035342887 — Khet talab mahesh singh Hari singh | New | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1709005016/IF/22012035342972 — nirmanneer lakhanchouri ball singh ke khet pass | New | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1709005016/IF/22012035343224 — kapil dhara koop mahraj singh makkepala | New | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1709005016/IF/22012035343274 — kapil dhara koop hallu singh makkepala | New | 0 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005016/IF/22012035350034 — फतेपुर -खेत तालाब निर्माण कार्य केशरानी /परसु | Approved | 199426.06 | 0 | 2025-04-14
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005016/IF/22012035350037 — फतेपुर -खेत तालाब निर्माण कार्य प्रेमसिंह /नोनेलाल | Ongoing | 198579.76 | 0 | 2025-05-01
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1709005016/IF/22012035350042 — फतेपुर -खेत तालाब निर्माण कार्य mhesh/हरी सिंह | Ongoing | 198900.24 | 0 | 2025-05-04
PANNA / SHAHNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1709005016/IF/22012035462552 — फतेपुर- रिचार्ज पिट कार्य kanchedi कूप के पास | Ongoing | 25899.46 | 0 | 2025-05-22
PANNA / SHAHNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1709005016/IF/22012035462592 — फतेपुर -रिचार्ज पिट निर्माण कार्य हरि सिंह | Ongoing | 25899.46 | 0 | 2025-05-22
PANNA / SHAHNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1709005016/IF/22012035462614 — फतेपुर -रिचार्ज पिट निर्माण कार्य मोहन सिंह | Ongoing | 25899.46 | 0 | 2025-06-30
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4588718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121346948 | Ongoing | 27000 | 0 | 2025-01-01
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4590125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121371798 | Ongoing | 27000 | 0 | 2024-11-25
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4599719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123356688 | Ongoing | 27000 | 0 | 2025-01-01
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4601567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124183921 | Ongoing | 27000 | 0 | 2025-01-01
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4607859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123834745 | Ongoing | 27000 | 0 | 2025-01-01
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4634344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129114279 | Ongoing | 27000 | 0 | 2025-01-01
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4634452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129224738 | Ongoing | 27000 | 0 | 2025-01-01
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4763309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121357838 | Ongoing | 27000 | 0 | 2024-11-25
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4763776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122119333 | Physically Completed | 27000 | 0 | 2025-02-02 | 2026-10-18
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4763791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122123650 | Ongoing | 27000 | 0 | 2025-01-01
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4767650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123365690 | Ongoing | 27000 | 0 | 2025-01-01
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4769436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124181970 | Ongoing | 27000 | 0 | 2025-01-01
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4873916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121367969 | Ongoing | 27000 | 0 | 2025-04-03
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4873917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121370880 | Physically Completed | 23490 | 0 | 2025-04-03 | 2026-08-09
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4917764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121684575 | Ongoing | 27000 | 0 | 2025-09-27
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4918403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121373260 | Ongoing | 27000 | 0 | 2025-04-03
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/4918633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123366294 | Ongoing | 27000 | 0 | 2026-02-17
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5500446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123360677 | Ongoing | 27000 | 0 | 2025-09-29
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5525391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129227137 | Ongoing | 27000 | 8400 | 2026-02-17
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5639018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121370264 | Ongoing | 27000 | 0 | 2025-11-04
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5859922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129224074 | Ongoing | 27000 | 0 | 2026-02-17
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122131262 | Ongoing | 27000 | 0 | 2026-02-17
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122133376 | Approved | 27000 | 0 | 2025-02-16
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122118019 | Physically Completed | 27000 | 0 | 2026-01-02 | 2026-10-11
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122125472 | Approved | 27000 | 0 | 2025-02-16
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123363897 | Ongoing | 27000 | 0 | 2026-02-17
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123364538 | Ongoing | 27000 | 0 | 2026-02-17
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124176891 | Physically Completed | 27000 | 0 | 2026-06-12 | 2026-09-27
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124184603 | Ongoing | 27000 | 0 | 2026-01-02
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129224098 | Approved | 27000 | 0 | 2025-03-28
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129225097 | Ongoing | 27000 | 0 | 2026-01-02
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121352421 | Ongoing | 27000 | 0 | 2026-10-07
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121353073 | Approved | 27000 | 0 | 2025-02-16
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121685570 | Ongoing | 27000 | 0 | 2026-06-12
PANNA / SHAHNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121368195 | Ongoing | 27000 | 0 | 2026-05-08
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123355042 | Approved | 27000 | 0 | 2025-02-16
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123370890 | Ongoing | 27000 | 0 | 2026-01-02
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123371482 | Approved | 27000 | 0 | 2025-02-16
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121349859 | Approved | 27000 | 0 | 2024-09-29
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/5860348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123836698 | Ongoing | 27000 | 0 | 2026-01-02
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/6384736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123367566 | Approved | 27000 | 0 | 2025-02-16
PANNA / SHAHNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/72846 — Construction of IAY House -IAY REG. NO. MP-09-005-016-001/3788 | Approved | 27000 | 0 | 2015-09-28
PANNA / SHAHNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/72847 — Construction of IAY House -IAY REG. NO. MP-09-005-016-002/3819 | Approved | 27000 | 0 | 2015-09-28
PANNA / SHAHNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/72848 — Construction of IAY House -IAY REG. NO. MP-09-005-016-002/3822 | Approved | 27000 | 0 | 2015-09-28
PANNA / SHAHNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1709005016/IF/IAY/747520 — Construction of IAY House -IAY REG. NO. MP2452872 | Approved | 27000 | 0 | 2017-03-20
PANNA / SHAHNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1709005016/RC/22012034450118 — KANCHANPURA- CC ROAD + NALI NIRMAN KUNJAN KE GHAR SE BHAIYAN KE GHAR TAK | Ongoing | 84000 | 0 | 2019-06-14
PANNA / SHAHNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja Road for Community | Construction of Road and Culvert | 1709005016/RC/22012034839681 — Khet Talab Deelan Singh/Dharamdash GHUTEHI | New | 0 | 0 | 2025-01-25
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1709005016/WC/22012035215288 — Gp-Fatepur Greviyan Nirman Ridha nala pr shukh singh ke khet ke pas | Approved | 0 | 0 | 2024-06-06
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1709005016/WC/22012035215292 — Gp-Fatepur Greviyan Nirman Ridha nala pr shukh singh ke khet ke pas | Approved | 0 | 0 | 2024-06-06
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1709005016/WC/22012035215300 — Gp-Fatepur Greviyan Nirman Ridha nala pr khilane singh ke khet ke pas | Approved | 0 | 0 | 2024-06-06
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709005016/WC/22012035217158 — Gp-Fatepur Greviyan Nirman Ridha nala pr shukh singh ke khet ke pas | Approved | 236685.19 | 0 | 2024-04-07
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709005016/WC/22012035217159 — Gp-Fatepur Greviyan Nirman Ridha nala pr khilane singh ke khet ke pas | Approved | 236685.19 | 0 | 2024-04-07
PANNA / SHAHNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1709005016/WC/22012035217160 — Gp-Fatepur Greviyan Nirman Ridha nala pr shivraj singh ke khet ke pas | Approved | 236685.19 | 0 | 2024-04-07
PANNA / SHAHNAGAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Farm Roads for Community | Construction of Road and Culvert | 1709005/RC/199 — फतेपुर-बिगडेवनो का सुधार लालपुरा | Ongoing | 257000 | 0 | 2008-10-21