## Work List
Exported on: 2026-10-12 07:21:06
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: HARDUASARASBAHU
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PANNA / SHAHNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1709005019/DP/22012034524499 — निर्मल नीर कूप निर्माण कार्य -ग्राम पटेरिया | Physically Completed | 567610.07 | 422779.68 | 2021-05-12 | 2026-05-06
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709005019/IF/22012035374068 — Khet Talab Nirman Karya Jalam Singh/Laxman Singh | Physically Completed | 198819.39 | 187293.64 | 2025-05-14 | 2026-04-19
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709005019/IF/22012035374145 — Khet talab None lal/Laxman | Physically Completed | 198819.39 | 186555.68 | 2025-05-09 | 2026-04-19
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709005019/IF/22012035374155 — Khet talab Indresh/Mathura | Physically Completed | 198819.39 | 184845.58 | 2025-05-14 | 2026-04-19
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1709005019/IF/22012035374171 — Khet Talab Mohan/Halke | Physically Completed | 198819.39 | 187980.34 | 2025-05-14 | 2026-04-19
PANNA / SHAHNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1709005019/IF/22012035462358 — Recharge Pit Nathuwa choudhary/ganthola | Physically Completed | 25899.46 | 25737.2 | 2025-05-12 | 2026-05-08
PANNA / SHAHNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1709005019/IF/22012035517263 — Dugwell Recharge Pit Shankar/Ramesh Yadav | Physically Completed | 25899.46 | 24207.26 | 2025-05-21 | 2026-05-12
PANNA / SHAHNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1709005019/IF/22012035517280 — Dugwell Recharge Pit Mulayam singh/Gajraj singh | Physically Completed | 25899.46 | 24217.22 | 2025-05-21 | 2026-05-12
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005019/IF/IAY/4611576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125535375 | Physically Completed | 23490 | 22986 | 2024-12-16 | 2026-05-31
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005019/IF/IAY/4611866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125474854 | Physically Completed | 23490 | 22086 | 2024-12-16 | 2026-05-03
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005019/IF/IAY/4613328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125738334 | Physically Completed | 23490 | 22716 | 2025-02-17 | 2026-01-22
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005019/IF/IAY/4616393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126078144 | Physically Completed | 23490 | 22455 | 2025-03-25 | 2026-06-07
PANNA / SHAHNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005019/IF/IAY/4919708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125538596 | Physically Completed | 23490 | 23112 | 2025-03-07 | 2026-02-15
PANNA / SHAHNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1709005019/IF/IAY/5226425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124124886 | Physically Completed | 23490 | 22968 | 2025-07-19 | 2026-05-03
PANNA / SHAHNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709005019/RC/22012034818782 — सी सी रोड एवं नाली निर्माण कार्य प्रकाश के घर से नरेंद्र के घर की ओर | Physically Completed | 110000 | 57591 | 2024-06-24 | 2026-05-06
PANNA / SHAHNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1709005019/WC/22012035126923 — BOLDER CHEK DEM NIRMAN PATPARHAI NALA DOBHABAGHNARVA | Physically Completed | 256335.14 | 236535.19 | 2023-10-10 | 2026-04-21
PANNA / SHAHNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1709005019/WC/22012035126943 — BOLDER CHEK NIRMAN PANGHATA NALA DOBHABAGHNARVA | Physically Completed | 232882.66 | 228270 | 2023-12-08 | 2026-04-21
PANNA / SHAHNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1709005019/WC/22012035148630 — COMUNITY PARKULATION TANK HARDUA GIJAR | Physically Completed | 601522.23 | 518143.27 | 2024-02-21 | 2026-04-21
PANNA / SHAHNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1709/RC/22012034611007 — CMGSY Road Maintenance work Main Road To Pateriya GP. Harduya Sarasbahu JP Shahnagar | Physically Completed | 613000 | 359772.86 | 2022-03-30 | 2026-06-21