## Work List
Exported on: 2026-10-02 00:03:09
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SEMERA GANPAT RAO (P)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SAGAR / KHURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1710002012/IF/22012034692278 — PASHU SHED NIRMAN AVADHBAI / NIRANJAN | Ongoing | 102033.26 | 0 | 2021-08-09
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002012/IF/22012035294925 — khet talab Dharmendra/Harikrishna kurmi | New | 0 | 0 | 2024-10-02
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002012/IF/22012035408345 — khet Talab balram kurmi Bamhori | New | 0 | 0 | 2025-04-24
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002012/IF/22012035408446 — Khet Talab Sarojrani gram Semra Ganpat rao | New | 0 | 0 | 2025-04-24
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002012/IF/22012035434366 — Khet Talab Mohan gram panchayat Semra Ganpat | Ongoing | 147621.16 | 0 | 2025-05-01
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002012/IF/22012035434463 — Khet Talab Balram Kurmi gram Panchayat Semra ganpat | New | 0 | 0 | 2025-04-24
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002012/IF/22012035434630 — Khet Talab Balram Kurmi gram Panchayat Semra ganpat | Ongoing | 147621.16 | 0 | 2025-05-19
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002012/IF/22012035434691 — Khet Talab Prem Singh gram Panchayat Semra gantat | Ongoing | 147621.16 | 0 | 2025-05-01
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002012/IF/22012035554762 — khet talab nirman Veerpatap Singh Kurmi Bamori khadera | Approved | 0 | 0 | 2025-04-14
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002012/IF/22012035554783 — Khet talab Nirman Prabha Bai Semra Ganpat rao | Approved | 0 | 0 | 2025-04-14
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002012/IF/22012035554790 — Khet talab Nirman Ramkumar kurmi bamori khadera | Approved | 0 | 0 | 2025-04-14
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1710002012/IF/22012035610270 — ek bagiya maa ke naam Laxmi Bai Dangi | Ongoing | 264026.75 | 1800 | 2025-09-20
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002012/IF/IAY/4580443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118543099 | Ongoing | 27000 | 0 | 2025-03-25
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002012/IF/IAY/4580458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118544333 | Ongoing | 27000 | 0 | 2025-03-25
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002012/IF/IAY/4644447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137754058 | Ongoing | 27000 | 0 | 2025-02-10
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002012/IF/IAY/5194172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120561704 | Ongoing | 27000 | 0 | 2025-06-24
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002012/IF/IAY/5945109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120608043 | Ongoing | 27000 | 0 | 2026-04-09
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002012/IF/IAY/5945245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125823715 | Approved | 27000 | 0 | 2025-02-12
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002012/IF/IAY/5946174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120589234 | Approved | 27000 | 0 | 2025-03-02
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002012/IF/IAY/5946817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118560214 | Ongoing | 27000 | 0 | 2026-04-09
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002012/IF/IAY/5946863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118542387 | Approved | 27000 | 0 | 2025-03-02
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002012/IF/IAY/5946865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118543155 | Approved | 27000 | 0 | 2025-05-15
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002012/IF/IAY/5947351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120585869 | Ongoing | 27000 | 0 | 2026-04-09
SAGAR / KHURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1710002012/LD/22012034593567 — VASUDHA VANDAN AMRAT VATIKA NIRMAN SEMRA GANPAT RAO | Ongoing | 54564.94 | 0 | 2023-08-22
SAGAR / KHURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1710002012/RC/22012034657180 — CC ROAD NANI NIRMAN MEN ROAD SE TAVAR KI OR SEMRA GANPAT RAO | Ongoing | 64000 | 0 | 2023-10-13
SAGAR / KHURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1710002012/RS/22012034706642 — RCC NALI NIRMAN MUKHYA SADAK SE RAVIDAS MANDIR KI OR SEMRA GANPAT RAO | Ongoing | 22000 | 0 | 2024-08-04