## Work List
Exported on: 2026-10-12 19:09:43
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BAHROL (P)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SAGAR / KHURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1710002016/IF/22012035186239 — कपिल धारा रीना / डेलन कुर्मी | Ongoing | 282417.57 | 0 | 2024-03-05
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1710002016/IF/22012035198544 — KAPIL DHARA KOOP NIRMAN SURENDRA / KEDAR KURMI DHEMADHANA | Ongoing | 282417.57 | 0 | 2025-05-04
SAGAR / KHURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1710002016/IF/22012035246181 — PLANTATION KARAY FULSINGH / CHOUDE RAJAK BAHROL | Approved | 145050.83 | 0 | 2024-04-14
SAGAR / KHURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1710002016/IF/22012035255413 — PLANTATION KARY UTTAR SINGH / GOURISHANKAR KURMI DHEMADHANA | Approved | 0 | 0 | 2024-06-12
SAGAR / KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1710002016/IF/22012035470256 — Jgsv recharge pit nirman Kapil dhara koop kailash yadav dhemadhana | Ongoing | 25899.46 | 0 | 2025-05-07
SAGAR / KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1710002016/IF/22012035484940 — jgsa dugwell recharge rakesh/bhaiyalal kapil dhara koop ke pass dhemadhana | New | 0 | 0 | 2025-04-14
SAGAR / KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1710002016/IF/22012035485035 — jgsa dugwell recharge pit sanjeev/babulal ke kapil dhara koop ke pass dhemadhana | New | 0 | 0 | 2025-04-14
SAGAR / KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1710002016/IF/22012035485260 — jgsa dugwell recharge pit rajendra singh ke kapil dhara koop ke pass dhemadhana | New | 0 | 0 | 2025-04-14
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1710002016/IF/22012035485430 — jgsa khet talab nirman ramesh /pran singh dhemadhana | Ongoing | 25899.46 | 0 | 2025-05-07
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individual | Goat Shelter | 1710002016/IF/22012035579086 — bakri shed nirman sona bai ahirwar bahrol | New | 0 | 0 | 2025-04-14
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individual | Goat Shelter | 1710002016/IF/22012035579088 — bakri shed nirman sona bai ahirwar bahrol | Approved | 0 | 0 | 2025-04-14
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individual | Goat Shelter | 1710002016/IF/22012035579094 — bakri shed sudharani dhanak bahrol | Ongoing | 57842.61 | 0 | 2025-12-31
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individual | Goat Shelter | 1710002016/IF/22012035579095 — bakri shed nirman shubhratan /munna bahrol | Ongoing | 58016.3 | 0 | 2025-12-25
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1710002016/IF/22012035590959 — EK BAGIYA MA KE NAAM IS AJAAD RANI RAJAK BAHROL | Ongoing | 286524.91 | 0 | 2025-09-01
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Bio-drainage Plantation for Individual | Plantation | 1710002016/IF/22012035605159 — एक बगिया मा के नाम सुकून बाई ढेमा ढाना | New | 0 | 0 | 2025-08-15
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1710002016/IF/22012035605770 — EK BAGIYA MA KE NAAM SAKUN BAI DHEMADHANA | Ongoing | 264026.75 | 0 | 2025-09-03
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1710002016/IF/22012035605786 — EK BAGIYA MA KE NAAM SANJAY RANI BAHROL | Ongoing | 264026.75 | 7200 | 2025-09-05
SAGAR / KHURAI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/3257464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3347876 | Ongoing | 27000 | 0 | 2022-05-22
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/4621097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126528808 | Ongoing | 27000 | 0 | 2025-03-13
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/4623963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126563214 | Ongoing | 27000 | 0 | 2025-04-09
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/4713212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126654235 | Ongoing | 27000 | 0 | 2025-07-07
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/5605274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120637667 | Ongoing | 27000 | 4200 | 2025-08-25
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/5815196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124239284 | Approved | 27000 | 0 | 2025-03-13
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/5865580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125286944 | Ongoing | 27000 | 0 | 2026-06-08
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/5865649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126640597 | Approved | 27000 | 0 | 2025-03-13
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/5865653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124311301 | Ongoing | 27000 | 0 | 2025-12-24
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/5865842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126613936 | Approved | 27000 | 0 | 2025-03-13
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/5865927 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151101853 | Ongoing | 27000 | 0 | 2025-12-30
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/5865998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124424312 | Ongoing | 27000 | 0 | 2025-12-24
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/5866083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121364927 | Approved | 27000 | 0 | 2025-03-08
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/5866137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142539146 | Ongoing | 27000 | 0 | 2026-07-22
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/5866149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126651610 | Approved | 27000 | 0 | 2025-02-12
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/5974624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126619006 | Ongoing | 27000 | 12300 | 2026-07-22
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/5974926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121395379 | Approved | 27000 | 0 | 2026-02-19
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/6020392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120665607 | Ongoing | 27000 | 16800 | 2026-07-22
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/6025677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120873563 | Ongoing | 27000 | 8400 | 2026-07-22
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/6036698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126630264 | Ongoing | 27000 | 0 | 2026-06-08
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002016/IF/IAY/6322610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126551303 | Approved | 27000 | 0 | 2025-03-08
SAGAR / KHURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1710002016/LD/22012034593621 — VASUDHA VANDAN AMRAT VATIKA NIRMAN pushkar dharohar bahrol | Ongoing | 55847.4 | 0 | 2023-04-14
SAGAR / KHURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1710002016/RC/22012034628106 — cc road nali nirman kashiram dhanak ke ghar se ramdayalke & mahes, gajraj ke ghar tak dariya | Ongoing | 19050 | 0 | 2023-08-16
SAGAR / KHURAI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1710002016/RC/22012034670748 — CC ROAD NIRMAN THANSINGH KE GHAR SE RATIRAM AHIRWAR KE GHAR TAK BAHROL | Ongoing | 45000 | 0 | 2023-12-29
SAGAR / KHURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1710002016/RC/22012034836025 — CC ROAD NALI NIRMAN GRAM DARAIYA | Approved | 51000 | 0 | 2025-01-25
SAGAR / KHURAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1710002016/WC/22012035272618 — JGSA 2025 Recharg Stucture Nirmal Neer Dhemadhana | Ongoing | 25899.46 | 0 | 2026-04-08
SAGAR / KHURAI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1710002016/WC/22012035272631 — JGSA 2025 Recharg Stucture Nirmal Neer Bahrol | Ongoing | 25899.46 | 0 | 2026-04-08