## Work List
Exported on: 2026-09-09 20:45:00
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SARKHADI (P)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SAGAR / KHURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1710002037/IF/22012034603846 — pashu shed nirman kishan / babulal ahirwar | Ongoing | 63830.2 | 0 | 2020-10-28
SAGAR / KHURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1710002037/IF/22012034606644 — pashu shed nirman kavita sharma | Ongoing | 101804.91 | 0 | 2020-12-23
SAGAR / KHURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1710002037/IF/22012034614794 — pashu shed nirman mulu /khilan adiwasi | Ongoing | 63830.2 | 0 | 2020-10-28
SAGAR / KHURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1710002037/IF/22012034614796 — pashu shed nirman prabhu / dujje adiwasi | Ongoing | 63830.2 | 0 | 2020-10-28
SAGAR / KHURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1710002037/IF/22012034662393 — PASHU SH ED NIRMAN TAKHAT SINGH / UMEDI ADIWASI | Ongoing | 101804.91 | 0 | 2021-03-23
SAGAR / KHURAI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1710002037/IF/22012034664561 — pashu shed nirman ramkishan adiwasi | Ongoing | 101804.91 | 0 | 2021-03-23
SAGAR / KHURAI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002037/IF/22012034765495 — CTR KHET TALAB NIRMAN PARSOTTAM LODHI SARKHADI | Ongoing | 110516.06 | 0 | 2022-03-25
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002037/IF/22012035423665 — JGSA 2025 KHET TALAB NIRMAN KARY MOHAN AHIRWAR S/O HALKAI AHIRWAR GRAM ISHARWARA | Ongoing | 147621.16 | 0 | 2025-05-01
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002037/IF/22012035423685 — JGSA 2025 KHET TALAB NIRMAN KARY HARIRAM AHIRWAR S/O GAJJU AHIRWAR GRAM SARKHADI | Ongoing | 147621.16 | 0 | 2025-05-01
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002037/IF/22012035423695 — JGSA 2025 KHET TALAB NIRMAN KARY SURJAN SINGH RAJPOOT S/O BHAGWAAN SINGH GRAM SARKHADI | Ongoing | 147621.16 | 0 | 2025-05-01
SAGAR / KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1710002037/IF/22012035559212 — JGSA 2025 RECHARGE STRUCTURE KHAPIL DHARA KOOP CHATRA AHIRWAR | Approved | 25899.46 | 0 | 2025-04-14
SAGAR / KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1710002037/IF/22012035559219 — JGSA 2025 RECHARGE STRUCTURE KHAPIL DHARA KOOP FADDA AHIRWAR | Approved | 25899.46 | 0 | 2025-04-14
SAGAR / KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1710002037/IF/22012035559225 — JGSA 2025 RECHARGE STRUCTURE KHAPIL DHARA KOOP RADHARANI RAJPOOT | Approved | 25899.46 | 0 | 2025-04-14
SAGAR / KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1710002037/IF/22012035559229 — JGSA 2025 RECHARGE STRUCTURE KHAPIL DHARA KOOP KHEMA BANJARA | Approved | 25899.46 | 0 | 2025-04-14
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/2762038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4058814 | Ongoing | 27000 | 0 | 2024-06-14
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/2769102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5166111 | Ongoing | 27000 | 0 | 2024-06-28
SAGAR / KHURAI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/3948821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141916045 | Ongoing | 27000 | 0 | 2023-10-13
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/4573065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117404035 | Ongoing | 27000 | 0 | 2024-10-01
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/4573172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117415623 | Ongoing | 27000 | 0 | 2024-10-01
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/4585999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119874535 | Ongoing | 27000 | 0 | 2024-10-01
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/4592503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121620508 | Ongoing | 27000 | 0 | 2024-10-01
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/4595376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122765688 | Ongoing | 27000 | 0 | 2024-11-29
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/4602107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122741975 | Ongoing | 27000 | 0 | 2024-12-09
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/4606404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123806495 | Ongoing | 27000 | 0 | 2024-12-09
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/4620964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126517141 | Ongoing | 27000 | 0 | 2024-10-11
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/4706617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122724997 | Ongoing | 27000 | 0 | 2024-10-11
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/4718862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125073557 | Ongoing | 27000 | 0 | 2024-10-13
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/4718870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125075550 | Ongoing | 27000 | 0 | 2024-12-09
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/4764894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122754792 | Ongoing | 27000 | 0 | 2024-12-09
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/4852355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151171316 | Ongoing | 27000 | 0 | 2024-12-09
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5148548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119869024 | Approved | 27000 | 0 | 2025-03-05
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5156449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116924297 | Ongoing | 27000 | 0 | 2025-09-24
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5157854 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151285461 | Ongoing | 27000 | 0 | 2026-03-23
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5161997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123805039 | Ongoing | 27000 | 0 | 2026-03-23
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5241238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117607858 | Approved | 27000 | 0 | 2025-03-05
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5814614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126287015 | Approved | 27000 | 0 | 2025-03-05
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5814615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126287587 | Approved | 27000 | 0 | 2025-03-05
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5814638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119977360 | Approved | 27000 | 0 | 2025-03-07
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5814685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117411563 | Approved | 27000 | 0 | 2025-02-17
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5814720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151291263 | Approved | 27000 | 0 | 2025-02-12
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5814752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116443551 | Approved | 27000 | 0 | 2025-02-17
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5814792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126066387 | Approved | 27000 | 0 | 2025-05-27
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5814990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115339661 | Ongoing | 27000 | 0 | 2025-12-07
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119867536 | Ongoing | 27000 | 0 | 2026-08-06
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115343352 | Ongoing | 27000 | 0 | 2025-11-21
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116050118 | Approved | 27000 | 0 | 2025-02-27
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115669089 | Ongoing | 27000 | 0 | 2026-05-08
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115669113 | Approved | 27000 | 0 | 2025-02-17
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115731863 | Ongoing | 27000 | 0 | 2026-05-26
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115314236 | Ongoing | 27000 | 0 | 2025-09-24
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117783561 | Approved | 27000 | 0 | 2025-02-27
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115362213 | Ongoing | 27000 | 0 | 2026-04-09
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123534706 | Approved | 27000 | 0 | 2025-03-05
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118745995 | Approved | 27000 | 0 | 2025-02-27
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126303005 | Ongoing | 27000 | 0 | 2026-08-06
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117576273 | Ongoing | 27000 | 0 | 2025-10-29
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115356504 | Approved | 27000 | 0 | 2025-02-12
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115347395 | Ongoing | 27000 | 0 | 2025-11-21
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123802638 | Ongoing | 27000 | 0 | 2026-04-09
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124126700 | Ongoing | 27000 | 0 | 2025-10-25
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115720644 | Approved | 27000 | 0 | 2025-03-01
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115722744 | Physically Completed | 23490 | 0 | 2025-09-24 | 2026-07-19
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121614169 | Approved | 27000 | 0 | 2025-03-05
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126516404 | Ongoing | 27000 | 0 | 2026-04-09
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119985139 | Ongoing | 27000 | 0 | 2025-10-29
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123807561 | Approved | 27000 | 0 | 2025-06-03
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119858208 | Approved | 27000 | 0 | 2025-03-05
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119981415 | Ongoing | 27000 | 0 | 2026-07-28
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122383228 | Approved | 27000 | 0 | 2025-03-05
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116114175 | Ongoing | 27000 | 0 | 2025-12-07
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118744101 | Approved | 27000 | 0 | 2025-02-12
SAGAR / KHURAI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5815908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116041573 | Ongoing | 27000 | 0 | 2026-07-09
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002037/IF/IAY/5872888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122412030 | Approved | 27000 | 0 | 2025-09-16
SAGAR / KHURAI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1710002037/RC/22012034574408 — KHET SADAK MEN ROD ISHURWARA PULIYASE PANCHAM SEN KE KHET KI OR | Ongoing | 1498085.81 | 0 | 2021-06-21
SAGAR / KHURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1710002037/RC/22012034832934 — CC ROAD ORAN KE GHAR SE MEN ROAD KI OR SARKHADI | Ongoing | 60000 | 0 | 2025-01-16
SAGAR / KHURAI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1710002037/RC/22012034832943 — cc road magu banjara ke ghar se bhole ke ghar ki or | Ongoing | 34000 | 0 | 2025-06-19
SAGAR / KHURAI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1710002037/WC/22012034873129 — CHEK DEM NIRMAN SARKHADI | Ongoing | 99000 | 0 | 2021-11-16
SAGAR / KHURAI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1710002037/WC/22012035293360 — JGSA 2025 सामुदायिक तालाब निर्माण कार्य शमशान के पास ग्राम सरखडी | Approved | 0 | 0 | 2025-04-14