## Work List
Exported on: 2026-10-15 21:23:53
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: ASOLIGHAT
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SAGAR / KHURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1710002064/AV/22012034657262 — shantidham nirman asholi ghat | Approved | 229312.16 | 0 | 2024-06-08
SAGAR / KHURAI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1710002064/DP/22012034607722 — BASUDHA BANDAN BIRACHA ROPAN ASOLI | Ongoing | 55847.4 | 663 | 2023-09-08
SAGAR / KHURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of Water Courses and Field Channels for Community | Construction of Canal | 1710002064/IC/22012034884821 — Khet Talab Nirman Pran Singh/Amol Singh Giltora | New | 0 | 0 | 2024-06-08
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1710002064/IF/22012035236576 — Khet Talab Nirman Omvati/ Lal Singh Giltora | New | 0 | 0 | 2024-06-08
SAGAR / KHURAI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1710002064/IF/22012035246183 — Plantation Pran Singh /Amol Singh Asholi Ghat | Ongoing | 151484.66 | 52453.63 | 2024-09-04
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1710002064/IF/22012035377723 — khet talab Jagat singh/Amolsingh giltora | Ongoing | 199143.67 | 26510.99 | 2025-04-25
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1710002064/IF/22012035377799 — khet talab Pran singh/Amolsingh giltora | Completed | 199143.67 | 154251 | 2025-05-07 | 2026-04-12
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1710002064/IF/22012035377852 — Khet talab Harnam singh/Jorabal lodhi | Ongoing | 199143.67 | 26510.99 | 2025-04-25
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1710002064/IF/22012035401828 — JGSA Khet talab nirman prem | Approved | 196789.16 | 0 | 2025-04-14
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1710002064/IF/22012035498984 — Construction of IAY House kanai Ahirwar-IAY REG. NO. MP123514180 | Completed | 23490 | 23229 | 2025-06-10 | 2026-05-21
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1710002064/IF/22012035499008 — Construction of IAY House Damodar Thakur -IAY REG. NO. MP123569289 | Completed | 23490 | 21141 | 2025-07-12 | 2026-05-21
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1710002064/IF/22012035618208 — Ek Bagiya Maa Ke Naam Laxmi/Lokram Lodhi Giltora GP Asholi Ghat | New | 0 | 0 | 2025-08-15
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1710002064/IF/22012035625603 — Pmay g Anjani Lodhi MP117473072 | Approved | 23490 | 0 | 2025-08-15
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1710002064/IF/22012035633915 — Pmay G Rajendra PalMP123580347 | Completed | 23490 | 20358 | 2025-11-04 | 2026-06-22
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002064/IF/IAY/4707879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123570044 | Completed | 23490 | 22266 | 2025-02-27 | 2025-07-02
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002064/IF/IAY/4767966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123568870 | Completed | 23490 | 22572 | 2025-02-27 | 2026-04-01
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002064/IF/IAY/4767971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123570798 | Completed | 23490 | 21771 | 2025-02-27 | 2025-05-09
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002064/IF/IAY/4768016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123585905 | Approved | 27000 | 0 | 2024-10-07
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002064/IF/IAY/5843875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117473072 | Completed | 23490 | 21141 | 2025-10-24 | 2026-05-24
SAGAR / KHURAI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002064/IF/IAY/5844542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123569289 | Physically Completed | 23490 | 0 | 2025-02-17 | 2026-04-12
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1710002064/IF/IAY/5844851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123586784 | Completed | 23490 | 22185 | 2025-10-24 | 2026-05-30
SAGAR / KHURAI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1710002064/IF/IAY/5845770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123569697 | Ongoing | 27000 | 19053 | 2025-11-13
SAGAR / KHURAI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1710002064/RC/22012034666918 — सी सी नाली निर्माण संतोष के घर से प्रथमि स्कूल की ओर | Completed | 65000 | 64881 | 2025-02-23 | 2025-12-16
SAGAR / KHURAI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1710002064/RC/22012034837513 — सी सी रोड निर्माण कार्य पंचम के घर से देवीजी के चबूतरा तक ग्राम गिल्टोरा | Completed | 75000 | 74646 | 2025-04-09 | 2025-12-15
SAGAR / KHURAI | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1710002064/RC/VB/YD/22012034854656 — CC Road प्राथमिक शाला भवन से शासकीय कुआँ की ओर | Approved | 0 | 0 | 2026-08-15