## Work List
Exported on: 2026-09-26 18:04:15
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: PHUTAUNDHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1712002091/AV/1085 — Aanganbadi Bhavan Nirman Sewa Kendra,SATNA | Completed | 450000 | 449769.21 | 2014-02-28 | 2017-11-07
SATNA / SATNA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1712002091/AV/22012034312935 — AGANBADHI BHAWAN NIRMAN KRYA PHUTAUNDHA | Completed | 780000 | 179986.96 | 2017-06-21 | 2020-09-12
SATNA / SATNA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1712002091/AV/22012034399305 — बाउण्डीवाल निर्माण कार्य पंचायत भवन में फुटौंधा | Physically Completed | 133891 | 135442 | 2019-01-16 | 2020-08-20
SATNA / SATNA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1712002091/AV/22012034464913 — khel maidan nirman primary school kolgawana ke pass | Closed | 0 | 0 | 2018-12-29
SATNA / SATNA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1712002091/AV/22012034464914 — shanti dham phutaundha | Closed | 0 | 0 | 2018-12-29
SATNA / SATNA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1712002091/AV/22012034539491 — पेवर व्‍लाक फर्शीकरण पंचायत भवन परिशर फुटौधा (मनरेगा अभिशण) | Completed | 148000 | 147984 | 2020-10-30 | 2021-07-03
SATNA / SATNA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1712002091/AV/22012034543578 — पेवर व्‍लाक ि‍निर्माण एवं फर्शाकरण शासकीय प्राथमिक शाला कोलगवा (बाबूपुर) मनरेगा अभिशरण | Completed | 74000 | 73626 | 2020-12-18 | 2021-12-12
SATNA / SATNA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1712002091/AV/22012034573006 — daining set nirman kary prathmik sala phutaundha me | Completed | 16093.32 | 7644 | 2021-11-13 | 2024-01-12
SATNA / SATNA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1712002091/AV/22012034610709 — नाली निर्माण कार्य कोरियान बस्‍ती से स्‍कूल मुख्‍य मार्ग तक ग्राम पंचायत फुटौधा | Completed | 42000 | 49944 | 2022-01-13 | 2022-07-30
SATNA / SATNA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1712002091/AV/22012034638276 — सामुदायिक भवन निर्माण कार्य ग्राम पंचायत फुटौधा | Completed | 200000 | 172239 | 2023-07-24 | 2026-05-26
SATNA / SATNA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1712002091/AV/22012034652209 — शान्तिधाम निर्माण ग्राम पं फुटौन्धा | New | 0 | 0 | 2024-04-01
SATNA / SATNA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1712002091/AV/22012034661514 — शांतिधाम (मुक्तिधाम) निर्माण कार्य ग्राम बाबूपुर पंचायत फुटौधा | Ongoing | 23000 | 11669.43 | 2024-10-29
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1712002091/AV/853 — Anganwadi Sewa Kendra,SATNA | Deleted | 450000 | 0 | 2014-01-26
SATNA / SATNA | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1712002091/DP/01 — व़क्षारोपण कार्य गोरईया रोड मे फुटौधा | Completed | 275500 | 160056 | 2006-08-16 | 2006-09-30
SATNA / SATNA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1712002091/DP/169 — निर्मल वाटिका लीजपिट व्रक्षारोण बार्ड क्रं 08 से 13 तक कुल 78 हितग्राही फुटौंधा 638 | Completed | 321000 | 406116 | 2010-04-22 | 2010-03-18
SATNA / SATNA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1712002091/DP/170 — निर्मलवाटिका लीजपिट एवं ब्रक्षारोपण बार्ड क्रं 01 से 07 तक 115 हितग्राही ग्राम फुटौंधा 639 | Completed | 488000 | 374345 | 2010-04-28 | 2010-04-23
SATNA / SATNA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1712002091/DP/182 — निर्मलवाटिका 80 नग हरिआदि सीमान्‍त/ लघु क़ष्क फुटौंधा 138 | Completed | 352000 | 278534 | 2010-08-03 | 2011-07-30
SATNA / SATNA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1712002091/DP/22012034542564 — Mai ki bagiya Madhyamik sala gram panchayat phutaundha | Closed | 0 | 0 | 2021-10-02
SATNA / SATNA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1712002091/DP/22012034551781 — Maai Ki Bagiya Madhyamik Shala Phutaundha | Completed | 10315.5 | 4936 | 2022-03-24 | 2022-10-03
SATNA / SATNA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1712002091/DP/22012034551784 — Maa Ki Bagiya MadhyamikShala Phutaundha | Closed | 0 | 0 | 2021-08-16
SATNA / SATNA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1712002091/DP/66 — व़क्षारोपण संधारण फुटौंधा गोरईया रोड फुटौंधा | Completed | 174000 | 103125 | 2008-09-26 | 2011-07-13
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Food Grain | Food Grain / Repair and Maintenance of Food grain Storage Building for Community | Constr of Food Grain storage | 1712002091/FG/9425884004 — गोदाम निर्माण कार्य सामुदायिक भवन के पास फुटौधा | Completed | 873000 | 872547.98 | 2014-03-05 | 2018-08-19
SATNA / SATNA | 2012-2013 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1712002091/FP/9977521838 — NALI NIRMAN KARY GEDAUA KOL KE GHAR SE ATUL SINGH KE AHARI TAK | Deleted | 0 | 0 | 2012-10-02
SATNA / SATNA | 2012-2013 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1712002091/FP/9977521839 — NALI NIRAMN TIRATH GADGARIYA KE GHAR SE VANSH BAHADUR KE GHAR KE AGE TAK | Deleted | 0 | 0 | 2012-10-02
SATNA / SATNA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/IF/1000008565 — nirmal bharat dadolli / vishalee | Deleted | 4400 | 0 | 2012-11-07
SATNA / SATNA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/IF/1000008567 — nirmal bharat ramkali / shuklal kol | Deleted | 4400 | 0 | 2012-11-07
SATNA / SATNA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/IF/1000008571 — mariyada abhiyan rajbahor/ramlakhan kol | Deleted | 4400 | 0 | 2012-11-07
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/IF/1000015430 — मेड बंधान गजाधर/रामसजीवन पाल | Completed | 25000 | 24528 | 2013-06-05 | 2014-01-21
SATNA / SATNA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/IF/1000015434 — मेड बंधान राजेश/रामबहोर दाहिया | Deleted | 25000 | 0 | 2013-03-01
SATNA / SATNA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1712002091/IF/1000016318 — मेडबंधान रामप्रसाद / बैशाखू साकेत | Deleted | 18000 | 0 | 2012-10-02
SATNA / SATNA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/IF/1000027380 — निर्मल भारत अभियान महेन्‍द्र/रामखेलावन पाल | Completed | 9000 | 3127.2 | 2013-02-01 | 2013-07-23
SATNA / SATNA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/IF/1000027383 — निर्मल भारत अभियान हंसराज/जगदीश गडारिया | Completed | 9000 | 3076 | 2013-02-07 | 2013-07-23
SATNA / SATNA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/IF/1000027384 — निर्मल भारत अभियान रामखेलावन/जागेश्‍वर कोल | Completed | 9000 | 3076 | 2013-02-13 | 2013-07-23
SATNA / SATNA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/IF/1000027386 — निर्मल भारत अभियान सुदामा/रामप्रकाश कोल | Completed | 9000 | 3084.96 | 2013-02-21 | 2013-07-23
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1712002091/IF/1000065069 — बकरीपालनसेडनिर्माणशोभा/कामतायादव | Deleted | 0 | 0 | 2013-10-02
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1712002091/IF/1000065070 — बकरीपालनसेडनिर्माणमहेन्‍द्र/रामखेलावनपाल | Completed | 50000 | 49770.25 | 2014-03-03 | 2014-10-21
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1712002091/IF/1000065071 — बकरीपालनसेडनिर्माणचुनका/संसारीपाल | Deleted | 0 | 0 | 2013-10-02
SATNA / SATNA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1712002091/IF/1000065072 — बकरी पालन सेड निर्माण चुनका/संसारी पाल | Completed | 50000 | 49999 | 2014-06-25 | 2016-07-01
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1712002091/IF/1000065784 — BAKARI PALAN SED SHOBHA/RAMGARIB YADAV | Completed | 50000 | 48968.2 | 2014-01-22 | 2016-07-01
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1712002091/IF/22012034350488 — व्रक्षारोपड़ पानी के टंकी के पास | Completed | 131000 | 26660 | 2017-06-28 | 2022-02-05
SATNA / SATNA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Gabion Anicut for Individuals / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1712002091/IF/22012034482977 — medh bandhan ganesh/ramsajeevan kori | Closed | 58073.26 | 0 | 2018-12-29
SATNA / SATNA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Gabion Anicut for Individuals / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1712002091/IF/22012034482978 — medh bandhan shyamlal vishwakarma | Completed | 31930.58 | 25540 | 2019-12-11 | 2020-06-24
SATNA / SATNA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Gabion Anicut for Individuals / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1712002091/IF/22012034483002 — Medh Bandhan rakesh/ babulal vishwakrma | Completed | 45001.92 | 38750 | 2019-12-11 | 2020-07-10
SATNA / SATNA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Gabion Anicut for Individuals / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1712002091/IF/22012034483003 — Medh Bandhan Dadoli/ramnihor kori | Closed | 0 | 0 | 2018-12-29
SATNA / SATNA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Gabion Anicut for Individuals / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1712002091/IF/22012034483005 — Medh Bandhan shobha yadav | Completed | 34731.58 | 27860 | 2019-12-11 | 2020-08-18
SATNA / SATNA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Gabion Anicut for Individuals / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1712002091/IF/22012034553791 — medh bandhan rajkumar vishwakarmas/o parmeshwardeen vishwakarma | Deleted | 0 | 0 | 2020-01-26
SATNA / SATNA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Gabion Anicut for Individuals / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1712002091/IF/22012034555952 — medh bandhan butaniya kori w/o ramvinod kori ke khet me | Closed | 0 | 0 | 2020-01-26
SATNA / SATNA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Gabion Anicut for Individuals / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1712002091/IF/22012034555976 — MEDH BANDHAN JEETENDRA SINGH S/O DADUBHAI SINGH KE KHET ME | Closed | 0 | 0 | 2020-05-13
SATNA / SATNA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1712002091/IF/22012034556343 — medh bandhan rajkumar vishwakarma s/o parmeshwardeen vishwakarma ke khet me | Completed | 17790.96 | 14060 | 2020-06-03 | 2020-08-20
SATNA / SATNA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1712002091/IF/22012034556362 — medh bandhan jeetendra singh s/o dadubhai singh | Completed | 48576.8 | 41040 | 2020-06-03 | 2020-08-15
SATNA / SATNA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1712002091/IF/22012034556364 — medh bandhan butaniya kori w/o ramvinod kori ke khet me | Completed | 22503.08 | 17860 | 2020-06-10 | 2020-11-08
SATNA / SATNA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1712002091/IF/22012034564039 — medh bandhan ramalal kori s/o budha kori | Completed | 78263.04 | 66996 | 2020-06-10 | 2020-11-23
SATNA / SATNA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1712002091/IF/22012034564042 — medh bandhan rammilan kori s/o ramjiyavan kori | Completed | 39780.85 | 33250 | 2020-06-21 | 2020-10-11
SATNA / SATNA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1712002091/IF/22012034564044 — medh bandhan ramgopal gadariya s/o saman gadariya | Completed | 83760.62 | 71820 | 2020-06-21 | 2020-10-11
SATNA / SATNA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1712002091/IF/22012034564091 — medh bandhan chunkai pal s/o mathura pal | Closed | 0 | 0 | 2020-01-26
SATNA / SATNA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1712002091/IF/22012034564092 — medh bandhan teerath pal s/o mathura paal | Closed | 0 | 0 | 2020-01-26
SATNA / SATNA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1712002091/IF/22012034564544 — medh bandhan bhaiyala kori s/o chita kori | Completed | 108891.93 | 93860 | 2020-06-21 | 2020-10-20
SATNA / SATNA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1712002091/IF/22012034568352 — medh bandhan shyamsundar vishwakarma ke khet me | Completed | 23131.37 | 20617 | 2020-06-21 | 2021-09-20
SATNA / SATNA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1712002091/IF/22012034568353 — medh bandhan ramjatan kori s/o ramjiyawan ke khet me | Completed | 33498.01 | 40380 | 2020-06-21 | 2020-08-20
SATNA / SATNA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1712002091/IF/22012034803547 — JSA med bandhan vijay singh ke keth me | Completed | 50819.37 | 43758 | 2021-06-16 | 2021-12-27
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/IF/22012035390577 — जलगंगा अभियान अंतर्गत खेत तालाब निर्माण कार्य गणेस कोरी / रामसजीवन कोरी पंचायत फुटौधा | Physically Completed | 107986.51 | 44529.94 | 2025-04-29 | 2026-06-30
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/IF/22012035514298 — जलगंगा अभियान अंतर्गत खेत तालाब निर्माण कार्य जयपाल सिंह / पदमनारायण सिंह पंचायत हटिया | Deleted | 0 | 0 | 2025-04-14
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/IF/22012035527063 — जलगंगा संवर्धन अभियान खेत तालाब निर्माण कार्य रामशरण पिता श्यामलाल विश्वकर्मा ग्राम फुटोधा ,ग्रा.पं | Completed | 53020.14 | 33888.96 | 2025-05-18 | 2026-04-03
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/IF/22012035527109 — जलगंगा संवर्धन अभियान खेत तालाब निर्माण कार्य समयलाल उर्फ़ महेश पिता रामसजीवन विश्वकर्मा ग्राम फुटोधा | Completed | 53020.14 | 27102 | 2025-05-18 | 2026-04-03
SATNA / SATNA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1712002091/IF/346 — कू निर्माण राजेश प्रसाद/ रामबहोर दाहिया 559 | Completed | 295000 | 7397.1 | 2012-01-07 | 2013-01-18
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1712002091/IF/9926722655 — BAKRI PALAN SED JAGDEESH/SANSARI PAL | Completed | 50000 | 49998.82 | 2014-03-03 | 2016-07-01
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1712002091/IF/9926727833 — PASU SED RAMASHYA/VISHVNATH KOL | Deleted | 0 | 0 | 2014-02-28
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1712002091/IF/9926727834 — PASU SED KULDEEP/LAVKESH SINGH | Deleted | 0 | 0 | 2014-02-28
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1712002091/IF/9926727835 — PASU SED RAMLAL/MOTILAL PANDEY | Deleted | 0 | 0 | 2014-02-28
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1712002091/IF/9926727836 — PASU SED MOTILAL/BHAGWANDEEN SINGH | Deleted | 0 | 0 | 2014-02-28
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1712002091/IF/9926727837 — PASU SED PUSHPENDRA/DADUBHAI SINGH | Deleted | 0 | 0 | 2014-02-28
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1712002091/IF/9926727838 — PASU SED AVADHLAL/MOHANLAL | Deleted | 0 | 0 | 2014-02-28
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1712002091/IF/9926727839 — PASU SED SUKHLAL/RAMSAJIWAN SINGH | Deleted | 0 | 0 | 2014-02-28
SATNA / SATNA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1712002091/IF/9926728289 — मेड बंधान कुलदीप/लौकेश सिंह | Completed | 42000 | 42750 | 2014-06-11 | 2014-08-28
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1712002091/IF/9926728291 — मेड बंधान सुखलाल/रामसजीवन सिंह | Deleted | 0 | 0 | 2014-02-28
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1712002091/IF/9926728292 — मेड बंधान मोतीलाल/भगवानदीन सिंह | Deleted | 0 | 0 | 2014-02-28
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1712002091/IF/9926728293 — बकरी पालन सेड ब़जलाल/रामाधार दहिया | Deleted | 0 | 0 | 2014-02-28
SATNA / SATNA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1712002091/IF/9926728294 — बकरी पालन सेड शिवनाथ/सुखलाल कोल | Deleted | 0 | 0 | 2014-02-28
SATNA / SATNA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/9993679191 — IAY inder awas shir pal / chhuni | Completed | 14310 | 20886 | 2015-10-07 | 2018-08-30
SATNA / SATNA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1712002091/IF/9993693863 — mead badhan shyam lal / ram sajeevan | Closed | 42000 | 0 | 2015-10-02
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/1094893 — Construction of IAY House -IAY REG. NO. MP3422386 | Completed | 15480 | 15480 | 2017-08-09 | 2018-02-15
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/1135133 — Construction of IAY House -IAY REG. NO. MP2722161 | Completed | 15480 | 15480 | 2017-08-30 | 2017-11-10
SATNA / SATNA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/129540 — Construction of IAY House -IAY REG. NO. MP-12-002-091-002/28 | Completed | 14310 | 13630 | 2016-12-07 | 2019-06-15
SATNA / SATNA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/129541 — Construction of IAY House -IAY REG. NO. MP-12-002-091-002/46 | Completed | 14310 | 14519 | 2016-12-07 | 2019-06-10
SATNA / SATNA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/129542 — Construction of IAY House -IAY REG. NO. MP-12-002-091-002/97 | Approved | 27000 | 0 | 2016-02-06
SATNA / SATNA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/132534 — Construction of IAY House -IAY REG. NO. MP-12-002-091-002/37 | Completed | 14310 | 13797 | 2016-12-07 | 2019-06-14
SATNA / SATNA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/132535 — Construction of IAY House -IAY REG. NO. MP-12-002-091-002/45 | Completed | 14310 | 13797 | 2016-12-07 | 2019-06-07
SATNA / SATNA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/132536 — Construction of IAY House -IAY REG. NO. MP-12-002-091-002/74 | Completed | 14310 | 13959 | 2016-12-07 | 2019-06-13
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3037873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4424688 | Completed | 17370 | 16984 | 2021-05-13 | 2021-12-26
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3037893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4428175 | Completed | 17370 | 16791 | 2021-05-13 | 2022-02-03
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3038010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4412361 | Completed | 17370 | 17298 | 2021-05-13 | 2022-06-30
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3038025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4416154 | Completed | 17370 | 16984 | 2021-05-13 | 2022-01-07
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3215453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4114584 | Completed | 17370 | 17370 | 2021-08-31 | 2022-06-30
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3237197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4412108 | Completed | 17370 | 17370 | 2021-09-06 | 2022-06-18
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3263401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4428194 | Completed | 17370 | 17187 | 2022-01-13 | 2022-06-10
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3374494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4429598 | Completed | 17370 | 17319 | 2022-03-10 | 2022-07-08
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3374511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4434072 | Completed | 17370 | 17502 | 2022-03-09 | 2022-06-10
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3406505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4434373 | Completed | 17370 | 17062 | 2022-03-15 | 2022-08-16
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3406805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4439976 | Completed | 17370 | 17370 | 2022-03-15 | 2022-06-10
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3406870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4444164 | Completed | 17370 | 17365 | 2022-03-15 | 2022-09-09
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3531969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4441507 | Completed | 17370 | 17292 | 2022-03-10 | 2022-06-17
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3533079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4526787 | Completed | 17370 | 17370 | 2022-03-10 | 2022-06-17
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3558303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4995907 | Completed | 17370 | 17370 | 2022-03-10 | 2022-06-10
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3572758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5219093 | Completed | 17370 | 17350 | 2022-02-10 | 2022-06-17
SATNA / SATNA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3572759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5219106 | Completed | 17370 | 17368 | 2023-02-01 | 2023-12-07
SATNA / SATNA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3574011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5260433 | Completed | 17370 | 17480 | 2022-04-06 | 2022-06-10
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3575748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5241631 | Completed | 17370 | 17370 | 2022-03-15 | 2022-07-16
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3630381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4371377 | Completed | 17370 | 17340 | 2022-03-15 | 2022-06-17
SATNA / SATNA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3630444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4429739 | Completed | 17370 | 17298 | 2022-03-15 | 2022-07-08
SATNA / SATNA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3642148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4908887 | Completed | 18360 | 18320 | 2024-03-17 | 2024-06-10
SATNA / SATNA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3766358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126566313 | Completed | 18360 | 17952 | 2022-08-01 | 2022-10-18
SATNA / SATNA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/3899824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126240780 | Completed | 18360 | 18156 | 2022-08-01 | 2022-10-18
SATNA / SATNA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/4368749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126632967 | Completed | 18360 | 18360 | 2022-10-01 | 2023-01-19
SATNA / SATNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/4778355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126828046 | Completed | 23490 | 21921 | 2024-11-09 | 2025-04-21
SATNA / SATNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/4778463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126849540 | Completed | 23490 | 21870 | 2024-11-09 | 2025-04-21
SATNA / SATNA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/4778473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126851447 | Completed | 23490 | 21921 | 2024-11-09 | 2025-12-12
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5426286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127135763 | Completed | 23490 | 23490 | 2025-04-19 | 2025-09-22
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5426885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126611750 | Completed | 23490 | 23490 | 2025-04-19 | 2025-07-30
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5426929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126668153 | Completed | 23490 | 23490 | 2025-06-19 | 2025-10-01
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5427201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126831586 | Completed | 23490 | 23490 | 2025-05-26 | 2025-08-29
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5429595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126865156 | Completed | 23490 | 23490 | 2025-05-26 | 2025-09-04
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5431150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126567182 | Completed | 23490 | 23229 | 2025-06-19 | 2025-09-22
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5431606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126825986 | Completed | 23490 | 23490 | 2025-05-07 | 2025-09-13
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5559841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126255984 | Completed | 23490 | 23490 | 2025-06-19 | 2025-09-13
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5559909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126885588 | Completed | 23490 | 22542 | 2025-05-26 | 2025-09-11
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5702626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126843802 | Completed | 23490 | 23490 | 2025-07-29 | 2026-05-12
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5703226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126667412 | Completed | 23490 | 23490 | 2025-07-29 | 2025-11-27
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5831152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126840128 | Completed | 23490 | 23490 | 2025-10-24 | 2026-02-23
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5831196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126826969 | Completed | 23490 | 23490 | 2025-10-06 | 2026-02-17
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5831304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126565420 | Completed | 23490 | 23490 | 2025-09-30 | 2026-01-05
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5831352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127131637 | Physically Completed | 23490 | 23490 | 2025-10-06 | 2025-12-13
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5831353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127133158 | Completed | 23490 | 23490 | 2025-10-06 | 2026-04-27
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5831387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126856333 | Physically Completed | 23490 | 23490 | 2025-10-06 | 2025-12-13
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5831423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126257003 | Completed | 23490 | 23229 | 2025-10-06 | 2026-02-25
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5831436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127123035 | Completed | 23490 | 23490 | 2025-09-30 | 2026-01-05
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5831658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126661603 | Completed | 23490 | 23490 | 2025-09-30 | 2025-11-13
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5831893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126568063 | Physically Completed | 23490 | 23490 | 2025-10-06 | 2025-12-18
SATNA / SATNA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/5832069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126669289 | Completed | 23490 | 23490 | 2025-10-06 | 2026-02-17
SATNA / SATNA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/620585 — Construction of IAY House -IAY REG. NO. MP1360075 | Completed | 17100 | 167 | 2017-03-15 | 2017-04-15
SATNA / SATNA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/620699 — Construction of IAY House -IAY REG. NO. MP1406140 | Completed | 15030 | 15475 | 2017-03-15 | 2018-04-01
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/818770 — Construction of IAY House -IAY REG. NO. MP2113452 | Completed | 15480 | 15616 | 2018-01-10 | 2019-07-20
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/818779 — Construction of IAY House -IAY REG. NO. MP2113908 | Completed | 15480 | 15480 | 2017-08-09 | 2017-12-15
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/818908 — Construction of IAY House -IAY REG. NO. MP2125864 | Completed | 15480 | 15480 | 2017-07-26 | 2018-02-20
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/819076 — Construction of IAY House -IAY REG. NO. MP2138243 | Completed | 15480 | 15480 | 2017-08-23 | 2017-10-15
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/823953 — Construction of IAY House -IAY REG. NO. MP2715781 | Completed | 15480 | 15480 | 2017-08-02 | 2017-11-10
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/827351 — Construction of IAY House -IAY REG. NO. MP3383694 | Completed | 15480 | 15480 | 2017-06-07 | 2018-02-18
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/827466 — Construction of IAY House -IAY REG. NO. MP3403258 | Completed | 15480 | 15480 | 2017-06-14 | 2017-12-28
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/827467 — Construction of IAY House -IAY REG. NO. MP3403268 | Completed | 15480 | 15480 | 2017-06-07 | 2018-02-10
SATNA / SATNA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/827572 — Construction of IAY House -IAY REG. NO. MP3419640 | Completed | 17100 | 16932 | 2022-09-08 | 2023-02-10
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/965466 — Construction of IAY House -IAY REG. NO. MP3431829 | Completed | 15480 | 15480 | 2017-08-23 | 2017-11-20
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/965467 — Construction of IAY House -IAY REG. NO. MP3431840 | Completed | 15480 | 15480 | 2017-10-25 | 2018-01-15
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/966623 — Construction of IAY House -IAY REG. NO. MP3463168 | Completed | 15480 | 17028 | 2017-09-20 | 2017-12-15
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/966757 — Construction of IAY House -IAY REG. NO. MP3466690 | Completed | 15480 | 15480 | 2017-06-07 | 2018-02-25
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/996703 — Construction of IAY House -IAY REG. NO. MP3403241 | Completed | 15480 | 15480 | 2017-12-13 | 2018-03-01
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/996745 — Construction of IAY House -IAY REG. NO. MP3420557 | Completed | 15480 | 15480 | 2017-06-07 | 2018-02-20
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/996787 — Construction of IAY House -IAY REG. NO. MP3431953 | Completed | 15480 | 15480 | 2017-10-11 | 2017-12-27
SATNA / SATNA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712002091/IF/IAY/996858 — Construction of IAY House -IAY REG. NO. MP3464261 | Completed | 15480 | 15480 | 2017-06-07 | 2018-03-30
SATNA / SATNA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1712002091/LD/119 — शांतिधाम निर्माण फुटौंधा 918 | Completed | 499000 | 68336.98 | 2010-12-23 | 2011-06-25
SATNA / SATNA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1712002091/RC/005 — जीएसबी रोड निर्माण लिलोरी रोड से बालमीक की अहरी तक 700मी फुटौंधा | Completed | 200000 | 361010 | 2007-04-03 | 2007-06-17
SATNA / SATNA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/02 — पी, सी, सी, रोड निमार्ण गोरईयारोड से फुटौधा बस्‍ती तक 365 मी, फुटौधा | Completed | 499000 | 465005 | 2007-03-02 | 2009-11-22
SATNA / SATNA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/03 — पी, सी, सी, रोड एवं नाली निमार्ण फुटौधाबस्‍ती से गोरइया तक 255 मी, फुटौधा | Completed | 390000 | 287864 | 2006-12-01 | 2006-12-31
SATNA / SATNA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1712002091/RC/.04 — जी, एस, बी, रोड निमार्ण द्वितिय गोरइया रोड से कोलगवां बस्‍ती तक फुटौधा | Completed | 492000 | 367800 | 2007-01-27 | 2006-10-31
SATNA / SATNA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/165 — पी,सी,सी,रोड निर्माण कोटियान टोला में पार्वती पाण्‍डेय के घर से चुनका गडरिया के झार के पास फुटौधा | Completed | 380000 | 429568 | 2009-04-17 | 2009-05-07
SATNA / SATNA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1712002091/RC/173 — जी,एस,बी,रोड निर्माण डफाई रोड से कोरियान वस्‍ती तक फुटौधा | Completed | 400000 | 363705 | 2009-03-22 | 2009-01-26
SATNA / SATNA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034165669 — pcc rode and nali nirmad ramlal panday ke ghar se shukhlal ke handpamp tak 588 | Completed | 173000 | 53244 | 2013-03-04 | 2013-03-16
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034169361 — पीसीसी रोड निर्माण राजू गुप्‍ता के घर के पास से पप | Completed | 119000 | 105585 | 2013-10-23 | 2014-01-21
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034169365 — पीसीसी रोड एवं नाली निर्माण गीता दाहिया केघर से ब़ | Completed | 135000 | 99588 | 2014-02-19 | 2014-06-27
SATNA / SATNA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034169368 — PCC ROD NIRMAN PUSHPENDRA SINGH KE GHAR SE TRANFARMA KE PAS | Deleted | 0 | 0 | 2012-10-02
SATNA / SATNA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034169370 — PCC ROD NIRMAN DIVAKAR SINGH KE GHAR SE SEMARIYA PAHUCH MARG | Deleted | 0 | 0 | 2012-10-02
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034169372 — PCC ROD NIRMAN PINTU SINGH KE GHAR SE GORAIYA ROD TAK | Deleted | 0 | 0 | 2013-04-14
SATNA / SATNA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1712002091/RC/22012034169373 — मिटटीमुरूमीकरण कोटवारन बस्‍ती पहुचमार्ग से स्‍वामी | Completed | 83000 | 14230.5 | 2014-07-09 | 2016-07-01
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1712002091/RC/22012034169374 — जीएसबी रोड मिटटीमुरूमी करण कोटवारन बस्‍ती पहुचमार | Completed | 80000 | 52632 | 2014-01-01 | 2016-07-01
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034206829 — पीसीसी रोड एवं नाली निर्माण ददोली कोल के घर से डफाई मेन रोड तक | Deleted | 0 | 0 | 2014-01-26
SATNA / SATNA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034206830 — पीसीसी रोड एवं नाली निर्माण रामसखी कोल के घर जीएसब | Deleted | 744000 | 0 | 2016-08-22
SATNA / SATNA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1712002091/RC/22012034291869 — khat sadak nirnal idayraj singh ke khat se hanumanmandir tak | Completed | 933000 | 43407 | 2015-12-09 | 2016-09-30
SATNA / SATNA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034304169 — Puspundra singhkaygharsayTransformer ki taraph | Closed | 0 | 0 | 2016-01-26
SATNA / SATNA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034304171 — Dharmandra singh kay pass say goraiya main road tak | Closed | 0 | 0 | 2016-01-26
SATNA / SATNA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034304194 — PCC ROAD NALI NIRMAN LALAN KOL KA HOME SA DADOLI KA HOME TAK | Deleted | 0 | 0 | 2016-01-26
SATNA / SATNA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034376389 — KHAT SADAK SACHIN SINGH KA GHAR KA PASS SA KOLGWA BASTI KE OR | Closed | 0 | 0 | 2017-10-02
SATNA / SATNA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1712002091/RC/22012034376705 — खेत सडक योजना निर्माण सचिन सिंह के घर के पास से कोलगवां बस्ती की ओर तक | Completed | 813000 | 296786 | 2018-01-17 | 2021-11-22
SATNA / SATNA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1712002091/RC/22012034443071 — Mgnrega se Mitti murmikaran | Closed | 0 | 0 | 2019-01-26
SATNA / SATNA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1712002091/RC/22012034443074 — Mgnrega se Mitti murmikaran | Closed | 0 | 0 | 2019-01-26
SATNA / SATNA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034623975 — पीसीसी रोड एवं नाली निर्माण मिलन चौराहा से सियालाल कोल के घर तक ग्राम पंचायत फुटौधा | Completed | 56000 | 55945 | 2022-12-26 | 2024-07-03
SATNA / SATNA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034643962 — बीटी डामर रोड निर्माण कार्य बाबूपुर चौकी के पास से १० नम्‍बर डफाई ग्राम पंचायत फुटौधा | Deleted | 0 | 0 | 2023-04-15
SATNA / SATNA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/22012034644774 — बीटी रोड निर्माण मेन रोड बाबूपुर चौकी के पास से डफाई बस्ती 10 नम्बर तक ग्राम पंचायत फुटौधा | Completed | 290000 | 264941.24 | 2023-08-05 | 2026-05-26
SATNA / SATNA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1712002091/RC/22012034846383 — ग्रेवल रोड घुनचिहाई मार्ग से डफाई बस्‍ती तक निर्माण कार्य ग्राम पंचायत फुटौधा | Ongoing | 333000 | 197509.5 | 2025-11-21
SATNA / SATNA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1712002091/RC/337 — जीएसबी रोड निर्माण गोरईया रोड से कोटवारन बस्‍ती फुटौंधा 914 | Completed | 345000 | 327590 | 2010-11-10 | 2012-05-30
SATNA / SATNA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712002091/RC/468 — पंचपरमेश्‍वर पीसीसी रोड एवं नाली निर्माण ट्रांसफार | Completed | 173000 | 56103.62 | 2012-05-28 | 2014-03-24
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1712002091/RS/22012034190839 — निर्मल भारत अभियान ददोली/ विशाल कोल | Deleted | 0 | 0 | 2013-10-26
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1712002091/RS/22012034190881 — निर्मल भारत अभियान राजबहोर/रामलखन कोल | Completed | 4500 | 3878 | 2014-01-22 | 2014-03-24
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1712002091/RS/22012034194216 — निर्मल भारत अभियान मेवालाल/सुखलाल कोल | Completed | 4500 | 3878 | 2014-01-15 | 2014-03-24
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1712002091/RS/22012034199543 — निर्मल भारत अभियान राजनारायण/रामलखन कोल | Completed | 4500 | 3878 | 2014-01-29 | 2014-03-24
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1712002091/RS/22012034199548 — निर्मल भारत अभियान शिवनाथ/सुखलाल कोल | Completed | 4500 | 3878 | 2014-01-29 | 2014-03-24
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1712002091/RS/22012034201386 — निर्मल भारत अभियान रामभान कोल/रामफल कोल | Completed | 4500 | 3878 | 2014-02-05 | 2014-03-24
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1712002091/RS/22012034201390 — निर्मल भारत अभियान ददोली/विशाले कोल | Completed | 4500 | 3878 | 2014-02-05 | 2014-03-24
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1712002091/RS/22012034204696 — निर्मल भारत अभियान रामस्‍वरूप कोल/रामगोपाल कोल | Completed | 4500 | 3878 | 2014-02-12 | 2014-03-24
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1712002091/RS/22012034204702 — निर्मल भारत अभियान रामपाल/परसादी गडरिया | Completed | 4500 | 3878 | 2014-02-12 | 2014-03-24
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1712002091/RS/22012034210422 — निर्मल भारत अभियान राजेश/रामफल कोल | Completed | 5300 | 3878 | 2014-03-05 | 2014-03-24
SATNA / SATNA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1712002091/RS/22012034210424 — निर्मल भारत अभियान देवीदीन कोल/मनबहोर कोल | Completed | 5300 | 3878 | 2014-02-26 | 2014-03-24
SATNA / SATNA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1712002091/RS/22012034532538 — pani ki tanki ke pass soakpit nirman | Closed | 0 | 0 | 2021-06-28
SATNA / SATNA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1712002091/RS/22012034667793 — सामुदायिक नाडेप निर्माण कार्य 05 नग ग्राम पंचायत फुटौधा | Completed | 15000 | 14912 | 2022-10-03 | 2023-07-04
SATNA / SATNA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1712002091/RS/22012034668325 — सामुदायिक सोकपिट निर्माण हैण्डपम्प के पास ग्राम पंचायत फुटौधा | Completed | 35000 | 34924 | 2022-10-15 | 2023-07-04
SATNA / SATNA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1712002091/RS/22012035130714 — नाली निर्माण कार्य बंशबहादुर पाल के घर से राजकुमार विश्‍वकर्मा के घर तक ग्राम पंचायत फुटौधा | Completed | 66000 | 42791.58 | 2024-09-24 | 2026-05-27
SATNA / SATNA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1712002091/RS/22012035130800 — सामुदायिक सोकपिट निर्माण कार्य 5 नग ग्राम पंचायत फुटौधा | Completed | 27500 | 5867.2 | 2024-10-29 | 2026-05-27
SATNA / SATNA | 2014-2015 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | Upgradation/extension of panchayat Bhawan / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1712002091/SK/9993626256 — Bharat Nirman Rajeev Gandhi Sewa Kendra,PHUTAUNDHA | Completed | 1485000 | 1033103.05 | 2014-07-09 | 2018-03-28
SATNA / SATNA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1712002091/WC/08 — सार्वजनिक कूप निर्माण फुटौंधा | Completed | 463000 | 454580 | 2008-05-13 | 2008-05-13
SATNA / SATNA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1712002091/WC/22012034318293 — TALAB MED SHUDHAR AND GAHARIKRAN | Closed | 0 | 0 | 2017-01-26
SATNA / SATNA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1712002091/WC/22012034466579 — talab gehrikaran | Closed | 0 | 0 | 2018-12-29
SATNA / SATNA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1712002091/WC/22012034568164 — हैण्डपम्प सोखता गडढा 7 नग शासकीय भवन ग्राम पंचायत फुटौधा | Completed | 98000 | 62588 | 2020-07-29 | 2021-11-22
SATNA / SATNA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1712002091/WC/22012034568171 — शासकीय भवनो मे वाटर हारवेस्टिंग 7 नग ग्राम पंचायत फुटौधा | Completed | 56000 | 59309 | 2020-07-29 | 2021-08-11
SATNA / SATNA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1712002091/WC/22012034786507 — phutaundha hat bajar me water hurwesting | Closed | 0 | 0 | 2021-06-28
SATNA / SATNA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1712002091/WC/22012034786554 — prathmik salaphutaundha me rain water hurwesting | Closed | 0 | 0 | 2021-06-28
SATNA / SATNA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1712002091/WC/22012034786575 — 10 number dafai ke hundpump me riharge pit | Closed | 0 | 0 | 2021-06-28
SATNA / SATNA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1712002091/WC/22012034786579 — rambai kol ke ghar ke pass hundpump me richarge pit | Closed | 0 | 0 | 2021-06-28
SATNA / SATNA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1712002091/WC/22012034836474 — HDPE TANKगेदउआ कोल के घर के पास ग्राम पंचायत फुटौधा (मनरेगा अभिशरण) | Completed | 10000 | 9990 | 2021-11-16 | 2022-07-30
SATNA / SATNA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1712002091/WC/22012034876940 — phutaundha talab me medh sudhar avam gridodhwar | Closed | 0 | 0 | 2021-11-17
SATNA / SATNA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1712002091/WC/22012034927694 — phutaundha talab me medh sudhar avam gridodhwar | Closed | 0 | 0 | 2022-01-26
SATNA / SATNA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1712002091/WC/22012034927695 — phutaundha talab me medh sudhar avam gridodhwar | Closed | 0 | 0 | 2022-01-26
SATNA / SATNA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1712002091/WC/22012035306606 — जलगंगा अभियान अंतर्गत सामुदायिक ओपन डग वेल मे रिचार्ज पिट निर्माण मा.शा.भवन के पास ग्राम पं फुटौन्धा | Completed | 14224 | 12014.92 | 2025-05-16 | 2026-06-02
SATNA / SATNA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1712002091/WC/22012035307280 — जलगंगा अभियान अंतर्गत सामुदायिक ओपन डग वेल मे रिचार्ज कार्य शोभा दहायत के घर के पास ग्राम पं फुटौन्ध | Completed | 14224 | 7803.96 | 2025-05-18 | 2026-06-02
SATNA / SATNA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1712002091/WC/9993632851 — TALAB PHAUTAUDHA GAD NIKASI | Deleted | 0 | 0 | 2012-10-02
SATNA / SATNA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1712002091/WH/06 — जलसंग्रहण एवं क्षमता फुटौंधा तालाब फुटौंधा | Completed | 142000 | 242964 | 2007-05-11 | 2007-04-07
SATNA / SATNA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1712002091/WH/07 — जलसंग्रहण क्षमता लहुखा तालाब गहरीकरण फुटौंधा | Completed | 188000 | 426524 | 2007-12-21 | 2007-03-13
SATNA / SATNA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1712002091/WH/19959570 — तालाब निर्माण फुटौधा | Completed | 96000 | 80163 | 2017-05-17 | 2020-06-28
SATNA / SATNA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1712002091/WH/19962329 — KOLGAWA TALAB NIRMAN PHUTHUDHA | Closed | 197000 | 0 | 2017-05-05
SATNA / SATNA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1712002091/WH/22012034921708 — फुटौंधा तालाब मेंड़ सुधार कार्य | Closed | 0 | 0 | 2021-08-16