## Work List
Exported on: 2026-09-30 12:25:19
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SATNA / MAIHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1712008002/AV/22012034625262 — खेल मैदान जूरा | Ongoing | 223375.39 | 0 | 2023-12-30
SATNA / MAIHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1712008002/AV/22012034639146 — आंगनवाडी भवन निर्माण हरिजन बस्ती जूरा | Ongoing | 80000 | 0 | 2024-04-29
SATNA / MAIHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1712008002/IF/22012035047926 — व्यक्तिगत शोक पिट निर्माण कार्य जूरा | Ongoing | 101063.72 | 0 | 2023-02-07
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1712008002/IF/22012035605122 — Ek Bagiya Maa Ke Naam Asha Jaiswal MP12008002002 785 | Ongoing | 261747.23 | 0 | 2025-09-03
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1712008002/IF/22012035610987 — Ek Bagiya Ma Ke Naam Mithlesh Gupta MP12008002002 896 | Ongoing | 289598.86 | 0 | 2025-09-07
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1712008002/IF/22012035615005 — ek bagiya ma ke nam rasna sharma mp17120080002002732 samooh id604657 | Ongoing | 141600.05 | 0 | 2025-09-10
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1712008002/IF/22012035648234 — ek bagiya ma ke nam subhadra viswakarma mp12/008/002/002/897 shg 2910964 | Ongoing | 168945.89 | 0 | 2026-01-15
SATNA / MAIHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/2750585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4252990 | Ongoing | 27000 | 0 | 2021-03-19
SATNA / MAIHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/3237162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4258387 | Completed | 23490 | 0 | 2023-02-18 | 2026-08-24
SATNA / MAIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/4869408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137326082 | Physically Completed | 23490 | 0 | 2025-02-18 | 2026-07-19
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5208359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127342477 | Completed | 23490 | 0 | 2025-04-20 | 2026-08-24
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5209816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113969396 | Ongoing | 27000 | 0 | 2025-04-20
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5230403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127344452 | Completed | 23490 | 0 | 2025-04-20 | 2026-08-24
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5235547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124770285 | Ongoing | 27000 | 0 | 2025-04-20
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5524720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127345244 | Completed | 23490 | 0 | 2025-06-06 | 2026-08-24
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5817406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113962486 | Ongoing | 27000 | 0 | 2025-10-14
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5817727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113947066 | Physically Completed | 23490 | 0 | 2025-10-14 | 2026-07-19
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5817879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137012563 | Physically Completed | 23490 | 0 | 2025-10-05 | 2026-08-16
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5818329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114083257 | Completed | 23490 | 0 | 2025-10-05 | 2026-08-24
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5818411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113942297 | Completed | 23490 | 0 | 2025-10-05 | 2026-08-24
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5818440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113964927 | Completed | 23490 | 0 | 2025-10-05 | 2026-08-24
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5818443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124728724 | Completed | 23490 | 0 | 2025-10-05 | 2026-08-24
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5818564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125103001 | Completed | 23490 | 0 | 2025-10-05 | 2026-08-24
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5818566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124444638 | Physically Completed | 23490 | 0 | 2025-10-05 | 2026-07-26
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5818599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113941876 | Physically Completed | 23490 | 0 | 2025-10-14 | 2026-07-19
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5818741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137000886 | Completed | 23490 | 0 | 2025-10-05 | 2026-08-24
SATNA / MAIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1712008002/IF/IAY/5818742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137002710 | Completed | 23490 | 0 | 2025-10-05 | 2026-08-24
SATNA / MAIHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1712008002/LD/22012034942774 — वृक्षारोपण कार्य मा.शाला परिसर झाली | Ongoing | 58988.78 | 261 | 2024-07-26
SATNA / MAIHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1712008002/RC/22012034849275 — PCC road Jahura prajapati ke ghar se manoj sharma ki or | New | 0 | 0 | 2025-04-14
SATNA / MAIHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1712008002/RS/22012035128875 — नाली निर्माण कार्य झाली वस्ती रामकुमार के घर से पोखरा की ओर दक्षिण साईड | Approved | 100000 | 0 | 2024-06-08