## Work List
Exported on: 2026-09-09 22:21:47
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: GUHIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
REWA / SIRMOUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1713003068/AV/22012034662232 — Shantidham NIrman Bagdha Pidihan Shmshan Bhumi Par | Approved | 31000 | 0 | 2024-08-16
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1713003068/FP/22012034636623 — Shes Nali Nirman Jaylal Kol Ke Ghar Se Shivnath Kol Ke Ghar Tak | Ongoing | 35000 | 0 | 2023-10-13
REWA / SIRMOUR | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1713003068/FP/22012034641693 — Nali Nirman Mandir se Pushpendra Tiwari ke ghar Taraf | Ongoing | 62000 | 0 | 2025-01-12
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713003068/IF/22012034827401 — Cattel shed nirman sheela bai tiwari | Ongoing | 64323.65 | 0 | 2022-02-03
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713003068/IF/22012034881050 — Plantation work vedprakash garg ke khet me | Ongoing | 108843.85 | 0 | 2022-01-14
REWA / SIRMOUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713003068/IF/22012035208285 — Khet Talab Nirman Karya Gram Guhiya | New | 0 | 0 | 2024-01-27
REWA / SIRMOUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713003068/IF/22012035208293 — Kapildhara Koop Nirman | New | 0 | 0 | 2024-01-27
REWA / SIRMOUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713003068/IF/22012035209628 — Kapildhara koop nirman birendra Shukla | Ongoing | 296962.26 | 0 | 2024-03-09
REWA / SIRMOUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713003068/IF/22012035209633 — Khettalab Nirman Rajpal Shukla | Ongoing | 385261.22 | 0 | 2024-03-13
REWA / SIRMOUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713003068/IF/22012035229511 — Kapildhara koop Nirman Sanjeev Shukla | Ongoing | 310544.79 | 0 | 2024-06-17
REWA / SIRMOUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713003068/IF/22012035230296 — Kapildhara koop Nirman Sanjeev Shukla | New | 0 | 0 | 2024-06-08
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713003068/IF/22012035504990 — Khettalab Nirman Birendra Shukla | Approved | 55865.38 | 0 | 2025-04-16
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713003068/IF/22012035546720 — Khettalab Nirman Ramjiyavan Tiwari | Approved | 55865.38 | 0 | 2025-04-14
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713003068/IF/22012035546735 — Khettalab Nirman Arun kumar Mishra | Approved | 55865.38 | 0 | 2025-04-14
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713003068/IF/22012035597951 — Ek Bagiya Maa ke naam Janaksuta Job Card 847 | Ongoing | 269386.03 | 0 | 2025-08-28
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713003068/IF/22012035597961 — Ek Bagiya Maa Ke Naam Reetu Tiwari Job Card 9313 | Ongoing | 266577.25 | 0 | 2025-10-06
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713003068/IF/22012035597967 — Ek Bagiya Maa Ke Naam Mahima Dwivedi Job Card 872 | Ongoing | 266577.25 | 0 | 2025-08-28
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713003068/IF/22012035601406 — Ek Bagiya Ma Ke Name Munni Tiwari | Ongoing | 266577.25 | 0 | 2025-08-28
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713003068/IF/22012035628408 — Ek Bagiya Ma Ke Name Ramkishori Tiwari | Ongoing | 198880.27 | 0 | 2025-10-08
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713003068/IF/22012035628409 — Ek Bagiya Ma Ke Name Seema Dwivedi | Ongoing | 199558.3 | 0 | 2025-10-08
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713003068/IF/22012035628410 — Ek Bagiya Ma Ke Name BUtan Devi Shukla | Ongoing | 198024.99 | 0 | 2025-10-08
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/4399615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118337232 | Approved | 27000 | 0 | 2022-06-04
REWA / SIRMOUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/4567962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116487480 | Approved | 27000 | 0 | 2024-09-15
REWA / SIRMOUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/4574368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117436965 | Approved | 27000 | 0 | 2024-09-15
REWA / SIRMOUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/4597110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122462072 | Approved | 27000 | 0 | 2024-09-15
REWA / SIRMOUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/4620893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126777283 | Approved | 27000 | 0 | 2024-09-15
REWA / SIRMOUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/4703698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120355203 | Approved | 27000 | 0 | 2024-09-15
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5174561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124184680 | Ongoing | 27000 | 0 | 2025-04-08
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5780167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126746845 | Ongoing | 27000 | 0 | 2025-09-05
REWA / SIRMOUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5780312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126758228 | Ongoing | 27000 | 16800 | 2026-08-01
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5780662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126128790 | Ongoing | 27000 | 4200 | 2025-09-04
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5780740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126775957 | Ongoing | 27000 | 0 | 2025-09-05
REWA / SIRMOUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5780824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120355735 | Approved | 27000 | 0 | 2025-02-09
REWA / SIRMOUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5781235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124184069 | Approved | 27000 | 0 | 2025-03-03
REWA / SIRMOUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5781819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123958061 | Approved | 27000 | 0 | 2025-03-03
REWA / SIRMOUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5782025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117338137 | Ongoing | 27000 | 8400 | 2026-08-16
REWA / SIRMOUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5782027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117339011 | Approved | 27000 | 0 | 2025-03-01
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5782157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123955712 | Ongoing | 27000 | 4200 | 2025-09-05
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5782365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116231349 | Ongoing | 27000 | 0 | 2025-09-05
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5782368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116361845 | Ongoing | 27000 | 0 | 2025-09-05
REWA / SIRMOUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5782502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117435810 | Approved | 27000 | 0 | 2025-02-19
REWA / SIRMOUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5886958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120357723 | Approved | 27000 | 0 | 2025-02-27
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5894299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119518066 | Approved | 27000 | 0 | 2026-01-22
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5894400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149504410 | Approved | 27000 | 0 | 2026-02-03
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5895175 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148586953 | Approved | 27000 | 0 | 2026-02-03
REWA / SIRMOUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5895221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124441877 | Ongoing | 27000 | 8400 | 2026-08-05
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5895364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117871994 | Approved | 27000 | 0 | 2026-02-03
REWA / SIRMOUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5896959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120348112 | Ongoing | 27000 | 4200 | 2026-05-05
REWA / SIRMOUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5896971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122459420 | Ongoing | 27000 | 4200 | 2026-05-05
REWA / SIRMOUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/5897472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124790524 | Ongoing | 27000 | 8400 | 2026-08-01
REWA / SIRMOUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/6037138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122459953 | Ongoing | 27000 | 4200 | 2026-05-05
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/6037708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124178766 | Approved | 27000 | 0 | 2026-02-23
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003068/IF/IAY/6230886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119518170 | Approved | 27000 | 0 | 2026-02-03
REWA / SIRMOUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003068/RC/22012034449269 — PCC sah nali nirman Adiwasi basti Ward no 16 | Ongoing | 84000 | 0 | 2019-03-05
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003068/RC/22012034678946 — pcc road nirman | New | 0 | 0 | 2023-04-02
REWA / SIRMOUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713003068/RC/22012034835327 — main road se yadav ke ghar tak 400m Gravel sadak nirman karya GP guhiya JP sirmour | Ongoing | 300000 | 0 | 2025-05-06