## Work List
Exported on: 2026-09-07 14:27:21
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: BADRAON GAUTAMAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
REWA / SIRMOUR | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1713003080/AV/22012034504587 — Chabutara Nirman Devi mandir ke pass | Completed | 18000 | 17724 | 2020-03-03 | 2020-12-23
REWA / SIRMOUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713003080/AV/22012034568444 — Puliya nirman Main road se Panchayat bhawan ke pass | Completed | 21000 | 16212 | 2021-07-02 | 2024-02-16
REWA / SIRMOUR | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1713003080/AV/22012034568794 — uparjan kendra me chabutara nirman kary badarav gautman | Completed | 48000 | 53268 | 2021-07-14 | 2023-12-24
REWA / SIRMOUR | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1713003080/AV/22012034572213 — Seggregation shed nirman badarav gautaman | Closed | 54000 | 0 | 2021-04-15
REWA / SIRMOUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1713003080/AV/22012034604722 — Naali Nirman Balendra Dwivedi ke ghar se main road par bani puliya tak | Ongoing | 61000 | 10422 | 2021-11-23
REWA / SIRMOUR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713003080/AV/22012034627598 — RCC Naali Nirman Raja Gautam ke ghar se Nahar tak | Completed | 133000 | 114852 | 2023-01-06 | 2025-05-19
REWA / SIRMOUR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713003080/AV/22012034627599 — RCC Nali Nirman EGS Shala Se nahar tak | Closed | 0 | 0 | 2022-04-02
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1713003080/AV/22012034632053 — Naali cover ka karya Gaya Gautam ke ghar se Nahar tak | Ongoing | 30000 | 29172 | 2023-05-20
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713003080/AV/22012034632054 — Naali Nirman Karya EGS Shala se Nahar tak | Completed | 86000 | 85330 | 2023-06-12 | 2024-01-23
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713003080/AV/22012034635502 — Naali Nirman Karya EGS Shala Se Nahar Tak | Closed | 86000 | 0 | 2023-04-02
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1713003080/AV/22012034641212 — Boundry wall Nirman High School Badraon Gautman | Completed | 95000 | 92378 | 2023-10-04 | 2023-12-30
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713003080/AV/22012034642230 — Naali Nirman Karya Ramsujan Gautam ke ghar se Vikash Gautam ke ghar tak | Completed | 22000 | 19448 | 2023-08-30 | 2024-02-25
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1713003080/AV/22012034649455 — Paver Block High School Badraon Gautman | Ongoing | 169000 | 884 | 2024-03-10
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1713003080/AV/22012034649460 — Paver Block EGS Karya Vidyalay Badraon Gautman | Ongoing | 50000 | 1105 | 2024-03-10
REWA / SIRMOUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1713003080/AV/22012034652723 — Naali Nirman | Approved | 0 | 0 | 2024-04-02
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1713003080/AV/22012034654068 — RCC Jal Nikasi Shitala Tripathi Ke ghar ke pass se Gyanedra tripathi ke ghar ke pass | Completed | 36000 | 33637 | 2024-03-10 | 2026-05-22
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1713003080/AV/22012034654069 — Rcc Drain Cover Kallu kol ke ghar se nahar tak | Ongoing | 15000 | 14820 | 2024-03-10
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713003080/AV/22012034656086 — Jal Nikasi Drain Ashok Dwivedi ke ghar se CFT Bhawan tak | Completed | 71000 | 68080 | 2024-03-16 | 2025-05-19
REWA / SIRMOUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1713003080/DP/22012034597212 — VASUDHA VANDAN AMRIT VATIKA HIGH SCHOOL BADRAON GAUTMAN | Closed | 0 | 0 | 2023-04-14
REWA / SIRMOUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1713003080/DP/22012034598623 — DEVI MANDIR PARISAR | Closed | 0 | 0 | 2023-04-14
REWA / SIRMOUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713003080/IF/2 — कपिलधारा सिंचाई कूप निर्माण बदरांव गौतमान राधवेन्‍द्र गौतम | Completed | 254000 | 115862 | 2009-03-23 | 2012-07-12
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713003080/IF/22012034315725 — Kapildhara Koop Khet Talab Sahit Nirman Karya | Closed | 0 | 0 | 2017-04-01
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1713003080/IF/22012034354247 — Poudharopan karya School ke Pass | Suspended | 335000 | 12000 | 2017-08-22
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1713003080/IF/22012034372262 — PAUDHA ROPAN CFT KEAMANK 02 | Deleted | 335000 | 0 | 2017-08-19
REWA / SIRMOUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1713003080/IF/22012034533358 — Medh Bandhan Indramani Tirapthi/ Ambika Prasad Tripathi | Closed | 48327.47 | 0 | 2020-06-16
REWA / SIRMOUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713003080/IF/22012034533360 — Kapildhara koop Nirman Laxmikant Dwivedi S/o Shiyawar Prasad Dwivedi | Closed | 251081.27 | 0 | 2019-04-02
REWA / SIRMOUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1713003080/IF/22012034615119 — Medh Bnadhan Balendra Prasad | Closed | 0 | 0 | 2020-04-02
REWA / SIRMOUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1713003080/IF/22012034616193 — Khet Talab Nirman Indira raman Tripathi | Closed | 0 | 0 | 2020-04-02
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713003080/IF/22012034827312 — SHG Pashu sed nirman kary aneeta gautam ke bhumi par | Ongoing | 64323.65 | 26287 | 2021-10-17
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713003080/IF/22012034827313 — SHG Pashu sed nirman kary Priyanka gautam ke bhumi par | Ongoing | 64323.65 | 57289.53 | 2021-10-17
REWA / SIRMOUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1713003080/IF/22012035533163 — Khet talab Nirman Sarvesh kumar kushwaha | New | 0 | 0 | 2025-04-14
REWA / SIRMOUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1713003080/IF/22012035533167 — Khet talab Nirman Sarvesh kumar kushwaha | Approved | 0 | 0 | 2025-04-14
REWA / SIRMOUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713003080/IF/22012035545231 — Khet talab Munni devi Kushwaha | Closed | 55865.38 | 261 | 2025-05-26
REWA / SIRMOUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1713003080/IF/9993748558 — IAY Construction Khelawan Kol/Samaji Kol | Closed | 0 | 0 | 2015-10-02
REWA / SIRMOUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/9993748559 — IAY Construction Khelawan Kol/ Samji Kol | Completed | 14310 | 13128 | 2016-06-20 | 2020-11-06
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1104641 — Construction of IAY House -IAY REG. NO. MP1320509 | Completed | 15480 | 15444 | 2018-01-06 | 2019-07-17
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1131227 — Construction of IAY House -IAY REG. NO. MP2419142 | Completed | 15480 | 15436 | 2018-01-06 | 2018-08-16
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1138410 — Construction of IAY House -IAY REG. NO. MP2996597 | Completed | 15480 | 15436 | 2018-01-06 | 2018-08-16
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1139639 — Construction of IAY House -IAY REG. NO. MP3118074 | Deleted | 15480 | 0 | 2017-05-17
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1140310 — Construction of IAY House -IAY REG. NO. MP3181482 | Completed | 15480 | 15444 | 2018-01-06 | 2019-07-17
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1140493 — Construction of IAY House -IAY REG. NO. MP3196637 | Completed | 15480 | 15436 | 2018-01-06 | 2018-08-16
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1140732 — Construction of IAY House -IAY REG. NO. MP3217809 | Completed | 17100 | 13522 | 2018-01-06 | 2020-10-18
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1140842 — Construction of IAY House -IAY REG. NO. MP3226334 | Completed | 15480 | 15561.8 | 2018-01-06 | 2019-07-17
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1140990 — Construction of IAY House -IAY REG. NO. MP3239888 | Completed | 15480 | 15381.8 | 2018-01-06 | 2018-08-16
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1141007 — Construction of IAY House -IAY REG. NO. MP3240975 | Completed | 15480 | 15610 | 2018-01-06 | 2018-07-25
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1141438 — Construction of IAY House -IAY REG. NO. MP3286326 | Deleted | 15480 | 0 | 2017-05-17
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1163584 — Construction of IAY House -IAY REG. NO. MP3925701 | Completed | 15480 | 16201.6 | 2018-01-06 | 2018-08-16
REWA / SIRMOUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1225359 — Construction of IAY House -IAY REG. NO. MP1237354 | Deleted | 15480 | 0 | 2017-02-22
REWA / SIRMOUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1225618 — Construction of IAY House -IAY REG. NO. MP4117081 | Deleted | 15480 | 0 | 2017-02-12
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1225978 — Construction of IAY House -IAY REG. NO. MP1463956 | Deleted | 15480 | 0 | 2017-05-11
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1227813 — Construction of IAY House -IAY REG. NO. MP3286326 | Deleted | 15480 | 0 | 2017-05-17
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1228506 — Construction of IAY House -IAY REG. NO. MP3118074 | Deleted | 15480 | 0 | 2017-05-17
REWA / SIRMOUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/133016 — Construction of IAY House -IAY REG. NO. MP-13-003-080-001/7 | Approved | 27000 | 0 | 2016-02-12
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1661810 — Construction of IAY House -IAY REG. NO. MP1420468 | Completed | 17100 | 15377.6 | 2018-07-25 | 2020-10-24
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1662463 — Construction of IAY House -IAY REG. NO. MP1802399 | Completed | 17100 | 15096 | 2018-07-25 | 2020-12-23
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1663496 — Construction of IAY House -IAY REG. NO. MP2337323 | Completed | 15660 | 15853.4 | 2018-07-25 | 2019-07-17
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1663565 — Construction of IAY House -IAY REG. NO. MP2379664 | Completed | 15660 | 15834 | 2018-10-26 | 2019-07-17
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1665404 — Construction of IAY House -IAY REG. NO. MP3224072 | Completed | 15660 | 15953.2 | 2018-07-25 | 2019-07-10
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1714992 — Construction of IAY House -IAY REG. NO. MP3233951 | Completed | 17100 | 15091.2 | 2018-07-25 | 2020-10-24
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1900164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4117081 | Closed | 17100 | 0 | 2018-07-13
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1900194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1237354 | Completed | 17100 | 15894 | 2018-09-10 | 2020-10-23
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1900202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3286326 | Completed | 17100 | 14164 | 2018-07-26 | 2020-10-23
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1900204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3118074 | Completed | 17100 | 15532 | 2018-07-26 | 2020-10-24
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/1900219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1463956 | Completed | 17100 | 16126 | 2018-11-03 | 2020-12-23
REWA / SIRMOUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/2062739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3673356 | Completed | 17100 | 15639 | 2019-11-25 | 2023-05-03
REWA / SIRMOUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/2414486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4104124 | Completed | 17100 | 13402 | 2020-05-17 | 2023-12-26
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/2417714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4419560 | Completed | 17100 | 16468 | 2021-08-18 | 2023-08-16
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/2764336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4373426 | Physically Completed | 17100 | 14543 | 2021-05-17 | 2024-11-21
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/2927666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4166349 | Completed | 17100 | 11387 | 2021-06-23 | 2023-12-26
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/2930283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4388409 | Physically Completed | 17100 | 12352 | 2021-06-23 | 2024-11-21
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/2985658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4180490 | Physically Completed | 17100 | 12159 | 2021-07-16 | 2024-11-21
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/2986043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4373732 | Physically Completed | 17100 | 13703 | 2021-05-17 | 2024-11-21
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/2986982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4413035 | Physically Completed | 17100 | 11773 | 2021-05-24 | 2024-11-21
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3219371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4145278 | Completed | 17370 | 17092 | 2021-09-06 | 2024-02-25
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3301530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4373345 | Completed | 17370 | 16216 | 2022-02-13 | 2023-12-26
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3372713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4149935 | Ongoing | 27000 | 13260 | 2022-05-30
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3374241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4382055 | Approved | 27000 | 0 | 2021-11-17
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3374270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4388464 | Closed | 17370 | 0 | 2021-11-24
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3374300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4392196 | Closed | 17370 | 0 | 2021-11-24
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3374358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4404676 | Completed | 17370 | 17196 | 2022-05-30 | 2024-02-25
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3378647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5017499 | Approved | 27000 | 0 | 2021-11-17
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3378737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5030675 | Physically Completed | 17370 | 7802 | 2022-02-13 | 2024-11-27
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3397085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4149871 | Completed | 17370 | 17334 | 2022-04-22 | 2023-08-16
REWA / SIRMOUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3416460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4764383 | Physically Completed | 17370 | 14807 | 2023-08-14 | 2024-11-27
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3417624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4789823 | Closed | 17370 | 0 | 2021-12-03
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3418677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4807260 | Completed | 17370 | 17169 | 2022-04-22 | 2023-08-01
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3603723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4213928 | Physically Completed | 17370 | 10200 | 2022-04-22 | 2024-11-21
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3603757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4358982 | Completed | 17370 | 15554 | 2022-04-22 | 2023-08-01
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3604381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4386522 | Completed | 17370 | 16931 | 2022-04-22 | 2023-08-01
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3604457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4176050 | Completed | 17370 | 15450 | 2022-01-28 | 2023-08-01
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3604523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4333178 | Completed | 17370 | 17300 | 2022-04-22 | 2023-12-05
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3604858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4154713 | Completed | 17370 | 16942 | 2022-02-13 | 2023-08-16
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3605236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4163372 | Physically Completed | 17370 | 17151 | 2022-02-13 | 2024-11-26
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3605745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4843987 | Physically Completed | 17370 | 10454 | 2022-02-13 | 2024-11-21
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3605918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4776301 | Completed | 17370 | 17180 | 2022-02-13 | 2023-08-16
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3605925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4777458 | Completed | 17370 | 16524 | 2022-05-30 | 2023-08-01
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3605928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4777840 | Completed | 17370 | 16370 | 2022-05-18 | 2023-08-01
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3606150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4768993 | Completed | 17370 | 17296 | 2022-02-13 | 2023-12-05
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3606432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5037397 | Completed | 17370 | 16574 | 2022-05-30 | 2023-08-01
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3606523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4805545 | Completed | 17370 | 17246 | 2022-04-22 | 2023-12-05
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3606528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4806159 | Completed | 17370 | 16896 | 2022-02-13 | 2024-02-25
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3606532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4806381 | Completed | 17370 | 16828 | 2022-02-13 | 2023-08-01
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3606906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4775385 | Completed | 17370 | 15808 | 2022-02-13 | 2023-08-01
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3607095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4789677 | Physically Completed | 17370 | 10758 | 2022-02-13 | 2024-11-21
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3607297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4804950 | Completed | 17370 | 17236 | 2022-02-13 | 2022-11-21
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3607636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4764534 | Completed | 17370 | 17332 | 2022-04-22 | 2023-08-16
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3607638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4764778 | Completed | 17370 | 16862 | 2022-02-13 | 2023-08-01
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3607831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4791811 | Completed | 17370 | 17059 | 2022-04-22 | 2023-08-01
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3607843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4793917 | Completed | 17370 | 16982 | 2022-04-22 | 2023-08-01
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3608119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5292589 | Completed | 17370 | 16624 | 2022-02-13 | 2023-12-11
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3609116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5362105 | Completed | 17370 | 17334 | 2022-11-11 | 2023-08-16
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3609268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5303484 | Physically Completed | 17370 | 16064 | 2022-02-13 | 2024-11-21
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3609277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5304183 | Completed | 17370 | 17202 | 2022-11-11 | 2023-08-01
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3609486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5301491 | Completed | 17370 | 16676 | 2022-05-30 | 2023-12-26
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3609647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5276119 | Physically Completed | 17370 | 15826 | 2022-02-13 | 2024-11-27
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3609703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5390210 | Completed | 17370 | 16942 | 2022-02-13 | 2023-08-16
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3609891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5392081 | Completed | 17370 | 16692 | 2022-02-13 | 2023-12-11
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3609902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5393628 | Completed | 17370 | 16778 | 2022-03-11 | 2023-08-01
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3610284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5431950 | Completed | 17370 | 16642 | 2022-11-11 | 2024-02-25
REWA / SIRMOUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3610811 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5401003 | Completed | 17370 | 16454 | 2022-02-13 | 2023-08-01
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/3650860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5301466 | Physically Completed | 18360 | 17136 | 2022-05-30 | 2024-11-21
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/4366365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151736144 | Approved | 27000 | 0 | 2022-07-18
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/4371369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145493251 | Closed | 18360 | 0 | 2022-09-29
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/4371487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130222137 | Closed | 18360 | 0 | 2022-09-29
REWA / SIRMOUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/4386333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127356406 | Closed | 18360 | 0 | 2022-11-24
REWA / SIRMOUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/4626170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126901869 | Ongoing | 27000 | 0 | 2024-09-15
REWA / SIRMOUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/651947 — Construction of IAY House -IAY REG. NO. MP4117081 | Deleted | 15030 | 0 | 2017-02-12
REWA / SIRMOUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/652285 — Construction of IAY House -IAY REG. NO. MP1237354 | Deleted | 15030 | 0 | 2017-02-22
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/833459 — Construction of IAY House -IAY REG. NO. MP1240644 | Completed | 15480 | 15608 | 2017-05-22 | 2019-07-17
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/845758 — Construction of IAY House -IAY REG. NO. MP1434291 | Approved | 27000 | 0 | 2017-04-01
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/847950 — Construction of IAY House -IAY REG. NO. MP1463956 | Deleted | 15480 | 0 | 2017-04-03
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/870052 — Construction of IAY House -IAY REG. NO. MP1735921 | Completed | 17100 | 15832.6 | 2018-07-25 | 2020-12-23
REWA / SIRMOUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/87817 — Construction of IAY House -IAY REG. NO. MP-13-003-080-001/11 | Approved | 27000 | 0 | 2015-10-14
REWA / SIRMOUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/87819 — Construction of IAY House -IAY REG. NO. MP-13-003-080-001/27 | Approved | 27000 | 0 | 2015-10-14
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/917238 — Construction of IAY House -IAY REG. NO. MP2379623 | Completed | 15480 | 15495.4 | 2018-10-26 | 2019-07-17
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/917793 — Construction of IAY House -IAY REG. NO. MP2387829 | Completed | 15480 | 15610 | 2018-01-06 | 2018-07-25
REWA / SIRMOUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/918955 — Construction of IAY House -IAY REG. NO. MP2405583 | Completed | 15480 | 16056.8 | 2018-07-25 | 2019-07-17
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/956278 — Construction of IAY House -IAY REG. NO. MP3202884 | Completed | 15480 | 15432 | 2017-05-22 | 2018-08-16
REWA / SIRMOUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713003080/IF/IAY/958564 — Construction of IAY House -IAY REG. NO. MP3251814 | Completed | 17100 | 15678.8 | 2017-05-22 | 2020-10-23
REWA / SIRMOUR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1713003080/LD/165 — खेल मैदान शा0 हाई स्‍कूल बदराव गौतमान T S 165 | Completed | 205000 | 79630 | 2012-06-01 | 2015-02-26
REWA / SIRMOUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034172694 — पीसीसी सह नाली निर्माण मुख्‍यमार्ग से रामसजीवन कुश | Completed | 115000 | 110532 | 2013-06-24 | 2014-07-08
REWA / SIRMOUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034188537 — पीसीसी सह नाली निर्माण सुशील गौतम की दुकान से रामा | Completed | 128000 | 97508 | 2013-10-04 | 2016-10-03
REWA / SIRMOUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034262948 — PCC Road Nirman 170 Mtr | Deleted | 0 | 0 | 2015-01-26
REWA / SIRMOUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034289610 — PCC Road Ramkishor Kol Ke Ghar se Chandrakant Goutam Ke ghar ki Taraf | Deleted | 128000 | 0 | 2013-10-02
REWA / SIRMOUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034289614 — PCC Road Vishal Prajapati Ke Ghar Indramani Tripathi Ke ghar Ki Taraf | Completed | 128000 | 56922 | 2015-11-28 | 2017-12-12
REWA / SIRMOUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034319571 — NALI NIRMAD CFT BHAVAN KE SAMNE BADRAV GAUTAMAN | Completed | 244000 | 43186 | 2017-01-09 | 2017-12-12
REWA / SIRMOUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034372817 — PCC Nirman | Closed | 0 | 0 | 2017-04-02
REWA / SIRMOUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034440093 — PCC Road nirman 150 Mtrs | Closed | 0 | 0 | 2019-05-02
REWA / SIRMOUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034514016 — PCC Road Nirman | Closed | 0 | 0 | 2019-11-14
REWA / SIRMOUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034541744 — PCC Road Shatrughan Dubey ke Ghar se bandha tak | Ongoing | 102000 | 76380 | 2020-12-29
REWA / SIRMOUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034541747 — PCC Road CFT Bhawan ke pass se Vishram Kushwaha Ke ghar tak | Completed | 95000 | 55290 | 2020-10-18 | 2024-02-25
REWA / SIRMOUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034558497 — पी सी सी सड़क निर्माण मेन रोड से लालमणि प्रजापति के घर तक | Ongoing | 20000 | 17290 | 2021-02-20
REWA / SIRMOUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034558499 — पी सी सी सड़क निर्माण मेन रोड से रामभजन कोल के घर तक | Ongoing | 29000 | 25502 | 2021-03-03
REWA / SIRMOUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034558500 — पी सी सी सह नाली निर्माण सुदामा दुबे के घर से विन्धेश्वरी शुक्ल के घर तक | Ongoing | 25200 | 22002 | 2021-04-18
REWA / SIRMOUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034564916 — पी सी सी रोड निर्माण प्रदुम्न गौतम के हैंडपंप से हनुमानजी मंदिर तक | Closed | 38000 | 0 | 2020-04-14
REWA / SIRMOUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034564919 — पी सी सी रोड निर्माण सी एफ टी भवन के पास से विश्राम कुशवाहा के घर तक | Closed | 70000 | 0 | 2020-04-14
REWA / SIRMOUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034574777 — Pcc Road CFT bhawan ke pass se vishram kushwaha ke ghar taj | Closed | 70000 | 0 | 2021-04-02
REWA / SIRMOUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034627853 — PCC Road Belha Kol ke ghar se Panna Kol ke ghar tak | Ongoing | 12000 | 7140 | 2023-02-19
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034631413 — PCC ROad Nirman Mukhya marg se ramayan Gautam ke ghar tak | Completed | 31000 | 30927 | 2023-04-27 | 2024-02-25
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034631414 — PCC Road Nirman Santosh Kushwaha Ke ghar se Raja Kushwaha Ke ghar tak | Completed | 16000 | 15890 | 2023-04-18 | 2024-01-23
REWA / SIRMOUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034678679 — PCC Road Nirman Santosh Gautam ke ghar se Sanjay gautam ke ghar tak | Approved | 94000 | 0 | 2024-04-02
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034683757 — PCC Road Nirman Santosh Gautam ke ghar se Sanajay Gautam ke ghar taraf | Ongoing | 94000 | 93441.14 | 2024-03-16
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034683780 — PCC Road Sanjay gautam ke ghar ke pass se bhupendra gautam ke ghar tak | Closed | 94000 | 0 | 2023-04-02
REWA / SIRMOUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034819467 — PCC Road Nirman Sanjay Gautam ke ghar ke pass se bhupendra Gautam ke ghar tak | Completed | 94000 | 91264 | 2025-03-12 | 2026-05-22
REWA / SIRMOUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034832147 — PCC Road Nirman Main Road se kalandar Kol ke ghar tak | Approved | 20000 | 0 | 2024-05-14
REWA / SIRMOUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/22012034842210 — Nali Nirman Karya devi mandir ke peeche se rajkumar gautam ke ghar tak | Ongoing | 77000 | 41760 | 2025-07-22
REWA / SIRMOUR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713003080/RC/550 — आंतरिक पीसीसी रोड निर्माण सहनाली कुंजल तिपाठी के घर से हनुमान मंदिर तक TS 550 | Completed | 487000 | 76677 | 2012-02-21 | 2012-06-30
REWA / SIRMOUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034329885 — Souchalay Nirman Ganga Kol | Completed | 12000 | 11372 | 2017-05-02 | 2018-05-10
REWA / SIRMOUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034333278 — RAKESH KUMAR DWIVEDI | Closed | 0 | 0 | 2017-01-26
REWA / SIRMOUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034333282 — SOUCHALAY NIRMAN RAKESH KUMAR DWIVEDI | Closed | 0 | 0 | 2016-04-02
REWA / SIRMOUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034333421 — SOUCHALAY RAKESH KUMAR DWIVEDI | Closed | 0 | 0 | 2017-01-26
REWA / SIRMOUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034333589 — LATRINE KHELAWAN KOL | Completed | 12000 | 11372 | 2017-05-27 | 2018-05-10
REWA / SIRMOUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Stabilization Pond / Construction of Stabilization Pond for Community | Solid and Liquid Waste Management | 1713003080/RS/22012034334201 — SAUCHALAY SANAT KOAL | Closed | 0 | 0 | 2017-01-26
REWA / SIRMOUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034334317 — sauchalay dinesh koal | Closed | 0 | 0 | 2017-01-26
REWA / SIRMOUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034334338 — sauchalay ramkhelavan koal | Closed | 0 | 0 | 2017-01-26
REWA / SIRMOUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034334343 — sauchalay lalohar koal | Closed | 12000 | 0 | 2017-01-26
REWA / SIRMOUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034335071 — sauchalay bhuralal koal | Closed | 0 | 0 | 2017-01-26
REWA / SIRMOUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034340576 — shouchalay nirman santosh vishwkarma | Deleted | 12000 | 0 | 2017-04-13
REWA / SIRMOUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034340581 — shuchalay nirman Ramnaresh vishwakarma | Completed | 12000 | 9802 | 2017-04-13 | 2018-05-30
REWA / SIRMOUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034340590 — sauchalay nirman sanath kol | Completed | 12000 | 11706 | 2017-05-02 | 2018-05-10
REWA / SIRMOUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034340591 — sauchalay nirman bhura lal kol | Completed | 12000 | 11372 | 2017-05-02 | 2018-05-10
REWA / SIRMOUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034340592 — sauchalay nirman lalohar kol | Completed | 12000 | 11706 | 2017-05-02 | 2018-05-05
REWA / SIRMOUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Stabilization Pond / Construction of Stabilization Pond for Community | Solid and Liquid Waste Management | 1713003080/RS/22012034344780 — sauchalay nirman ramkhelawan kol | Closed | 0 | 0 | 2016-04-26
REWA / SIRMOUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034349587 — Souchalay Nirman Dinesh Kol | Completed | 12000 | 11706 | 2017-05-29 | 2018-05-10
REWA / SIRMOUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034349590 — Souchalay Nirman Sunita Kol | Completed | 12000 | 3006 | 2017-05-29 | 2020-10-18
REWA / SIRMOUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034349591 — Souchalay Nirman Ashwani Shukla | Completed | 12000 | 11806 | 2017-05-29 | 2018-05-05
REWA / SIRMOUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034349592 — Souchalay Nirman Vindheshwari Shukla | Completed | 12000 | 11806 | 2017-05-29 | 2018-05-05
REWA / SIRMOUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713003080/RS/22012034349593 — Souchalay Nirman Dharmendra Gautam | Completed | 12000 | 11806 | 2017-05-29 | 2018-05-05
REWA / SIRMOUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1713003080/RS/22012034512463 — सीमेंट क्रंक्रीट नाली निर्माण सी एफ टी भवन के पास से विश्राम कुशवाहा के घर तक | Closed | 70000 | 0 | 2021-03-19
REWA / SIRMOUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1713003080/RS/22012034568569 — Nadep nirman kary 5 nag badrav gautman | Closed | 7700 | 0 | 2021-09-17
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1713003080/RS/22012034706658 — Soucalay Nirmam Badraon Tiwariyan Madhymik Shala Parishar | Closed | 17000 | 0 | 2023-04-02
REWA / SIRMOUR | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1713003080/SK/536 — Bharat Nirman Rajeev Gandhi Sewa Kendra,BADRAON GAUTAMAN | Completed | 1485000 | 334156 | 2013-09-08 | 2016-10-03
REWA / SIRMOUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713003080/WC/22012034828845 — Shok pit nirman kary 10 nag badrava gautaman | Closed | 103650 | 0 | 2021-08-15
REWA / SIRMOUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1713003080/WC/22012035139370 — Naali Nirman Devnarayan Pandey ke Ghar se Sudama Kol ke ghar tak | Closed | 100000 | 0 | 2023-04-02
REWA / SIRMOUR | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1713003080/WC/22012035196602 — Nala Gahrikaran Badraon Gautman | Closed | 0 | 0 | 2023-10-20
REWA / SIRMOUR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713003080/WC/2946 — कपिलधारा कूप निर्माण श्रीनिवास गौतम Ts 2946 | Completed | 118000 | 19642 | 2011-12-20 | 2015-02-26
REWA / SIRMOUR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713003080/WC/766 — नाला गहरीकरण वदरांव गौतमान ts no 766 | Completed | 492000 | 50064 | 2011-04-13 | 2013-04-24