## Work List
Exported on: 2026-10-21 06:13:09
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: RAMPURWA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
REWA / GANGEV | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1713004039/DP/22012034530673 — Sarvajanik Vriksharopan 1000 paudhe project gram panchayat Rampurwa | Ongoing | 983354.19 | 0 | 2021-08-23
REWA / GANGEV | 2025-2026 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1713004039/FP/22012034642029 — स्टार्म वाटर ड्रेन का निर्माण रामनरेश पटेल के घर से हीरालाल पटेल के घर की ओर | Approved | 101000 | 0 | 2025-04-01
REWA / GANGEV | 2025-2026 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1713004039/FP/22012034642030 — स्टार्म वाटर ड्रेन का निर्माण मुन्ना लाल साहू के घर से मुनिन्द्र साहू के घर की ओर | Approved | 59000 | 0 | 2025-04-01
REWA / GANGEV | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713004039/IF/22012035594912 — Ek Bagiya Maa ke naam Saroj Patel Rampurwa MP13004039001 327 | Ongoing | 266577.25 | 12600 | 2025-10-11
REWA / GANGEV | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713004039/IF/22012035627706 — एक बगिया मा के नाम एस0एच0जी0हितग्राही प्रियंका देवी पटेल के निजी भूमि में | Approved | 0 | 0 | 2025-08-15
REWA / GANGEV | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713004039/IF/22012035627708 — एक बगिया मा के नाम एस0एच0जी0हितग्राही निर्मला देवी के निजी भूमि में | New | 0 | 0 | 2025-08-15
REWA / GANGEV | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713004039/IF/22012035637874 — Ek Bagiya Maa Ke Naam SHG Hitgrahi Nirmala Patel Ke Niji Khet Me | Ongoing | 146354.34 | 8320.8 | 2025-11-07
REWA / GANGEV | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713004039/IF/22012035637875 — Ek Bagiya Maa Ke Naam SHG Hitgrahi Priyanka Devi Patel Patel Ke Niji Khet Me | New | 0 | 0 | 2025-08-15
REWA / GANGEV | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/3444012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5625942 | Ongoing | 27000 | 0 | 2023-12-07
REWA / GANGEV | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/3444743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5618958 | Ongoing | 27000 | 0 | 2023-12-07
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/4609472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125168826 | Ongoing | 27000 | 0 | 2026-10-05
REWA / GANGEV | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/4609535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125178599 | Completed | 27000 | 0 | 2025-01-09 | 2026-09-22
REWA / GANGEV | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/4619352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126925990 | Completed | 27000 | 0 | 2025-01-09 | 2026-09-22
REWA / GANGEV | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/4619362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126927221 | Completed | 27000 | 0 | 2025-07-24 | 2026-09-22
REWA / GANGEV | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/4855245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126989773 | Completed | 27000 | 0 | 2025-01-09 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6029111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125917212 | Completed | 27000 | 9600 | 2026-04-06 | 2026-10-16
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6029116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126948602 | Completed | 27000 | 8700 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6029681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126966352 | Completed | 23490 | 7200 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126946699 | Ongoing | 27000 | 0 | 2026-04-06
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127133558 | Completed | 27000 | 8700 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127164727 | Completed | 27000 | 10800 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126957899 | Completed | 27000 | 7500 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126972446 | Completed | 27000 | 8700 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125934464 | Completed | 27000 | 8700 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126983771 | Ongoing | 27000 | 0 | 2026-04-06
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127106979 | Completed | 27000 | 8700 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126979395 | Completed | 27000 | 8700 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126978744 | Completed | 27000 | 4200 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151052813 | Completed | 27000 | 8700 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126925228 | Ongoing | 27000 | 0 | 2026-04-06
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126933554 | Ongoing | 27000 | 9900 | 2026-04-06
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126940822 | Ongoing | 27000 | 0 | 2026-04-06
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126949574 | Completed | 27000 | 8700 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127166413 | Completed | 27000 | 8700 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6030852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145094473 | Completed | 27000 | 8700 | 2026-04-06 | 2026-09-22
REWA / GANGEV | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1713004039/IF/IAY/6280836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126990848 | Ongoing | 27000 | 0 | 2026-10-17
REWA / GANGEV | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1713004039/RC/22012034836472 — पीसीसी रोड निर्माण कार्य मुख्य सड़क से पंचायत भवन की ओर | Ongoing | 55500 | 0 | 2025-04-26
REWA / GANGEV | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of IHHL for Individual | Construction of Toilets | 1713004039/RS/22012034330125 — नवीन शौचालय निर्माण दिवाकर पटेल पिता लक्ष्मण | Physically Completed | 12000 | 0 | 2017-04-07 | 2026-10-15
REWA / GANGEV | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1713004039/RS/22012035122961 — नाडेप टांका निर्माण पंचायत भवन के पास | New | 0 | 0 | 2024-01-26
REWA / GANGEV | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1713004039/WC/22012034661716 — Talab Jal Samta Vishtarikarn Mishra tola ke pokhar me | Ongoing | 999751.78 | 0 | 2021-05-19
REWA / GANGEV | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Repair & Maintenance of Flood or Diversion Channel for Community | Terracing | 1713004039/WC/22012034690851 — Nala Saaf Safai evam Trenching karya Devi Mandir se Kamlesh patel ke khet taraf 200m | Ongoing | 327537.6 | 0 | 2021-05-30