## Work List
Exported on: 2026-08-20 05:21:48
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KOLAHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
REWA / HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1713005016/AV/22012034624780 — Santi dham nirman karya Sannasiha talab ke bhitha par | Physically Completed | 306483.89 | 0 | 2023-05-04 | 2026-08-05
REWA / HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1713005016/AV/22012034649189 — Panchyat Bhwan nirman krya kolha me | Ongoing | 920000 | 0 | 2023-10-09
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1713005016/DP/22012034615056 — Sarvajanik koop nirman kary rajesh patel ke ghar ke pas | Ongoing | 537251.35 | 0 | 2025-06-07
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1713005016/IC/22012034890031 — Sarvajanik koop nirman kary adiwasi basti bageeche ke pas | Physically Completed | 327831.8 | 0 | 2025-06-02 | 2026-08-05
REWA / HANUMANA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713005016/IF/22012035175426 — Kapil Dhara koop nrman karya Adarsh shukla ki bhumi par | Ongoing | 296962.26 | 0 | 2023-10-09
REWA / HANUMANA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713005016/IF/22012035175462 — Kapil Dhara koop nrman karya balmiki shukla ki bhumi par | Ongoing | 296962.26 | 0 | 2023-10-09
REWA / HANUMANA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713005016/IF/22012035206785 — Kapil dhara koop nirman karya Ahsok kumar | New | 0 | 0 | 2024-01-26
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713005016/IF/22012035217579 — Kapil dhara koop nirman kary udayan kumar shukla ke bhumi par | Ongoing | 403315.5 | 0 | 2024-11-19
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713005016/IF/22012035263968 — Kapil dhara koop nirman kary amritlal saket ke bhumi par | Approved | 0 | 0 | 2024-08-15
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713005016/IF/22012035332188 — Kapil dhara koop nirman kary gyanendra upadhyay ke bhumi par | Approved | 327831.8 | 0 | 2025-04-05
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713005016/IF/22012035436277 — Khet talab nirman kary aridaman kumar shukla ke bhumi par | Approved | 0 | 0 | 2025-04-14
REWA / HANUMANA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/2842117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4235647 | Ongoing | 23490 | 0 | 2021-06-29
REWA / HANUMANA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/3106565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4114083 | Ongoing | 23490 | 0 | 2021-07-02
REWA / HANUMANA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/3154549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4114074 | Approved | 23490 | 0 | 2020-11-03
REWA / HANUMANA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/3373881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4331323 | Ongoing | 23490 | 0 | 2021-12-28
REWA / HANUMANA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/3603729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4215049 | Approved | 23490 | 0 | 2022-01-09
REWA / HANUMANA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4332900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121593681 | Approved | 23490 | 0 | 2022-08-14
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4709127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124784392 | Ongoing | 23490 | 0 | 2024-12-31
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4761988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120566276 | Ongoing | 23490 | 0 | 2024-12-31
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4762304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120929897 | Approved | 23490 | 0 | 2024-09-26
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4762716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121610347 | Ongoing | 23490 | 0 | 2024-11-07
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4769161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124482476 | Ongoing | 23490 | 0 | 2024-11-25
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4771125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124816553 | Ongoing | 21870 | 0 | 2024-11-26
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4799877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148954053 | Ongoing | 23490 | 0 | 2024-11-07
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4823349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121611344 | Ongoing | 23490 | 0 | 2025-01-16
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4823863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121989854 | Ongoing | 23490 | 0 | 2025-01-16
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4827822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126655971 | Ongoing | 23490 | 0 | 2025-01-16
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4974466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124786975 | Ongoing | 23490 | 0 | 2025-03-21
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4974467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124787691 | Ongoing | 23490 | 0 | 2025-03-21
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4974471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124789110 | Ongoing | 23490 | 0 | 2025-03-21
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/4976149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120563920 | Ongoing | 23490 | 0 | 2025-03-21
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/5265294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124768902 | Approved | 23490 | 0 | 2025-03-19
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/5268135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124780418 | Physically Completed | 23490 | 0 | 2025-10-24 | 2026-08-16
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/5341790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148954338 | Physically Completed | 23490 | 0 | 2025-10-24 | 2026-08-16
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/5422396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143520736 | Ongoing | 23490 | 0 | 2025-10-24
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/5442613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121616215 | Physically Completed | 23490 | 0 | 2025-10-24 | 2026-07-05
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/5443604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121988965 | Approved | 23490 | 0 | 2025-04-08
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/5569625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124783156 | Approved | 23490 | 0 | 2025-04-13
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/5772515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133127804 | Ongoing | 23490 | 0 | 2025-10-08
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/5772716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123773237 | Ongoing | 23490 | 0 | 2025-09-16
REWA / HANUMANA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005016/IF/IAY/950627 — Construction of IAY House -IAY REG. NO. MP3059632 | Approved | 23490 | 0 | 2017-04-01
REWA / HANUMANA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1713005016/LD/22012034533162 — MED BADHAN NIRMAN KARYA UPENDRA SINGH KI BHUMI PAR | Ongoing | 64165.14 | 0 | 2021-03-24
REWA / HANUMANA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1713005016/RS/22012035133730 — Nadep nirman kary 10 nag gram panchayat kolha | Approved | 40000 | 0 | 2024-08-15
REWA / HANUMANA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1713005016/WC/03/????? — 1713005016/WC/03/ | Ongoing | 0 | 0 | 2013-11-01