## Work List
Exported on: 2026-09-07 23:03:24
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: DADAR PURVI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
REWA / HANUMANA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713005078/AV/22012034542967 — Nali nirman Kary ramnath kol ke gar se suresh Gupta ki gar ki taraf | Ongoing | 75000 | 0 | 2020-12-08
REWA / HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1713005078/AV/22012034624456 — Shanti Dham Nirman Kary Gram Kerha Kala me | Ongoing | 288548.97 | 0 | 2023-06-06
REWA / HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1713005078/AV/22012034633191 — Samtalikaran nirmam kary dadar kurmiyan school ke charo taraf | Ongoing | 835128 | 0 | 2023-06-07
REWA / HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1713005078/AV/22012034633392 — Samatlikaran kbristan dadar me | Ongoing | 710308.8 | 0 | 2023-06-09
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713005078/IF/22012035501183 — Khet Talab Nirman Kary Rajbahor Patel bhimi per gp dadar purvi | New | 0 | 0 | 2025-05-05
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713005078/IF/22012035502679 — Khet Talab Nirman Kary Janki Patel/wisram patel bhimi per gp dadar purvi | Approved | 450885.64 | 0 | 2025-04-14
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713005078/IF/22012035502718 — Khet Talab Nirman Kary Ramnidhi Patel ke bhimi per gp dadar purvi | Approved | 450885.64 | 0 | 2025-04-14
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713005078/IF/22012035502743 — Khet Talab Nirman Kary Nandlal Singh ke bhimi per gp dadar purvi | Ongoing | 147621.16 | 0 | 2025-05-14
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713005078/IF/22012035505130 — Khet Talab Nirman Kary Ramnewaj Patel bhimi per gp dadar purvi | Approved | 147621.16 | 0 | 2025-04-14
REWA / HANUMANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1713005078/IF/22012035506737 — Sok pit Devlal ke gar ke pass haindpump gp dadar purvi | Approved | 0 | 0 | 2025-04-14
REWA / HANUMANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1713005078/IF/22012035506903 — JGSA 2025 kapildara koop amrjeet singh | New | 0 | 0 | 2025-04-14
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713005078/IF/22012035507124 — khet talab safirunisha /mehadihasan ke bhumi per | New | 0 | 0 | 2025-04-14
REWA / HANUMANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1713005078/IF/22012035515217 — JGSA 2025 Gugwell Recharge pit kapildara koop Amarjit singh ke bhumi per | Approved | 25899.46 | 0 | 2025-04-14
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713005078/IF/22012035515882 — khet talab Amarjeet singh ke bhumi per | Ongoing | 450885.64 | 0 | 2025-05-27
REWA / HANUMANA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005078/IF/IAY/3521122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4113246 | Ongoing | 27000 | 0 | 2022-02-14
REWA / HANUMANA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005078/IF/IAY/4303524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119085680 | Ongoing | 27000 | 0 | 2022-08-05
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005078/IF/IAY/4713458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125975273 | Ongoing | 27000 | 0 | 2025-01-01
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005078/IF/IAY/4719603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126843646 | Physically Completed | 23490 | 0 | 2024-12-17 | 2026-08-09
REWA / HANUMANA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005078/IF/IAY/4719644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126859598 | Ongoing | 27000 | 0 | 2025-01-01
REWA / HANUMANA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713005078/IF/IAY/88508 — Construction of IAY House -IAY REG. NO. MP-13-005-078-003/57 | Ongoing | 27000 | 0 | 2025-08-08
REWA / HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713005078/RC/22012034677278 — Sudur Road Keraha se dadar school tk pahuch marg | New | 0 | 0 | 2024-01-27
REWA / HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713005078/RC/22012034677279 — Sudur Road Keraha se dadar school tk pahuch marg | New | 0 | 0 | 2024-01-27
REWA / HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713005078/RC/22012034677282 — Sudur road Hata road dadar se Bhadauha pahuch marg | New | 0 | 0 | 2024-01-27
REWA / HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1713005078/RS/22012034705085 — Dadar purvi school ke pass Samudhyik Swachhata shochalay Parisar Nirman | Ongoing | 80000 | 0 | 2023-10-13
REWA / HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1713005078/RS/22012035123441 — Shok pit(Recharge pit) kerha dadar | New | 0 | 0 | 2024-01-27
REWA / HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1713005078/RS/22012035123444 — Shok pit(Recharge pit) dadar me | New | 0 | 0 | 2024-01-27
REWA / HANUMANA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Vermi Compost structure for Groups / Construction of Vermi Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1713005078/RS/22012035123445 — Varmi composti | New | 0 | 0 | 2024-01-27
REWA / HANUMANA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713005078/WC/22012035303721 — Sok pit nirman Ramnidhi ke gar ke pass haidpump | Approved | 0 | 0 | 2025-04-14