## Work List
Exported on: 2026-09-05 11:04:49
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: KUSAHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
REWA / NAIGARHI | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713007006/AV/22012034503549 — छतदार पुलिया निर्माण कार्य रहीश साकेत के घर के पास | Completed | 25200 | 21930 | 2019-11-24 | 2020-05-28
REWA / NAIGARHI | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713007006/AV/22012034503562 — छतदार पुलिया निर्माण कार्य श्रीनावास यादव के घर के पास | Closed | 25200 | 0 | 2019-10-02
REWA / NAIGARHI | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713007006/AV/22012034504091 — छतदार पुलिया निर्माण रामजियावन यादव के घर के पास | Closed | 25200 | 0 | 2019-08-15
REWA / NAIGARHI | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713007006/AV/22012034550456 — Nali nirman karya PS itarngaw se Rajeshwar prasad pandey ke ghar tak | Deleted | 51000 | 0 | 2019-08-15
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1713007006/AV/22012034567360 — Paver block nirman govt middle school kushaha | Ongoing | 115800 | 48500 | 2021-07-16
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1713007006/AV/22012034574739 — seggregation shed kushaha | Completed | 149500 | 116750 | 2021-11-09 | 2024-05-13
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713007006/AV/22012034593103 — Puliya nirman intarangaw PCC road ke paas | Completed | 25200 | 8150 | 2021-11-24 | 2023-11-13
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1713007006/AV/22012034612958 — Maa ki bagiya nirman GPS. Kushaha | Closed | 0 | 0 | 2021-10-02
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1713007006/AV/22012034612959 — Maa ki bagiya nirman karya UGS. Dharmnaghari | Closed | 0 | 0 | 2021-10-02
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1713007006/AV/22012034612961 — Maa ki bagiya nirman karya UGS.itarangown | Closed | 0 | 0 | 2021-10-02
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1713007006/AV/22012034612963 — Maa ki bagiya nirman karya UGS. Rojhaunh | Closed | 0 | 0 | 2021-10-02
REWA / NAIGARHI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1713007006/AV/22012034637366 — RCC puliya Nirman Ashok Tiwari ke Ghar ke pas gram kushaha | Completed | 23000 | 18600 | 2023-10-13 | 2024-01-17
REWA / NAIGARHI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1713007006/AV/22012034650429 — आंगनवाड़ी भवन निर्माण ग्राम कुसहा | Closed | 0 | 0 | 2023-08-16
REWA / NAIGARHI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1713007006/AV/22012034652376 — आंगनवाड़ी भवन निर्माण ग्राम कुसहा | New | 0 | 0 | 2024-01-27
REWA / NAIGARHI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1713007006/AV/22012034665236 — Shanti Dham Nirman Harijan basti Gosaitara Talab ke Bheetha Me Kushaha | New | 29000 | 0 | 2024-10-02
REWA / NAIGARHI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1713007006/DP/1 — पथ व़क्षा रोपण डेहमहान टोला पहुच मार्ग के दोनों ओर कुशहा | Deleted | 187000 | 31913 | 2008-08-08
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/10 — निर्मल बाटिका BPL दुर्गा पिता राम प्रताप कुशहा | Completed | 4200 | 728 | 2009-08-11 | 2012-07-10
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/11 — निर्मल बाटिका BPL राजेश्‍वर पिता राम प्रसाद कुशहा | Completed | 4200 | 728 | 2009-08-07 | 2012-09-02
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/12 — निर्मल बाटिका BPL सुभाष पिता शीतला प्रसाद कुशहा | Completed | 4200 | 728 | 2009-08-11 | 2012-09-02
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/13 — निर्मल बाटिका BPL ठाकुर प्रसाद कुशहा | Completed | 4200 | 728 | 2009-08-11 | 2012-09-02
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/14 — निर्मल बाटिका BPL राजकुमार पिता नागेश्‍वर कुशहा | Completed | 4200 | 728 | 2009-08-16 | 2012-09-02
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/15 — निर्मल बाटिका BPL चक्रधर पिता जगमोहन कुशहा | Completed | 4200 | 728 | 2009-08-13 | 2012-09-02
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/16 — निर्मल बाटिका BPL जीतेन्‍द्र पिता राजकुमार कुशहा | Completed | 4200 | 728 | 2009-08-17 | 2012-07-07
REWA / NAIGARHI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1713007006/DP/2 — पथ व़क्षा रोपण ग्राम इटारगॉव धर्मनगरी पहुच मार्ग के दोनों ओर कुशहा | Completed | 187000 | 33061 | 2008-08-25 | 2012-05-22
REWA / NAIGARHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1713007006/DP/22012034585570 — अमृत बाटिका गोसाई तारा तालाब कुशहा | Closed | 0 | 0 | 2023-04-14
REWA / NAIGARHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1713007006/DP/22012034624955 — Briksharopan kary gosaitara Talab ke bhitha me gram kusha | Approved | 0 | 0 | 2024-06-11
REWA / NAIGARHI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/3 — निर्मल बाटिका कार्य 50 हितग्राही BPL कुशहा | Deleted | 270000 | 148142 | 2010-06-25
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/4 — निर्मल बाटिका BPL छोटेलाल पिता मथुरा इटारनगॉव कुशहा | Deleted | 0 | 0 | 2009-05-25
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/5 — निर्मल बाटिका BPL छोटेलाल पिता मथुरा इटारनगॉव कुशहा | Completed | 4200 | 728 | 2009-08-16 | 2012-07-10
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/6 — निर्मल बाटिका BPL चन्द्रिका पिता बद्रीराम कुशहा | Completed | 4200 | 728 | 2009-08-16 | 2012-07-10
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/7 — निर्मल बाटिका BPL रमेश पिता शिवमूर्ति कुशहा | Completed | 4200 | 728 | 2009-08-07 | 2012-07-10
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/8 — निर्मल बाटिका BPL यशोमति कुशहा | Completed | 4200 | 364 | 2009-08-14 | 2012-07-10
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1713007006/DP/9 — निर्मल बाटिका BPL मिठाईलाल पिता बद्रीराम कुशहा | Completed | 4200 | 728 | 2009-08-07 | 2012-07-10
REWA / NAIGARHI | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713007006/DW/2171 — पेयजल कूप नि० मस्जिद के पास कुशहा टी.एस 1030 | Completed | 339000 | 236622.8 | 2014-02-10 | 2016-10-10
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Cement lining / Lining of distributary Canal for Community | Works for Flood Control and Protection | 1713007006/FP/1 — नाली निर्माण कार्य अहिरान बस्‍ती कुशहा | Completed | 352000 | 275326.21 | 2009-06-22 | 2011-06-30
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034298667 — Nadep Taka Nirman Dileep Kumar Pandey TS 602 | Completed | 15700 | 13746.75 | 2016-11-08 | 2017-07-26
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034298668 — Nadep Taka Nirman Kedar Ram TS 598 | Completed | 15700 | 15334.27 | 2016-11-08 | 2017-07-26
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034298669 — Nadep Taka Nirman Chhotelal Pandey TS 599 | Deleted | 15700 | 0 | 2016-09-07
REWA / NAIGARHI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713007006/IF/22012034316694 — kapildhara koop sah khet talab nirman | Closed | 0 | 0 | 2017-04-01
REWA / NAIGARHI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713007006/IF/22012034327614 — Kapildhara Koop Nirman Sah Khet Talab Hitgrahi Savitri Tiwari W/O Shri Ashok Tiwari | Completed | 230000 | 201984 | 2017-04-11 | 2020-05-28
REWA / NAIGARHI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1713007006/IF/22012034334512 — कपिलधारा सह खेत तालाब - अनीता / सतीश तिवारी के खेत में | Completed | 230000 | 193984 | 2017-04-21 | 2020-05-28
REWA / NAIGARHI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1713007006/IF/22012034353508 — Vriksharopan Karya PM Sadak ke kinare Kushaha | Completed | 335000 | 6536 | 2017-08-30 | 2018-09-30
REWA / NAIGARHI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1713007006/IF/22012034353511 — Vriksharopan Karya Gosaee Tara talab ke bhita par | Completed | 335000 | 23880 | 2017-07-06 | 2018-12-31
REWA / NAIGARHI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1713007006/IF/22012034353518 — Vriksharopan Karya Sadak ke kinare itarangaw | Closed | 167500 | 0 | 2017-04-14
REWA / NAIGARHI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1713007006/IF/22012034431526 — Paudhropan karya Nandlal avm Heeralal Tiwari ke khet ki med me | Deleted | 94600 | 0 | 2018-04-14
REWA / NAIGARHI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1713007006/IF/22012034481214 — Med bandhan karya heeralal tiwari | Completed | 58230.87 | 47460 | 2019-10-20 | 2022-11-28
REWA / NAIGARHI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1713007006/IF/22012034481215 — Med bandhan karya Nandlal tiwari | Completed | 65436.55 | 53880 | 2019-11-23 | 2024-05-17
REWA / NAIGARHI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1713007006/IF/22012034501584 — Med bandhan karya Rajendra Mishra | Completed | 75311 | 65230 | 2020-06-04 | 2022-03-03
REWA / NAIGARHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1713007006/IF/22012034560473 — मेड बंधान निर्माण कार्य तेजेश्वरी प्रसाद तिवारी के खेत में | Completed | 97147.74 | 76400 | 2020-06-26 | 2024-06-14
REWA / NAIGARHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1713007006/IF/22012034560769 — मेड बंधान निर्माण कार्य ॳगद साकेत के भूमि में | Completed | 98027.96 | 83320 | 2020-06-13 | 2022-01-04
REWA / NAIGARHI | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034586201 — Nadep taka kary nand lal tiwari ke ghar ke samne | Completed | 26519.52 | 3700 | 2021-03-19 | 2022-11-28
REWA / NAIGARHI | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034586208 — Nadep taka karya Ashok kumar tiwari ke ghar ke samne | Closed | 0 | 0 | 2020-01-26
REWA / NAIGARHI | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034594694 — नाडेप टांका निर्माण कार्य तेजेश्वरी प्रसाद तिवारी के भूमि मे | Closed | 0 | 0 | 2020-01-26
REWA / NAIGARHI | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034594702 — नाडेप टांका निर्माण कार्य राजमणि जायसवाल के भूमि मे | Closed | 0 | 0 | 2020-01-26
REWA / NAIGARHI | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034594704 — नाडेप टांका निर्माण कार्य शम्भू पुरी के भूमि में | Closed | 0 | 0 | 2020-01-26
REWA / NAIGARHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1713007006/IF/22012034614389 — मेड बंधान निर्माण कार्य अनीता तिवारी के भूमि मे | Completed | 40362.09 | 33000 | 2020-12-02 | 2022-11-26
REWA / NAIGARHI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1713007006/IF/22012034630298 — मेड बंधान निर्माण कार्य सावित्री तिवारी के भूमि मे ग्राम कुशहा | Closed | 18777.69 | 0 | 2020-10-02
REWA / NAIGARHI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1713007006/IF/22012034630304 — मेड बंधान निर्माण कार्य सौखीलाल तिवारी के भूमि मे ग्राम कुशहा | Closed | 58022.05 | 0 | 2020-10-02
REWA / NAIGARHI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1713007006/IF/22012034630307 — मेड बंधान निर्माण कार्य लालमणि जायसवाल के भूमि मे ग्राम कुशहा | Completed | 19268.24 | 14640 | 2021-01-04 | 2022-09-25
REWA / NAIGARHI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1713007006/IF/22012034631181 — Med bandhan nirman karya Surendra Tiwari ke bhumi me | Closed | 59984.28 | 0 | 2020-10-02
REWA / NAIGARHI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1713007006/IF/22012034631187 — Med bandhan nirman karya rajesh Tiwari ke bhumi me kushaha | Closed | 0 | 0 | 2020-10-02
REWA / NAIGARHI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1713007006/IF/22012034631193 — Med bandhan nirman karya harikeshar Tiwari ke bhumi me kushaha | Closed | 0 | 0 | 2020-10-02
REWA / NAIGARHI | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034631346 — Nadep tanka Rajesh Tiwari ke bhumi me kushaha | Closed | 0 | 0 | 2020-10-02
REWA / NAIGARHI | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034631347 — Nadep tanka karya pavan kumar Tiwari ke bhumi me kushaha | Closed | 0 | 0 | 2020-10-02
REWA / NAIGARHI | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034631348 — Nadep tanka nirman karya uma Shankar dwivedi ke bhumi me | Completed | 19110.29 | 1800 | 2021-03-19 | 2024-05-13
REWA / NAIGARHI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1713007006/IF/22012034637440 — मेड बंधान निर्माण कार्य प्रभा तिवारी के भूमि मे ग्राम कुशहा | Completed | 85493.12 | 67110 | 2021-01-04 | 2025-01-04
REWA / NAIGARHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1713007006/IF/22012034639339 — बकरी शेड निर्माण कार्य अंजू साकेत के भूमि मे | Physically Completed | 46926.81 | 42567 | 2021-02-22 | 2026-06-29
REWA / NAIGARHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1713007006/IF/22012034639882 — बंजर भूमि विकास निर्माण कार्य अशोक तिवारी के भूमि मे ग्राम कुशहा | Completed | 68944.78 | 56750 | 2021-03-06 | 2022-11-29
REWA / NAIGARHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1713007006/IF/22012034640399 — बंजर भूमि विकास निर्माण कार्य उमेश मिश्रा ग्राम ईटारनगाव | Completed | 77822.44 | 63940 | 2021-03-20 | 2022-11-26
REWA / NAIGARHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1713007006/IF/22012034643695 — Vriksharopan karya Rajendra Mishra ke bhumi me | Deleted | 115360 | 0 | 2020-10-02
REWA / NAIGARHI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1713007006/IF/22012034643697 — Vriksharopan karya Umesh mishra ke bhumi me | Deleted | 115360 | 0 | 2020-10-02
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034877107 — Nadep taka nirman hafij baks ke ghar ke pas | Deleted | 4000 | 0 | 2021-04-14
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034877140 — Nadep taka nirman Rajeshwari Prasad Tiwari ke ghar ke pas | Deleted | 4000 | 0 | 2021-04-14
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1713007006/IF/22012034877145 — Nadep taka nirman Rajkumar Pandey | Deleted | 4000 | 0 | 2021-04-14
REWA / NAIGARHI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1713007006/IF/22012035140610 — Kailashvati pandey/shomeshwar ki Bhumi Me Falodyan ka kary | Ongoing | 391000 | 93731.55 | 2023-09-28
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713007006/IF/22012035346655 — Khet Talab Nirman Chhotelal Pandey ke Bhumi me Gram Itarangav | Physically Completed | 450885.64 | 359556.28 | 2025-04-24 | 2026-05-27
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1713007006/IF/22012035538758 — Khet Talab nirman Shanti Jaiswal Ki Bhumi Me Gram Rojhau | Physically Completed | 450885.64 | 210504.64 | 2025-05-23 | 2026-06-25
REWA / NAIGARHI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713007006/IF/9926701862 — Cattle Shed Kedarram TS 1444 | Completed | 53000 | 51528.22 | 2014-02-14 | 2014-09-14
REWA / NAIGARHI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713007006/IF/9926701864 — Cattle Shed Dilip Kumar TS 1027 | Completed | 53000 | 51396.22 | 2014-02-14 | 2014-09-14
REWA / NAIGARHI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713007006/IF/9926701865 — Cattle Shed Pawan Kumar Pandey TS 1028 | Completed | 53000 | 51528.22 | 2014-02-14 | 2014-09-14
REWA / NAIGARHI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713007006/IF/9926701866 — Cattle Shed Ugrasen Puri TS 1024 | Completed | 53000 | 51396.22 | 2014-02-14 | 2015-03-30
REWA / NAIGARHI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713007006/IF/9926701869 — Cattle Shed Vindra Jayswal TS 1029 | Completed | 53000 | 50586.22 | 2014-02-14 | 2014-09-14
REWA / NAIGARHI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713007006/IF/9926702510 — Pashu Shed Rajkumar/Vashudev Ram | Completed | 53000 | 50586.22 | 2014-02-16 | 2014-09-14
REWA / NAIGARHI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713007006/IF/9926712430 — Ts. 1976 Pashu Shed Nirman Sukhsen Puri | Completed | 53000 | 50850.22 | 2014-03-03 | 2015-03-30
REWA / NAIGARHI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713007006/IF/9926712433 — Ts. 1975 Pashu Shed Nirman Sunil Puri | Completed | 53000 | 51396.22 | 2014-03-03 | 2014-09-14
REWA / NAIGARHI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713007006/IF/9926712437 — Ts. 1972 Pashu Shed Nirman Krishnakant Puri | Completed | 53000 | 51924.22 | 2014-03-03 | 2015-03-30
REWA / NAIGARHI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713007006/IF/9926712439 — Ts. 1974 Pashu Shed Nirman Chhotelal Pandey | Completed | 53000 | 51528.22 | 2014-03-03 | 2014-09-14
REWA / NAIGARHI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713007006/IF/9926712441 — Ts. 1971 Pashu Shed Nirman Sidhgopal | Completed | 53000 | 51396.22 | 2014-03-03 | 2014-09-14
REWA / NAIGARHI | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1713007006/IF/9926712443 — Ts. 1973 Pashu Shed Nirman Ramesh Pandey | Completed | 53000 | 51396.22 | 2014-03-03 | 2014-09-14
REWA / NAIGARHI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/9993751430 — IAY brijkishor shukla/bhagwatram shukla TS no. 417/6/1,Date 21/09/2015 | Completed | 14300 | 14195 | 2016-07-25 | 2017-11-08
REWA / NAIGARHI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/9993751762 — IAY brijlal saket/heeralal saket ts no.417/6/2 Date 21/9/2015 | Completed | 14300 | 14300 | 2016-07-25 | 2017-11-08
REWA / NAIGARHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/3124883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4111016 | Completed | 17370 | 17222 | 2021-06-05 | 2021-12-16
REWA / NAIGARHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/3336865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5564096 | Completed | 17370 | 17173 | 2022-02-18 | 2022-09-24
REWA / NAIGARHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/3525995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4154197 | Completed | 17370 | 17193 | 2022-02-18 | 2022-09-24
REWA / NAIGARHI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/3565102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5115543 | Completed | 17370 | 17294 | 2022-03-12 | 2022-10-11
REWA / NAIGARHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/3778867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126653350 | Completed | 18360 | 18080 | 2022-08-27 | 2022-12-27
REWA / NAIGARHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/3892336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143464743 | Completed | 18360 | 17888 | 2022-08-27 | 2023-01-31
REWA / NAIGARHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/4310438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143463591 | Completed | 18360 | 18080 | 2022-08-27 | 2022-12-27
REWA / NAIGARHI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/4334088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125777734 | Closed | 18360 | 0 | 2022-08-19
REWA / NAIGARHI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/4649053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143462981 | Completed | 21870 | 21380 | 2024-10-21 | 2025-01-11
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/5245523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116502845 | Completed | 23490 | 23460 | 2025-04-06 | 2026-02-23
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/5252712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143470616 | Completed | 23490 | 23229 | 2025-05-13 | 2026-01-25
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/5267541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143463849 | Ongoing | 27000 | 14314 | 2025-04-06
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/5269958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143465192 | Completed | 23490 | 23169 | 2025-04-17 | 2025-12-11
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/5296029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143464070 | Completed | 23490 | 18748 | 2025-04-06 | 2025-12-11
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/5303443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143464308 | Completed | 23490 | 23229 | 2025-06-14 | 2025-12-11
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/5304284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143463066 | Completed | 23490 | 23185 | 2025-04-07 | 2025-12-11
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/5322842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143464114 | Completed | 23490 | 23490 | 2025-05-13 | 2026-02-11
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/5323306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143464566 | Completed | 23490 | 23185 | 2025-04-07 | 2025-12-11
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/5332482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143470420 | Ongoing | 27000 | 15891 | 2025-04-06
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/5332694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125809797 | Ongoing | 27000 | 15630 | 2025-04-06
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/5338219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143463519 | Completed | 23490 | 23185 | 2025-04-07 | 2025-12-11
REWA / NAIGARHI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/53560 — Construction of IAY House -IAY REG. NO. MP-13-007-006-001/37026982 | Approved | 27000 | 0 | 2015-12-12
REWA / NAIGARHI | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/53561 — Construction of IAY House -IAY REG. NO. MP-13-007-006-003/25699801 | Approved | 27000 | 0 | 2015-12-12
REWA / NAIGARHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713007006/IF/IAY/5715843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143463916 | Completed | 23490 | 23229 | 2025-08-01 | 2026-02-11
REWA / NAIGARHI | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1713007006/LD/1102 — खेल मैदान मा0 शा0 कुशहा | Completed | 36000 | 30576 | 2011-12-11 | 2013-03-30
REWA / NAIGARHI | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1713007006/LD/22012034236142 — med bandhan karya lalbahadur/hardev singh ke bhumi ts 490 date 13/10/2015 | Completed | 60000 | 58004 | 2015-12-06 | 2016-09-05
REWA / NAIGARHI | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1713007006/LD/22012034236144 — med bnadhan karya abhyraj /hardev sigh ke bhumi me ts 495 date 13/10/2015 | Completed | 60000 | 56772 | 2015-11-28 | 2016-09-05
REWA / NAIGARHI | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1713007006/LD/22012034236205 — med badhan karya umashanakr/gokulram dwivedi ke bhumi me ts 496 date 13/10/2015 | Completed | 60000 | 57584 | 2015-11-06 | 2016-09-05
REWA / NAIGARHI | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1713007006/LD/22012034236208 — med bandhan karya avdhesh/kripashankar tiwari ke bhumi me 496 date 13/10/2015 | Completed | 60000 | 52964 | 2015-11-05 | 2016-09-05
REWA / NAIGARHI | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1713007006/LD/22012034237601 — med bandhan karya ashok kumar/ rajeshwari tiwari ke bhumi me ts 494 date 13/10/2015 | Deleted | 0 | 0 | 2015-08-15
REWA / NAIGARHI | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1713007006/LD/22012034237605 — med bandhan karya ashok kumar /rajeshwari ke bhumi ts 494 date 13/10/2015 | Completed | 60000 | 57824 | 2015-11-18 | 2016-09-05
REWA / NAIGARHI | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1713007006/LD/22012034237649 — मेड बंधान कार्य राघवेंद्र/राजकेशर तिवारी के भूमि टी यस 491 दिनाक 13/10/2015 | Completed | 60000 | 51516 | 2015-12-05 | 2016-09-05
REWA / NAIGARHI | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1713007006/LD/22012034249492 — med bandhan kary rajmani/ramsundar ke bhumi me TS.911 date18/12/2015 | Completed | 78000 | 74916 | 2016-02-15 | 2016-09-05
REWA / NAIGARHI | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1713007006/LD/22012034249539 — med bandhan karya saroj tiwari ts 913 date 18/12/2015 | Deleted | 30000 | 0 | 2015-12-22
REWA / NAIGARHI | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1713007006/LD/22012034249558 — med bandhan kary tejpratap ke ghumi me ts912 date18/12/2015 | Completed | 78000 | 60705.4 | 2016-02-15 | 2016-09-05
REWA / NAIGARHI | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1713007006/LD/22012034251269 — med bandhan karya kamleshwar/shyamsundar ke bhumi me ts 914 date 18/12/2015 | Completed | 78000 | 69800 | 2016-03-03 | 2016-09-05
REWA / NAIGARHI | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1713007006/LD/22012034256698 — भूमिशिल्प निर्माण कार्य | Closed | 0 | 0 | 2016-04-14
REWA / NAIGARHI | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1713007006/LD/3799435962 — Ts. 1690 Med Bandhan Nirman Kedar Ram | Completed | 41000 | 26280 | 2014-03-14 | 2015-03-30
REWA / NAIGARHI | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713007006/RC/1 — ग्रेवल रोड मार्ग निर्माण प्रधान0 रोड से इटारनगॉव तक कुशहा | Completed | 448000 | 349308 | 2011-03-01 | 2012-04-24
REWA / NAIGARHI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034186393 — पीसीसी सह नाली निर्माण कार्य ददन जाय. के घर से शेष | Completed | 127000 | 124156 | 2013-09-29 | 2015-03-30
REWA / NAIGARHI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713007006/RC/22012034200193 — TS 896 खे०स०ग्रेवल प्रधानमंत्री रोड से गगोलिहानटोला पं. क | Completed | 1149695 | 741631.2 | 2014-01-25 | 2016-09-04
REWA / NAIGARHI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034210791 — Ts. 1693 PCC Road Nirman Dadan Ke Ghar se Prathmik | Completed | 127500 | 122288 | 2014-03-03 | 2015-03-30
REWA / NAIGARHI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713007006/RC/22012034214430 — Ts. 1689 Khet Sadak Yojna Dharmnagari Mod Se yagya | Completed | 804593 | 396237.6 | 2014-03-14 | 2016-09-04
REWA / NAIGARHI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1713007006/RC/22012034214431 — Ts. 1688 Khet Sadak Yojna PCC Road Se Badri Jaiswa | Deleted | 258000 | 0 | 2014-01-30
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034263538 — PCC Road Nirman Karya Yagyasen saket ke ghar se Krishnkant puri ke ghar tak | Completed | 114750 | 112883 | 2017-10-31 | 2019-04-28
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034263557 — आंतरिक पी०सी०सी० पथ सह नाली श्याम सुन्दर पाण्डेय के घर के पास से बृजकिशोर के आम के पेड़ तक | Completed | 104000 | 92912.97 | 2016-12-16 | 2017-10-10
REWA / NAIGARHI | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713007006/RC/22012034295793 — sudur gram sampark khet sadak karya panadyen ganw ke pachim sima se lekar dharmnagarhi ganw tak | Deleted | 1179000 | 0 | 2015-12-22
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034349133 — PCC sah nali nirman karya Umashankar Dwivedi ke ghar se Badri Jaiswal ke ghar tak | Completed | 20062 | 16452 | 2017-08-16 | 2017-12-12
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034364224 — सीमेंट कंक्रीट रोड निर्माण कार्य प्राथमिक पाठशाला से रोझाऊ से उत्तर की ओर पुलिया तक | Completed | 480000 | 67080 | 2017-10-20 | 2018-01-01
REWA / NAIGARHI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034373117 — Pcc road nirman karya jamuna yadav ke ghar se transformer ke pas tak | Completed | 38250 | 38190 | 2019-03-05 | 2020-05-28
REWA / NAIGARHI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034396860 — pcc road nirman karya Rajesh payasi ke dukan se krishnkant puri ke ghar tak | Completed | 38250 | 34680 | 2019-03-05 | 2019-06-20
REWA / NAIGARHI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034396867 — pcc road nirman Yadav basti se kot sonvarsha pahunch marg tak | Completed | 76500 | 73662 | 2018-11-08 | 2019-06-20
REWA / NAIGARHI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034439191 — pcc road nirman kary jamuna yadav k gher k pas se transformer k pas tk | Deleted | 0 | 0 | 2019-01-26
REWA / NAIGARHI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034447008 — Pcc road nirman karya krishnkant puri ke ghar se paschim ki taraf | Closed | 114750 | 0 | 2019-01-26
REWA / NAIGARHI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034513931 — pcc road nirman | Closed | 0 | 0 | 2019-10-02
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034596352 — PCC sadak nirman PMGSY road se Dileep Pandey ke ghar tak | Closed | 103275 | 0 | 2021-04-15
REWA / NAIGARHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034622625 — पीसीसी रोड पंचायत भवन से रामजियावन यादव के घर तक कुशहा | Completed | 229500 | 181008 | 2023-08-30 | 2024-05-11
REWA / NAIGARHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/22012034657207 — पीसीसी रोड निर्माण कार्य रिजवान मोहम्मद के घर हफीज वक्स के घर तक १८० मीटर | Completed | 96750 | 76100 | 2023-10-09 | 2024-10-28
REWA / NAIGARHI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1713007006/RC/414 — ग्रेवल मार्ग निर्माण प्रधानमंत्री रोड से मुसलमान ब | Completed | 499000 | 481413.32 | 2012-12-01 | 2014-11-23
REWA / NAIGARHI | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713007006/RC/896 — पीसीसी रोड नाली सहित हरिजन वस्‍ती प्‍लाट के अतिशेष | Completed | 142000 | 137480 | 2012-02-01 | 2015-03-30
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034312700 — Shauchalay Marammat Karya Brijkishor S/O Bhagwatram Shukla | Completed | 11500 | 11444 | 2017-01-05 | 2018-08-01
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034312702 — Shauchalay Marammat Karya Rajesh S/O Lolarram Tiwari | Deleted | 9800 | 0 | 2016-12-13
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034312705 — Shauchalay Marammat Karya Dileep S/O Indradev Ram Pandey | Completed | 11500 | 10898 | 2017-01-05 | 2018-07-09
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034312712 — Shauchalay Marammat Karya Gopi S/O Sukuru Yadav | Completed | 11500 | 334 | 2017-01-05 | 2018-08-10
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034312714 — Shauchalay Marammat Karya Ganesh S/O Yagyasen Saket | Completed | 9800 | 9822 | 2017-01-05 | 2018-08-01
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034312716 — Shauchalay Marammat Karya Kanhaiyalal Vishwakarma | Completed | 9800 | 2422 | 2017-01-05 | 2018-08-11
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034322252 — shauchalay nirman karya amirun nisha | Completed | 12000 | 3006 | 2017-02-01 | 2022-10-10
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034322260 — shauchalay marammat karya shivmangal jayswal | Completed | 11500 | 11106 | 2017-02-01 | 2018-07-09
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034322268 — shauchalay marammat karya ramashankar puri | Completed | 11500 | 10605 | 2017-02-01 | 2018-07-27
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034322270 — shauchalay marammat karya umashankar sharma | Completed | 9800 | 9738 | 2017-02-01 | 2018-07-21
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034322274 — shauchalay nirman karya laish mohammad | Completed | 12000 | 11806 | 2017-02-01 | 2018-09-28
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034323679 — Shauchalay Nirman Karya Hafeej Baks | Completed | 12000 | 11806 | 2017-02-09 | 2017-07-12
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034323682 — Shauchalay Marammat Karya Abbu Hasan | Deleted | 11500 | 0 | 2016-12-13
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034323686 — Shauchalay Marammat Karya Heera Tiwari | Completed | 9800 | 9738 | 2017-02-09 | 2018-07-27
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034323948 — Shauchalay Nirman Karya Ramlal Saket | Completed | 12000 | 12140 | 2017-02-09 | 2017-10-30
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034323950 — Shauchalay Nirman Karya Ramesh Saket | Completed | 12000 | 11896 | 2017-04-04 | 2018-07-27
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034328365 — Shauchalay Nirman Karya Ali Ahamad | Completed | 12000 | 11806 | 2017-03-03 | 2017-07-12
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034328367 — Shauchalay Nirman Karya Muskil Baks | Completed | 12000 | 11806 | 2017-03-03 | 2017-07-12
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034333967 — शौचालय निर्माण कार्य -सुनील पुरी | Completed | 12000 | 11896 | 2017-04-26 | 2017-10-30
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034333972 — शौचालय निर्माण कार्य- राम कृपाल साकेत%कुंआरे साकेत | Deleted | 12000 | 0 | 2016-12-13
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034333974 — शौचालय निर्माण कार्य- बृज लाल साकेत%हीरालाल | Completed | 12000 | 11896 | 2017-04-04 | 2018-07-21
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034333978 — शौचालय निर्माण कार्य- कृण्ण कुमार तिवारी | Completed | 12000 | 11896 | 2017-04-04 | 2018-07-28
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034333984 — शौचालय निर्माण कार्य- महा रथी साकेत | Completed | 12000 | 11896 | 2017-04-04 | 2017-10-30
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034333986 — शौचालय निर्माण कार्य- वेबा यशोदा साकेत | Completed | 12000 | 11973 | 2017-03-21 | 2018-09-29
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034333988 — शौचालय निर्माण कार्य- पवन कुमार तिवारी | Completed | 12000 | 11973 | 2017-03-21 | 2017-10-30
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034333991 — शौचालय मर म्मत कार्य- रमेश पांडेय | Deleted | 9800 | 0 | 2016-12-13
REWA / NAIGARHI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034333995 — शौचालय मर म्मत कार्य- राजकुमार पांडेय | Deleted | 9800 | 0 | 2016-10-02
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034344813 — sauchalay nirman karya-ramkrishna prajapati | Completed | 12000 | 11896 | 2017-05-09 | 2017-07-12
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034344814 — sauchalay niraman-kaushal prajapati | Completed | 12000 | 11896 | 2017-05-11 | 2017-07-12
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034344858 — शौचालय निर्माण कार्य-रमई साकेत | Completed | 12000 | 11896 | 2017-05-09 | 2017-07-12
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034344860 — शौचालय निर्माण कार्य-रामसजीवन साकेत | Completed | 12000 | 11896 | 2017-05-11 | 2017-10-30
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034344861 — शौचालय निर्माण कार्य-हि च्छ लाल साकेत | Completed | 12000 | 11896 | 2017-06-08 | 2018-09-28
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034344874 — शौचालय मर म्मत कार्य-उग्रसेन पुरी | Completed | 11500 | 10764 | 2017-05-11 | 2018-08-15
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034344884 — शौचालय निर्माण कार्य हनीफ | Completed | 12000 | 11896 | 2017-05-11 | 2018-07-09
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034350005 — शौचालय निर्माण कार्य-कैलाश साकेत | Completed | 12000 | 11896 | 2017-06-01 | 2017-10-30
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034353154 — शौचालय निर्माण कार्य-दिनेश साकेत | Completed | 12000 | 11896 | 2017-07-03 | 2018-07-09
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034354300 — souchaly nirman karya babbu yadav | Completed | 12000 | 11896 | 2017-06-21 | 2018-07-09
REWA / NAIGARHI | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034356736 — शोचालय निर्माण कार्य-छोटे लाल साकेत%देवराज | Completed | 12000 | 11896 | 2017-07-04 | 2018-09-28
REWA / NAIGARHI | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1713007006/RS/22012034432348 — Nali nirman karya Kushaha plat me Transfarmer ke pas se Gosai tara talab tak | Deleted | 45000 | 0 | 2018-10-05
REWA / NAIGARHI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1713007006/RS/22012034432352 — Nali nirman karya Rahis Baks ke ghar se Heera Baks ke ghar ke pas tak | Deleted | 60000 | 0 | 2018-10-05
REWA / NAIGARHI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1713007006/RS/22012034475818 — सीमेंट कंक्रीट नाली निर्माण कार्य ट्रांसफर्मर के पास से गोसाई तारा तालाब तक | Completed | 43950 | 39150 | 2019-09-19 | 2020-05-28
REWA / NAIGARHI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1713007006/RS/22012034477102 — सीमेंट कंक्रीट नाली निर्माण कार्य राजेश्वर पांडे के घर से रामबदन पांडे के घर के पास तक | Completed | 51000 | 39060 | 2019-11-12 | 2023-12-30
REWA / NAIGARHI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1713007006/RS/22012034507259 — Sokhta gaddha nirman Ramlal saket ke ghar ke pas | Closed | 0 | 0 | 2020-10-02
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1713007006/RS/22012034507260 — Sokhta gaddha nirman MS SCHOOL KUSHAHA ke pas | Completed | 16445.48 | 2940 | 2021-10-11 | 2026-06-03
REWA / NAIGARHI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1713007006/RS/22012034507262 — Sokhta gaddha nirman PS SCHOOL KUSHAHA ke pas | Closed | 16445.48 | 0 | 2020-10-02
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1713007006/RS/22012034520127 — Cement concrete nali nirman Ramlagan Pandey ke ghar se Puliya tak Itarangaw | Ongoing | 143250 | 41940 | 2021-06-20
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1713007006/RS/22012034555915 — Cement concrete nali nirman PM road se dilip pandey ke ghar tak | Ongoing | 112200 | 300 | 2021-11-24
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1713007006/RS/22012034622993 — RCC nali nirman karya Gosai Tara talab harijan basti kushaha | Closed | 68850 | 0 | 2021-11-22
REWA / NAIGARHI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1713007006/RS/22012034623031 — सामुदायिक शौचालय निर्माण कार्य ग्राम पंचायत कुशहा | Completed | 100000 | 50966 | 2022-02-09 | 2023-12-30
REWA / NAIGARHI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1713007006/RS/22012034693439 — नाडेप टांका निर्माण हरिकेशर तिवारी के घर के पास ग्राम कुसहा | Closed | 3000 | 0 | 2023-01-27
REWA / NAIGARHI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1713007006/RS/22012034693441 — nadep naka nirman jahirunnisa | Closed | 3000 | 0 | 2023-01-27
REWA / NAIGARHI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1713007006/RS/22012034693442 — nadep naka nirman dilbahar | Closed | 3000 | 0 | 2023-01-27
REWA / NAIGARHI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1713007006/RS/22012034693443 — नाडेप टांका निर्माण रमेश पटेल के घर के पास ग्राम कुसहा | Closed | 3000 | 0 | 2023-01-27
REWA / NAIGARHI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1713007006/RS/22012034693445 — नाडेप टांका निर्माण उमेश पयाशी के घर के पास ग्राम इटारंगाव | Closed | 3000 | 0 | 2023-01-27
REWA / NAIGARHI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1713007006/RS/22012034693447 — नाडेप टांका निर्माण बृजमोहन पटेल के घर के पास ग्राम कुसहा | Closed | 3000 | 0 | 2023-01-27
REWA / NAIGARHI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1713007006/RS/22012034693449 — नाडेप टांका निर्माण ददन जैसवाल के घर के पास ग्राम रोझऊ | Closed | 3000 | 0 | 2023-01-27
REWA / NAIGARHI | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1713007006/RS/22012034693450 — नाडेप टांका निर्माण पवन पांडेय के घर के पास ग्राम इटारंगाव | Closed | 3000 | 0 | 2023-01-27
REWA / NAIGARHI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1713007006/RS/22012035117399 — नाली निर्माण कार्य कलीम के घर से रहीश बक्स के घर तक | Completed | 75000 | 68514.95 | 2023-10-08 | 2025-05-10
REWA / NAIGARHI | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713007006/WC/1 — तालाब गहरी करण बभनिया कुशहा | Completed | 447000 | 22284 | 2008-04-04 | 2012-04-24
REWA / NAIGARHI | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713007006/WC/2 — सोख्‍ता गडढा 1 नग छोटेलाल साकेत के घर के पास इटारनगॉव कुशहा | Completed | 19000 | 16474 | 2010-06-25 | 2012-03-29
REWA / NAIGARHI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1713007006/WC/22012034324737 — talab gahrikaran avam sudrikaran karya kushaha | Completed | 165000 | 1350 | 2017-05-15 | 2018-02-17
REWA / NAIGARHI | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1713007006/WC/22012034426785 — बंड विस्तारीकरण कार्य धरमनगरी तालाब ग्राम धरमनगरी | Completed | 246000 | 192494 | 2018-12-21 | 2022-01-04
REWA / NAIGARHI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1713007006/WC/22012034652000 — Babhaniya talab gaharikaran avam saundariykaran | Completed | 667781.36 | 608086.38 | 2022-02-12 | 2026-04-13
REWA / NAIGARHI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713007006/WC/22012034737404 — Roof water harvesting PS Itarangaw | Closed | 6000 | 0 | 2021-04-14
REWA / NAIGARHI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713007006/WC/22012034737420 — Roof water harvesting MS Kushaha | Closed | 6000 | 0 | 2021-04-14
REWA / NAIGARHI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713007006/WC/22012034737436 — Roof water harvesting Panchayat Bhawan Kushaha | Closed | 6000 | 0 | 2021-04-14
REWA / NAIGARHI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1713007006/WC/22012034752484 — Talab gaharikaran avam saundrikaran gosaitara talab me | Completed | 667781.36 | 598694.26 | 2021-06-29 | 2025-06-20
REWA / NAIGARHI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1713007006/WC/22012034994616 — संधारण कार्य गूडर नाला स्टाप डैम नं 2 | Closed | 50000 | 0 | 2022-04-14
REWA / NAIGARHI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen Check Dam for Community / Repair and Maintenance of Earthen Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1713007006/WC/22012034994620 — संधारण कार्य गूडर नाला स्टाप डैम नं 3 | Closed | 65000 | 0 | 2022-04-14
REWA / NAIGARHI | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1713007006/WC/3 — सोख्‍ता गढडा 1 नग ई जी एस शाला इटारनगॉव कुशहा | Completed | 19000 | 7708 | 2010-02-06 | 2012-04-24
REWA / NAIGARHI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713007006/WC/GIS/28873 — recharge pit nirman ramlal saket ke ghar ke pas gram kusha | Closed | 0 | 0 | 2022-04-10
REWA / NAIGARHI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713007006/WC/GIS/28875 — recharge pit nirman rajesh pyasi ke ghar ke pas gram itarangav | Closed | 0 | 0 | 2022-04-10
REWA / NAIGARHI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713007006/WC/GIS/28878 — recharge pit nirman sriniwas yadav ke ghar ke pas gram rojhaou | Closed | 0 | 0 | 2022-04-10
REWA / NAIGARHI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713007006/WC/GIS/28883 — recharge pit nirman chhotelal pandey ke ghar ke pas gram padengav | Closed | 0 | 0 | 2022-04-10
REWA / NAIGARHI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713007006/WC/GIS/28888 — Reacharge pit nirman lakheswari tiwari ke bhumi me gram kusha | Closed | 0 | 0 | 2022-04-10
REWA / NAIGARHI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713007006/WC/GIS/28892 — recharge pit nirman abhayraj singh ke ghar ke pas gram kusha | Closed | 0 | 0 | 2022-04-10
REWA / NAIGARHI | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1713007006/WC/GIS/28896 — recharge pit nirman ps dharmnagari | Closed | 0 | 0 | 2022-04-10
REWA / NAIGARHI | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1713007006/WH/1 — कूपनिर्माण सिंचाई राजबहोर पुरी धर्मनगरी कुशहा | Completed | 157000 | 185605 | 2007-11-24 | 2008-07-19