## Work List
Exported on: 2026-10-01 20:21:40
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JALDAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
REWA / RAIPUR KARCHULIYAN | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713009086/AV/22012034539581 — गौशाला निर्माण कार्य पोड़ी ईजीएस स्कूल के पास ग्राम पंचायत पंचायत जल्दर | Ongoing | 3804449.17 | 0 | 2020-11-26
REWA / RAIPUR KARCHULIYAN | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1713009086/AV/22012034664498 — शांति धाम निर्माण कार्य ग्राम पंचायत जल्दर | Approved | 39000 | 0 | 2024-10-02
REWA / RAIPUR KARCHULIYAN | 2025-2026 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1713009086/FP/22012034642267 — नाली निर्माण कार्य गजेन्द्र साकेत के घर से नव बधवा की ओर | Ongoing | 57000 | 1908 | 2026-02-05
REWA / RAIPUR KARCHULIYAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1713009086/IF/22012035182080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4620690 | Ongoing | 17370 | 0 | 2023-12-21
REWA / RAIPUR KARCHULIYAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1713009086/IF/22012035206554 — खेत तालाब कार्य प्रवीण पाण्डेय के खेत में | New | 0 | 0 | 2024-01-27
REWA / RAIPUR KARCHULIYAN | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/1144137 — Construction of IAY House -IAY REG. NO. MP1271694 | Approved | 27000 | 0 | 2017-05-19
REWA / RAIPUR KARCHULIYAN | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/1953647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1573887 | Approved | 27000 | 0 | 2019-06-19
REWA / RAIPUR KARCHULIYAN | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/2381967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3456442 | Approved | 27000 | 0 | 2020-04-29
REWA / RAIPUR KARCHULIYAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/3127026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4934089 | Ongoing | 27000 | 0 | 2021-06-30
REWA / RAIPUR KARCHULIYAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/3127354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3755151 | Ongoing | 27000 | 0 | 2021-06-21
REWA / RAIPUR KARCHULIYAN | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/3127792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2168704 | Approved | 27000 | 0 | 2020-10-24
REWA / RAIPUR KARCHULIYAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/3322462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4495030 | Ongoing | 27000 | 0 | 2022-04-18
REWA / RAIPUR KARCHULIYAN | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/3322501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4525445 | Ongoing | 27000 | 0 | 2023-12-11
REWA / RAIPUR KARCHULIYAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/3611515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5491357 | Ongoing | 27000 | 0 | 2022-04-18
REWA / RAIPUR KARCHULIYAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/3633163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4637294 | Approved | 27000 | 0 | 2022-01-14
REWA / RAIPUR KARCHULIYAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/4320776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125459874 | Approved | 27000 | 0 | 2022-06-12
REWA / RAIPUR KARCHULIYAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/4403952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125460541 | Approved | 27000 | 0 | 2022-09-27
REWA / RAIPUR KARCHULIYAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/4710084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125450860 | Physically Completed | 23490 | 0 | 2024-12-03 | 2026-08-16
REWA / RAIPUR KARCHULIYAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/4849371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125443718 | Approved | 27000 | 0 | 2024-09-16
REWA / RAIPUR KARCHULIYAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1713009086/IF/IAY/4849373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125447547 | Approved | 27000 | 0 | 2024-09-16
REWA / RAIPUR KARCHULIYAN | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1713009086/RC/22012034837708 — पी सी सी रोड निर्माण कार्य रामकरण कोल के घर से छोटे लाल कोलके घर तक | Ongoing | 90000 | 1122 | 2025-03-21