## Work List
Exported on: 2026-10-02 08:45:55
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: DHONGA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SINGRAULI / DEOSAR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food Grain Storage Building for Community | Constr of Food Grain storage | 1715005013/AV/22012034587764 — High School Dhonga Me Vriksha Ropan Karya (ma Ki Bagiya) | Ongoing | 394489.84 | 5399.64 | 2023-12-18
SINGRAULI / DEOSAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1715005013/AV/22012034587766 — Madhyamik Shala Chapari Purvi Me Vriksha Ropan Karya ( Ma Ki Bagiya) | Ongoing | 394489.84 | 0 | 2022-09-30
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Unskilled wage for Bio gas plant for community / Construction of Biogas Plant for Community | Bio-gas plant | 1715005013/AV/22012034658461 — High School Dhonga Ke pass Chabutara Nirman | Approved | 63000 | 0 | 2024-04-01
SINGRAULI / DEOSAR | 2025-2026 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural Produce Storage Building for Community | Constr of Food Grain storage | 1715005013/AV/22012034658466 — Shiv mandir mahan Nadi ke pas chabutara Nirman | Ongoing | 63000 | 299.79 | 2025-04-05
SINGRAULI / DEOSAR | 2024-2025 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural Produce Storage Building for Community | Constr of Food Grain storage | 1715005013/AV/22012034662314 — Gram Medh Me shanti Dham Ka Nirman | Ongoing | 334906.09 | 0 | 2025-03-06
SINGRAULI / DEOSAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1715005013/DP/22012034623603 — Pradhanmantri Road Bodiya Me Sadak Kinare Vriksharopan Karya | Ongoing | 453563.17 | 0 | 2024-07-28
SINGRAULI / DEOSAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of Feeder Canal for Community / Construction of Main Canal for Community | Construction of Canal | 1715005013/IC/22012034889544 — Ganga Ke bhumi Par Khet Talab | New | 0 | 0 | 2025-01-25
SINGRAULI / DEOSAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1715005013/IF/22012034640832 — Hitaishi Kapildhara Koop Raghuvir Ke Bhumi Par | Physically Completed | 246126.86 | 0 | 2021-01-17 | 2026-07-14
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035560532 — Ramsundar Ke Bhumi Par Laghu Talab Nirman | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035560562 — Ramlakhan Sahu Ke bhumi Par Laghu talab Nirman | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035567527 — Amit Ke bhumi par laghu Talab nirman | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035567528 — Jagdamba Ke Bhumi Par Laghu Talab Nirman | Approved | 199653.64 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035576308 — Construction of earthen anicut Rajaram ke bhumi par | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035576311 — Construction of earthen anicut Vijay sahu ke bhumi par | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035576313 — Construction of earthen anicut Ramsundar sahu ke bhumi par | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035576316 — Construction of earthen anicut Ramlakhan sahu ke bhumi par | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035576317 — Construction of earthen anicut Amit kumar ke bhumi par | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035576320 — Construction of earthen anicut Jagdamba ke bhumi par | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585750 — Tilakdhari Singh Ke bhumi par laghu Talab | Approved | 199683.95 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585752 — Chhotelal Ke bhumi par Laghu Talab Nirman | Completed | 199765.39 | 0 | 2025-11-25 | 2026-09-26
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585753 — Vijay Ke bhumi Par Laghu Talab | Approved | 199653.64 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585756 — Bhola charan Panika Ke bhumi Par laghu Talab | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585759 — Ramnarayan Ke bhumi Par Laghu Talab | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585760 — Santosh Ke Bhumi Par Laghu Talab | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585762 — Soniya Ke Bhumi Par Laghu Talab | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585764 — Arjun Ke bhumi Par Laghu Talab | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585765 — Durpati Ke Bhumi Par Peripheral bund nirman | New | 0 | 0 | 2025-07-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585768 — Durpati Ke Bhumi Par Peripheral bund nirman | Approved | 0 | 0 | 2025-07-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585769 — Jagnnath Ke Bhumi Par Peripheral bund nirman | Approved | 0 | 0 | 2025-07-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585771 — Ramesh Ke Bhumi Par Peripheral bund nirman | Approved | 0 | 0 | 2025-07-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585773 — Abhimanyu Ke Bhumi Par Peripheral bund nirman | Approved | 0 | 0 | 2025-07-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005013/IF/22012035585774 — Ramsundar Ke Bhumi Par Laghu Talab Nirman | Approved | 0 | 0 | 2025-07-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1715005013/IF/22012035586380 — ek bagiya ma ke name Lalli ke bhumi par | Approved | 0 | 0 | 2025-08-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Bio-drainage Plantation for Individual | Plantation | 1715005013/IF/22012035586482 — Ek Bagiya ma ke name Ramrajiya ke bhumi par | Ongoing | 198583.52 | 0 | 2025-08-28
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1715005013/IF/22012035600591 — ek bagiya ma ke name Anju Devi Ke bhumi Par | Ongoing | 190062.04 | 0 | 2025-09-26
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1715005013/IF/22012035600603 — ek bagiya ma ke name krishna ke bhumi par | Ongoing | 190062.04 | 0 | 2025-09-26
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1715005013/IF/22012035612365 — ek bagiya ma ke name Ramrajiya ke bhumi me | Ongoing | 198583.52 | 0 | 2025-09-25
SINGRAULI / DEOSAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/1949634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1151761 | Ongoing | 28500 | 0 | 2019-07-07
SINGRAULI / DEOSAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/2388227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3991313 | Approved | 28500 | 0 | 2020-04-30
SINGRAULI / DEOSAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/257932 — Construction of IAY House -IAY REG. NO. MP1108061 | Ongoing | 28500 | 0 | 2019-05-12
SINGRAULI / DEOSAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/3195225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5046208 | Approved | 28500 | 0 | 2021-06-26
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/3272567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5148591 | Completed | 24795 | 0 | 2025-09-05 | 2026-07-12
SINGRAULI / DEOSAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/3494808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4871523 | Approved | 28500 | 0 | 2021-12-31
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5092533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132403622 | Completed | 24795 | 0 | 2025-09-04 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152085798 | Completed | 24795 | 0 | 2025-07-27 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152085812 | Completed | 24795 | 0 | 2026-02-18 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152085820 | Ongoing | 28500 | 0 | 2025-08-13
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152085850 | Completed | 24795 | 0 | 2025-08-05 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152070059 | Completed | 24795 | 0 | 2025-08-29 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152070060 | Completed | 24795 | 0 | 2025-08-05 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152067639 | Ongoing | 28500 | 0 | 2025-08-29
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152084572 | Completed | 24795 | 0 | 2025-07-27 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152070462 | Completed | 24795 | 0 | 2025-07-27 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152071612 | Completed | 24795 | 0 | 2025-08-05 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152070800 | Physically Completed | 24795 | 0 | 2025-09-13 | 2026-07-10
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152071555 | Completed | 24795 | 0 | 2025-09-15 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152071558 | Completed | 24795 | 0 | 2025-09-17 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152071762 | Completed | 24795 | 0 | 2025-07-27 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152071763 | Completed | 24795 | 0 | 2026-02-19 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152071764 | Completed | 24795 | 0 | 2025-08-31 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152071765 | Completed | 24795 | 0 | 2025-07-27 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5630956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152087663 | Ongoing | 28500 | 0 | 2025-08-29
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5631336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152085683 | Completed | 24795 | 0 | 2025-07-27 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5631337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152085685 | Completed | 24795 | 0 | 2025-06-28 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5631338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152085690 | Completed | 24795 | 0 | 2025-07-27 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5631466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152086403 | Approved | 28500 | 0 | 2025-04-24
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5631525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152066483 | Physically Completed | 28500 | 1200 | 2025-08-05 | 2026-10-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5631533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152072436 | Physically Completed | 24795 | 0 | 2025-07-27 | 2026-07-05
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5631660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152084944 | Completed | 24795 | 0 | 2025-06-28 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5631765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152082266 | Completed | 24795 | 0 | 2025-08-13 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5631769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152082282 | Completed | 24795 | 0 | 2025-10-13 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5631792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152083571 | Approved | 28500 | 0 | 2025-04-24
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5632355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152071330 | Ongoing | 28500 | 1200 | 2025-08-29
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5652326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152085769 | Physically Completed | 28500 | 0 | 2026-04-07 | 2026-10-01
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5652567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152072439 | Ongoing | 28500 | 0 | 2026-09-23
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5652695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152071262 | Completed | 24795 | 0 | 2025-08-29 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5652696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152067629 | Completed | 24795 | 0 | 2025-08-29 | 2026-07-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5680084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152072083 | Physically Completed | 28500 | 0 | 2025-07-27 | 2026-10-01
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5803758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152070399 | Completed | 24795 | 0 | 2026-02-19 | 2026-09-26
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5829808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152071657 | Ongoing | 28500 | 0 | 2026-05-17
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5879779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152086856 | Approved | 28500 | 0 | 2025-12-11
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5879815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152082130 | Approved | 28500 | 0 | 2025-12-11
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5879840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152081810 | Physically Completed | 28500 | 0 | 2026-04-07 | 2026-10-01
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5880066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152090371 | Ongoing | 28500 | 0 | 2026-04-12
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5880072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152082091 | Ongoing | 28500 | 4500 | 2026-09-09
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5880080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152086877 | Approved | 28500 | 0 | 2025-12-11
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5880110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152082241 | Completed | 24795 | 0 | 2026-03-27 | 2026-07-12
SINGRAULI / DEOSAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/588255 — Construction of IAY House -IAY REG. NO. MP1152638 | Ongoing | 28500 | 0 | 2017-08-07
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5900419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152070750 | Ongoing | 28500 | 0 | 2026-05-17
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5901259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152087653 | Approved | 28500 | 0 | 2025-12-11
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5901550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152087784 | Approved | 28500 | 0 | 2025-12-11
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/5927840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128931481 | Ongoing | 28500 | 0 | 2026-05-17
SINGRAULI / DEOSAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/710319 — Construction of IAY House -IAY REG. NO. MP1564137 | Ongoing | 28500 | 0 | 2018-02-19
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005013/IF/IAY/974413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3661549 | Physically Completed | 24795 | 0 | 2026-04-13 | 2026-07-15
SINGRAULI / DEOSAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1715005013/RC/22012034836024 — Ramanuj Ke Ghar ke Pas Nala Me Puliya Nirman | Physically Completed | 250000 | 32374.14 | 2025-11-23 | 2026-09-17
SINGRAULI / DEOSAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Road for Community | Construction of Road and Culvert | 1715005013/RC/22012034837439 — Abhimanyu ke ghar ke pas dabal ro Hyum pipe puliya nirman | Approved | 0 | 0 | 2024-08-02
SINGRAULI / DEOSAR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1715005013/RC/22012034854032 — Pradhanmantri sadak se guthuriya pahunch marg nirman | Approved | 1999347.51 | 0 | 2026-04-14
SINGRAULI / DEOSAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1715005013/RS/22012035129371 — Pradhanmantri Sadak Se Rammilan Ke Ghar Tak Nali nirman | Approved | 166000 | 0 | 2024-07-01
SINGRAULI / DEOSAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Farm Forestry-Community / Line Plantation of Forestry Trees for Community | Plantation | 1715005013/WC/22012034514041 — Babbu Baiga Ke Ghar Ke Pass Sarwajanik Koop Niraman | Ongoing | 317685.98 | 0 | 2020-01-12
SINGRAULI / DEOSAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1715005013/WC/22012034520813 — Bodiya Me Talab Nirman | Ongoing | 1404942.7 | 25793.4 | 2021-11-16
SINGRAULI / DEOSAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1715005013/WC/22012034875252 — Seetaram Baiga Ke Ghar Ke Pas Chapari Nala Me Check Dem Nirman | Ongoing | 287000 | 0 | 2021-11-28
SINGRAULI / DEOSAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1715005013/WC/22012034990241 — Raghurai Singh Ke ghar ke pas Phal Paudharopan | Ongoing | 411318.19 | 0 | 2022-12-14
SINGRAULI / DEOSAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1715005013/WC/22012034993666 — Bodiya School Me Paudharopan Karya | Ongoing | 411318.19 | 0 | 2022-09-21
SINGRAULI / DEOSAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005013/WC/22012035211457 — Chapari Nala Me Check Dem Nirman | Approved | 0 | 0 | 2024-04-10
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005013/WC/22012035256257 — Piprhwa Nala Chapari me talab Nirman | Ongoing | 1488224.61 | 331126.59 | 2025-06-10
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005013/WC/22012035309324 — Chhote Ke ghar ke pas Nala bandhan | Approved | 0 | 0 | 2025-04-01
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005013/WC/22012035314487 — Ganpat Ke ghar Ke pas Nala Bandhan | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005013/WC/22012035319119 — Ramprasad Ke ghar ke pas Nala bandhan | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005013/WC/22012035319120 — Gram Medh me nala bandhan | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005013/WC/22012035319122 — Padrhwa Tola Nala Me Nala Bandhan | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005013/WC/22012035319123 — Baigan Basti Nala Me Talab Nirman | Approved | 0 | 0 | 2025-05-01
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005013/WC/22012035319124 — Bodrahiya Tola Me Peripheral bund nirman | Ongoing | 402547.65 | 0 | 2025-12-05
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005013/WC/22012035319125 — Gram Medh Me Peripheral bund nirman | Ongoing | 402547.65 | 0 | 2025-12-21
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005013/WC/22012035319126 — Gram Bodiya Me Peripheral bund nirman | Ongoing | 405850.83 | 0 | 2025-12-21
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005013/WC/22012035319127 — Chapari Tola Me Peripheral bund nirman | Ongoing | 409198.99 | 0 | 2025-12-21
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005013/WC/22012035319561 — Adiwashi Basti me chack Dam Nirman | Approved | 315000 | 0 | 2025-04-01
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005013/WC/22012035319958 — Jhapaka me peripheral Bound Nirman | Ongoing | 410106.54 | 0 | 2026-01-13
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1715005013/WC/22012035326451 — Mahulikhadi nala me Gabiyan Kramank 1 | Approved | 0 | 0 | 2025-10-02
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1715005013/WC/22012035326452 — Mahulikhadi nala me Gabiyan Kramank 2 | Approved | 0 | 0 | 2025-10-02
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1715005013/WC/22012035326453 — Mahulikhadi nala me Gabiyan Kramank 3 | Approved | 0 | 0 | 2025-10-02
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1715005013/WC/22012035326454 — Mahulikhadi nala me Gabiyan Kramank 4 | Approved | 0 | 0 | 2025-10-02
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1715005013/WC/22012035326456 — Mahulikhadi nala me Gabiyan Kramank 5 | Approved | 0 | 0 | 2025-10-02
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005013/WC/22012035326458 — Bodiya ma nala bandhan karya | Approved | 0 | 0 | 2025-10-02
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1715005013/WC/VB/22012035330824 — Santosh Ke Ghar Ke Pas Nala Me Gaibiyan Nirman | Approved | 432062.95 | 0 | 2026-07-15
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1715005013/WC/VB/22012035332300 — Sarihwa Nala Me Gaibiyan Kramank 2 | Approved | 0 | 0 | 2026-07-15
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1715005013/WC/VB/22012035332301 — Basahwa Nala Me Boder Check 5 Nag | Approved | 230505.11 | 0 | 2026-07-15
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005013/WC/VB/22012035332302 — Sarihwa Nala Me Boder Check Nirman | Approved | 0 | 0 | 2026-07-15
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1715005013/WC/VB/22012035332303 — Sarihwa Nala Me Gaibiyan Nirman | Approved | 0 | 0 | 2026-07-15
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1715005013/WC/VB/22012035332589 — Prathik Shala Sarapathi Me Rainwater Harvesting | Approved | 0 | 0 | 2026-07-15
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1715005013/WC/VB/22012035332590 — Aganwadi Kendra Kramank 3 Me Rainwater Harvesting | Approved | 0 | 0 | 2026-07-15
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1715005013/WC/VB/22012035332591 — Shashkiy Uchit Mulya Ki Dukan Bodiya Me Rainwater Harvesting | Approved | 0 | 0 | 2026-07-15