## Work List
Exported on: 2026-10-25 17:03:33
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BOORHADAND
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SINGRAULI / DEOSAR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1715005028/AV/22012034666927 — kitinihawa nala me puliya nirman | New | 0 | 0 | 2025-04-02
SINGRAULI / DEOSAR | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1715005028/AV/22012034666928 — kitinihawa nala me puliya nirman | New | 0 | 0 | 2025-04-02
SINGRAULI / DEOSAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1715005028/DP/22012034621921 — khairabada chhiwlahiya vriksharopan | Approved | 995197.08 | 0 | 2024-06-18
SINGRAULI / DEOSAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1715005028/IF/22012034522421 — ramjank sake ke khet me koop nriman | Physically Completed | 234458.57 | 0 | 2020-01-11 | 2026-07-13
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005028/IF/22012035230333 — ramraj patel ke khet me laghu talab | Approved | 294508.67 | 0 | 2024-04-02
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1715005028/IF/22012035230366 — ramraj ke khet me koop nirman | Approved | 0 | 0 | 2024-04-02
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005028/IF/22012035315414 — shukhapatiya ke khet me laghu talab | Approved | 0 | 0 | 2024-04-02
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1715005028/IF/22012035531726 — Ramlallu patel ke khet me khet talab | Approved | 87848.19 | 0 | 2025-04-14
SINGRAULI / DEOSAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/2963896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4765981 | Ongoing | 28500 | 0 | 2021-07-11
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/3054204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4066121 | Ongoing | 28500 | 0 | 2025-08-05
SINGRAULI / DEOSAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/3055753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5369948 | Ongoing | 28500 | 0 | 2021-08-23
SINGRAULI / DEOSAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/3056540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5169128 | Ongoing | 28500 | 0 | 2021-07-11
SINGRAULI / DEOSAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/3214544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4765739 | Approved | 28500 | 0 | 2021-06-29
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/3431633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5298512 | Ongoing | 28500 | 0 | 2026-06-04
SINGRAULI / DEOSAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/3481150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2044567 | Approved | 28500 | 0 | 2021-12-30
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/3575670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5279629 | Ongoing | 28500 | 0 | 2026-06-04
SINGRAULI / DEOSAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4145690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123275942 | Ongoing | 28500 | 0 | 2022-08-16
SINGRAULI / DEOSAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4147988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132811519 | Approved | 28500 | 0 | 2022-05-24
SINGRAULI / DEOSAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4215136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132165568 | Approved | 28500 | 0 | 2022-06-14
SINGRAULI / DEOSAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4235523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131060867 | Approved | 28500 | 0 | 2022-06-14
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4717555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130217010 | Ongoing | 28500 | 0 | 2024-10-08
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4717798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131059444 | Physically Completed | 24795 | 0 | 2025-02-14 | 2026-07-13
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4828732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130217183 | Physically Completed | 24795 | 0 | 2025-02-07 | 2026-07-13
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4828881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129183508 | Ongoing | 28500 | 0 | 2025-08-05
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4828882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129184181 | Physically Completed | 24795 | 0 | 2025-11-29 | 2026-07-13
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4830915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132457253 | Approved | 28500 | 0 | 2024-09-19
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4896733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152039069 | Ongoing | 28500 | 0 | 2025-03-15
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4896734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152039070 | Approved | 28500 | 0 | 2025-01-17
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4896735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152039072 | Physically Completed | 24795 | 0 | 2025-03-21 | 2026-07-13
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4896748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152039109 | Approved | 28500 | 0 | 2025-01-17
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4896792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152039297 | Ongoing | 28500 | 0 | 2025-03-21
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4896996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040132 | Ongoing | 28500 | 0 | 2025-03-15
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4897525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040214 | Ongoing | 28500 | 0 | 2025-08-07
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4897526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040215 | Ongoing | 28500 | 0 | 2025-08-07
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4897530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040224 | Ongoing | 28500 | 0 | 2025-03-21
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4897532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040228 | Ongoing | 28500 | 0 | 2025-03-21
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4897533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040236 | Approved | 28500 | 0 | 2025-01-17
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4897535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040263 | Physically Completed | 24795 | 0 | 2025-03-15 | 2026-07-26
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/4897581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040464 | Ongoing | 28500 | 0 | 2026-01-13
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5111238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152037872 | Physically Completed | 24795 | 0 | 2026-01-13 | 2026-07-26
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5111267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152039049 | Ongoing | 28500 | 0 | 2025-06-14
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5111270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152039074 | Ongoing | 28500 | 0 | 2025-09-02
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5111276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152039295 | Physically Completed | 24795 | 0 | 2026-01-13 | 2026-07-26
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5111358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040918 | Ongoing | 28500 | 0 | 2025-07-14
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5111360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040957 | Ongoing | 28500 | 0 | 2025-10-05
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5111364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040964 | Ongoing | 28500 | 0 | 2025-08-05
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5111367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040969 | Ongoing | 28500 | 0 | 2025-09-26
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5111369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041008 | Ongoing | 28500 | 0 | 2025-09-02
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5111370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041009 | Physically Completed | 24795 | 0 | 2025-11-13 | 2026-07-13
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5111372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041030 | Ongoing | 28500 | 0 | 2025-11-13
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5111373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152041031 | Approved | 28500 | 0 | 2025-01-22
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5630202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040244 | Approved | 28500 | 0 | 2025-01-17
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5630203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040251 | Approved | 28500 | 0 | 2025-01-17
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5630204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040258 | Ongoing | 28500 | 0 | 2026-06-04
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5630312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152039071 | Ongoing | 28500 | 0 | 2025-07-14
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5631037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132457380 | Approved | 28500 | 0 | 2024-09-18
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5631576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040966 | Ongoing | 28500 | 0 | 2025-09-26
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5632028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040265 | Ongoing | 28500 | 0 | 2026-05-15
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5652017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123744550 | Ongoing | 28500 | 0 | 2026-04-08
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5652221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122694252 | Approved | 28500 | 0 | 2025-05-05
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5876359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040266 | Approved | 28500 | 0 | 2025-12-11
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/5879923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040979 | Ongoing | 28500 | 0 | 2026-05-07
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6135804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130217055 | Approved | 28500 | 0 | 2026-02-24
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6135805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130217075 | Approved | 28500 | 0 | 2026-02-24
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6135806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130217134 | Ongoing | 28500 | 0 | 2026-05-07
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6145461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124600876 | Ongoing | 28500 | 0 | 2026-05-07
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6150069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123743100 | Ongoing | 28500 | 0 | 2026-05-07
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6150072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123744027 | Ongoing | 28500 | 0 | 2026-05-07
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6152412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123743550 | Ongoing | 28500 | 0 | 2026-05-07
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6152991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124593623 | Ongoing | 28500 | 10800 | 2026-05-07
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6159245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132811347 | Ongoing | 28500 | 9000 | 2026-05-07
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6160509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123739849 | Ongoing | 28500 | 0 | 2026-05-07
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6165348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123203971 | Ongoing | 28500 | 9000 | 2026-09-05
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6165741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124594670 | Approved | 28500 | 0 | 2026-02-24
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6165742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124595562 | Approved | 28500 | 0 | 2026-02-24
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6171658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123740263 | Ongoing | 28500 | 0 | 2026-05-07
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6333694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123744981 | Approved | 28500 | 0 | 2026-02-24
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6344937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130216979 | Approved | 28500 | 0 | 2026-02-24
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6352402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152040956 | Approved | 28500 | 0 | 2026-04-29
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/6353080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152039330 | Approved | 28500 | 0 | 2025-12-11
SINGRAULI / DEOSAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1715005028/IF/IAY/656028 — Construction of IAY House -IAY REG. NO. MP1183568 | Ongoing | 28500 | 0 | 2017-10-21
SINGRAULI / DEOSAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1715005028/RC/22012034836298 — baighaila aadiwashi tola se kitinihwa aagnwadi tak shudar sadak niraman | Approved | 0 | 0 | 2025-01-25
SINGRAULI / DEOSAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Road for Community | Construction of Road and Culvert | 1715005028/RC/22012034850625 — bhat tola pahuch marg me puliya nirman | Approved | 377000 | 0 | 2025-07-16
SINGRAULI / DEOSAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1715005028/WC/22012035248393 — baiga basthi gadai tola me sarwajanik koop | Approved | 0 | 0 | 2025-01-24
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005028/WC/22012035248446 — jogadhahwa me sarwajanik koop | Physically Completed | 265289.91 | 0 | 2025-05-02 | 2026-07-13
SINGRAULI / DEOSAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1715005028/WC/22012035248447 — chotelal patel ke ghar ke pass sarwajanik koop | Approved | 223556.15 | 0 | 2025-01-24
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1715005028/WC/22012035248451 — baiga bashti gadai tola me sarwajanik koop nirman | Physically Completed | 267886.01 | 0 | 2025-05-06 | 2026-07-13
SINGRAULI / DEOSAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005028/WC/22012035249366 — budhadand hardidand tola me talab nirman | Approved | 0 | 0 | 2025-01-25
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005028/WC/22012035252521 — budhadand me ramraj ke ghar ke pass sarwajnik koop | Physically Completed | 268258.08 | 0 | 2025-05-09 | 2026-07-13
SINGRAULI / DEOSAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005028/WC/22012035254417 — budhadand harijan bashti ke pass talab niraman | Approved | 0 | 0 | 2025-01-25
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005028/WC/22012035260761 — budhadand joba me talab niraman | Physically Completed | 1497758.49 | 0 | 2025-05-09 | 2026-07-13
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005028/WC/22012035260763 — budhadand baghaila me talab nirman | Physically Completed | 997302.09 | 0 | 2025-06-15 | 2026-07-13
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1715005028/WC/22012035295955 — kitab ke khet me khet talab | Approved | 0 | 0 | 2025-04-14
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005028/WC/22012035308302 — baighla me semra nala ke pass laghu talab | Approved | 0 | 0 | 2025-04-14
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1715005028/WC/22012035308309 — Lalbahadur patel ke khet ke pass koop nirman | Ongoing | 246185.5 | 0 | 2025-06-05
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005028/WC/22012035322851 — budhadand shahu tola me talab nirman | Approved | 0 | 0 | 2025-11-02
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005028/WC/22012035322854 — budhadand kitinihwa me talab nirman | Approved | 0 | 0 | 2025-11-02
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005028/WC/22012035322858 — khairabada chilahiya me talab nirman | Approved | 0 | 0 | 2025-11-02
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005028/WC/22012035322905 — Jogdahwa me thalab nirman | Ongoing | 986612.15 | 5997.76 | 2025-12-22
SINGRAULI / DEOSAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1715005028/WC/22012035322906 — Khairabada bhasloti me talab nirman | Approved | 0 | 0 | 2025-11-02
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035329790 — Khairabada Jogdahwa Nala me boldar Chek 01 | New | 0 | 0 | 2026-07-25
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035329812 — Khairabad chilhiya jogdhwa Nala me chak | Approved | 0 | 0 | 2026-07-15
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035329815 — Khairabad chilhiya jogdhwa Nala me chak 01 | New | 0 | 0 | 2026-07-15
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035329846 — khairabada chilahiya me bodar chek 01 | Ongoing | 57482.08 | 1499.95 | 2026-09-03
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035329850 — khairabada chilahiya me bodar chek 02 | Ongoing | 56801.3 | 1499.95 | 2026-09-03
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035329852 — khairabada chilahiya me bodar chek 03 | Ongoing | 54081.62 | 1640 | 2026-09-17
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035329853 — khairabada chilahiya me bodar chek 04 | New | 0 | 0 | 2026-07-10
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035330095 — khairabada chilahiya me bodar chek 04 | Ongoing | 56892.14 | 1600 | 2026-09-17
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035330096 — khairabada chilahiya me bodar chek 05 | Approved | 54081.62 | 0 | 2026-07-10
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035330097 — khairabada jogdhwa me bodar chek 02 | Approved | 0 | 0 | 2026-07-10
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035330098 — budhadand bhat tola nala me Gabian structure | Approved | 232136.3 | 0 | 2026-07-10
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035330105 — budhadand hradidand nala me Gabian structure | Approved | 0 | 0 | 2026-07-10
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035330106 — budhadand bhat tola nala me Gabian structure 01 | Approved | 0 | 0 | 2026-07-10
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035330107 — budhadand kashihwa nala me Gabian structure | Approved | 0 | 0 | 2026-07-10
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035330548 — Budhadand kitinihwa tolla me Gabin structure | Approved | 199759.64 | 0 | 2026-07-02
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035334444 — budhadand baghaila me gaibin structure | Ongoing | 462537.16 | 36599.58 | 2026-09-22
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035334445 — budhadand joba me gaibin structure | Approved | 453193.47 | 0 | 2026-08-16
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1715005028/WC/VB/22012035334446 — budhadand kashihwa nala me gaibin structure | Ongoing | 462537.16 | 23040 | 2026-10-07
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1715005028/WC/VB/22012035334840 — budhadand gram khairabada me gaibin structure | Approved | 0 | 0 | 2026-08-16
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1715005028/WC/VB/22012035334841 — khairabada jogdhwa me gaibin structure | Approved | 0 | 0 | 2026-08-16
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1715005028/WC/VB/22012035334842 — budhadand bhat adiwashi tola gaibin structure | Approved | 0 | 0 | 2026-08-16
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1715005028/WC/VB/22012035334843 — budhadand kitinihwa shahu tola me gaibin structure | Approved | 0 | 0 | 2026-08-16