## Work List
Exported on: 2026-10-23 23:23:34
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PURAIL
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SINGRAULI / DEOSAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/22012034952316 — PMAY Niraman Ramlallu Kol | Completed | 18400 | 0 | 2022-05-07 | 2026-07-14
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005052/IF/22012035441516 — JGSA Kailash S/O Rajendra Prasad Gupta ke bhumi par khet talab nirman | Approved | 0 | 0 | 2025-04-14
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1715005052/IF/22012035611894 — Ek Bagiya maa ke naam Shanti Gupta MP-15-0050-52-001/412-B | Ongoing | 190062.04 | 13250 | 2025-09-30
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1715005052/IF/22012035661767 — Dade Prasad s/o Ramadheen bais ke niji bhumi par nala bandhan | Approved | 0 | 0 | 2026-01-24
SINGRAULI / DEOSAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/3090317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4196535 | Ongoing | 28500 | 0 | 2021-06-04
SINGRAULI / DEOSAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/3098794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4927933 | Ongoing | 28500 | 0 | 2021-06-26
SINGRAULI / DEOSAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/3333786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4522313 | Ongoing | 28500 | 0 | 2022-04-22
SINGRAULI / DEOSAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/3333809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4533368 | Ongoing | 28500 | 0 | 2022-04-22
SINGRAULI / DEOSAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/3903726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148215043 | Ongoing | 28500 | 0 | 2022-06-13
SINGRAULI / DEOSAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/408010 — Construction of IAY House -IAY REG. NO. MP1245340 | Approved | 28500 | 0 | 2022-04-05
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/4657159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147793433 | Ongoing | 28500 | 0 | 2025-04-09
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/4659694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148207012 | Approved | 28500 | 0 | 2024-09-09
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/4837646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148377020 | Ongoing | 28500 | 0 | 2024-11-16
SINGRAULI / DEOSAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5097931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146229291 | Approved | 28500 | 0 | 2025-02-11
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5099534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147194682 | Ongoing | 28500 | 6000 | 2025-06-17
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5099883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147368496 | Ongoing | 28500 | 8100 | 2026-09-23
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5099965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147386153 | Ongoing | 28500 | 0 | 2025-07-02
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5100111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147545081 | Ongoing | 28500 | 0 | 2025-05-02
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5100115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147550858 | Completed | 28500 | 10500 | 2025-06-17 | 2026-10-16
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5100641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147721207 | Ongoing | 28500 | 12330 | 2026-02-03
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5100741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147780453 | Completed | 24795 | 0 | 2026-02-03 | 2026-10-16
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5100887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147812734 | Ongoing | 28500 | 0 | 2025-06-17
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5101665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148180004 | Ongoing | 28500 | 0 | 2025-07-02
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5102087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148374415 | Ongoing | 28500 | 0 | 2025-08-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5102088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148374802 | Ongoing | 28500 | 0 | 2025-08-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5102089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148375057 | Completed | 28500 | 5165 | 2025-04-09 | 2026-10-16
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5102091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148375822 | Ongoing | 28500 | 0 | 2025-07-29
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5102094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148376883 | Ongoing | 28500 | 8100 | 2026-09-23
SINGRAULI / DEOSAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5102099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148378628 | Ongoing | 28500 | 4500 | 2026-09-23
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5102100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148378805 | Ongoing | 28500 | 0 | 2025-08-12
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5104081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149241740 | Ongoing | 28500 | 0 | 2025-04-17
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5104103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149254778 | Ongoing | 28500 | 0 | 2025-04-09
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5104104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149254849 | Ongoing | 28500 | 0 | 2025-04-09
SINGRAULI / DEOSAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1715005052/IF/IAY/5652375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147744204 | Completed | 24795 | 0 | 2026-02-27 | 2026-07-17
SINGRAULI / DEOSAR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1715005052/RC/VB/YD/22012034855022 — Ramnaresh ke khet se Kamlesh kushwaha ke ghar tak pcc nirman | Approved | 0 | 0 | 2026-08-15
SINGRAULI / DEOSAR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1715005052/RS/VB/YD/22012035140588 — GOVT PS school ke pas compost pit ka nirman | Approved | 37740.24 | 0 | 2026-08-15
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1715005052/WC/VB/22012035329958 — Devsthan Handpamp ke pas Recharge Pit ka Nirman | Approved | 28570.85 | 0 | 2026-04-14
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1715005052/WC/VB/22012035329962 — Pds Bhavan ke pas Rain Water Harvesting Structure ka Nirman | Approved | 34995.49 | 0 | 2026-04-14
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1715005052/WC/VB/22012035331776 — Chhotelal Basor ke ghar ke pas Hand Pump me Recharge Pit ka nirman | Approved | 28570.85 | 0 | 2026-06-14
SINGRAULI / DEOSAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1715005052/WC/VB/YD/22012035336684 — PDS bhawan ke pas rain wather harwesting ka nirman | Approved | 36484.75 | 0 | 2026-08-15
SINGRAULI / DEOSAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1715005/DP/22012034577182 — बाँस बृक्षारोपण बड़कीगांव पी -665 रकवा 25 हैक्टेयर | Ongoing | 5399000 | 0 | 2023-06-12