## Work List
Exported on: 2026-10-15 16:54:21
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KARJU
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1716004078/IF/22012035481665 — JGSA 2025 Dugwell Recharge कूप रिचार्ज शंकरलाल नारायण ग्राम करजू | Approved | 0 | 0 | 2025-05-04
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1716004078/IF/22012035547742 — JGSA 2025 खेत तालाब निर्माण कला बाई रुघनाथ जी ग्राम करजू | Ongoing | 55865.38 | 0 | 2025-06-01
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1716004078/IF/22012035555374 — JGSA 2025 खेत तालाब निर्माण अंबालाल पिता मांगीलाल ग्राम करजू | Ongoing | 147621.16 | 0 | 2025-08-23
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1716004078/IF/22012035573244 — JGSA 2025 कूप रिचार्ज छगनलाल पिता शोभाराम जी | Approved | 25899.46 | 0 | 2025-06-18
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1716004078/IF/22012035573250 — JGSA 2025 कूप रिचार्ज सुमित्रा बाई बलवंत सिंह | Approved | 25899.46 | 0 | 2025-06-18
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716004078/IF/22012035591569 — एक बगिया मॉ के नाम कविता पति दिनेश पाटीदार | Approved | 229028.36 | 0 | 2025-08-01
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/4754801 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118309353 | Physically Completed | 27000 | 0 | 2025-11-29 | 2026-08-30
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/4757901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118785895 | Approved | 27000 | 0 | 2024-09-30
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/4758875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119314840 | Ongoing | 27000 | 0 | 2025-05-13
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/4758878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119315722 | Approved | 27000 | 0 | 2024-09-30
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/4758883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119316852 | Physically Completed | 27000 | 0 | 2025-05-26 | 2026-09-27
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/4759638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119317361 | Ongoing | 27000 | 0 | 2024-11-19
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/4759651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119320599 | Ongoing | 27000 | 0 | 2024-11-12
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/4871062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118750646 | Physically Completed | 27000 | 0 | 2025-03-12 | 2026-09-20
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5260061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125563175 | Approved | 27000 | 0 | 2025-02-27
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5269833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125802467 | Approved | 27000 | 0 | 2025-02-27
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5279537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126806941 | Physically Completed | 27000 | 15600 | 2026-07-28 | 2026-09-27
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5285548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126481437 | Ongoing | 27000 | 16800 | 2026-09-12
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5290140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126524116 | Approved | 27000 | 0 | 2025-02-27
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5297386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118504502 | Ongoing | 27000 | 8400 | 2026-09-28
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5298763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126541853 | Ongoing | 27000 | 21000 | 2026-08-20
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5308459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119311582 | Approved | 27000 | 0 | 2025-02-28
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5315575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127145290 | Physically Completed | 27000 | 6000 | 2025-05-05 | 2026-10-11
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5328353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126527833 | Ongoing | 27000 | 0 | 2026-01-24
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5330461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118757103 | Ongoing | 27000 | 7800 | 2026-09-15
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5331150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127116250 | Ongoing | 27000 | 16200 | 2026-09-14
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5339287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126520137 | Approved | 27000 | 0 | 2025-02-27
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5342266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118750914 | Ongoing | 27000 | 3900 | 2026-07-09
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5392077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121644975 | Approved | 27000 | 0 | 2025-02-27
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5396775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119841453 | Ongoing | 27000 | 0 | 2026-10-11
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5542688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119322430 | Ongoing | 27000 | 0 | 2025-09-18
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5547844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126472889 | Ongoing | 27000 | 3600 | 2026-09-29
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5583742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118750530 | Approved | 27000 | 0 | 2025-02-28
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5807345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119319824 | Ongoing | 27000 | 3600 | 2026-10-05
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5807386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126483999 | Approved | 27000 | 0 | 2025-02-27
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5807417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121643322 | Physically Completed | 27000 | 0 | 2025-09-18 | 2026-08-30
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5807702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127115456 | Ongoing | 27000 | 7800 | 2026-08-31
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5807771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119321458 | Ongoing | 27000 | 5700 | 2026-09-25
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5807828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126808447 | Physically Completed | 27000 | 0 | 2025-09-24 | 2026-08-30
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5808188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127142673 | Ongoing | 27000 | 0 | 2025-09-18
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5808277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118310116 | Ongoing | 27000 | 15600 | 2026-09-15
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/5850229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126470647 | Ongoing | 27000 | 0 | 2026-05-16
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/6243530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118751221 | Ongoing | 27000 | 19500 | 2026-07-04
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/6243531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118751848 | Physically Completed | 27000 | 21600 | 2026-07-09 | 2026-09-20
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/6243767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125797234 | Ongoing | 27000 | 0 | 2026-10-14
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/6243825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119082663 | Ongoing | 27000 | 0 | 2026-10-11
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/6243831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119315051 | Ongoing | 27000 | 8400 | 2026-09-12
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/6243858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126474095 | Ongoing | 27000 | 3000 | 2026-10-01
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/6243975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123434150 | Approved | 27000 | 0 | 2025-02-27
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/6244092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126807670 | Approved | 27000 | 0 | 2025-02-27
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/6246466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102246667 | Ongoing | 27000 | 0 | 2026-10-11
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/6261718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124091886 | Approved | 27000 | 0 | 2025-02-27
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004078/IF/IAY/6265095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126475722 | Approved | 27000 | 0 | 2025-02-27
MANDSAUR / MANDSAUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1716004078/RC/22012034851071 — सीसी रोड निर्माण मनरेगा राज्‍य स ग्राम करजू में मुख्‍य सडक करजू से मगरा माता मंदिर मुख्‍य द्वार तक | Ongoing | 124000 | 0 | 2025-12-14
MANDSAUR / MANDSAUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1716004078/WC/22012035215656 — डग आउट पोंड निर्माण करजू आकोदडा की सीमा के पास मगरा माताजी 202425 | Approved | 597874.75 | 0 | 2024-07-02
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1716004078/WC/22012035265701 — JGSA 2025 Dugwell Recharge शासकीय कुप झेल मे ग्राम करजू | Approved | 25899.46 | 0 | 2025-04-15
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1716004078/WC/22012035286807 — JGSA 2025 Dugwell Recharge कूप रिचार्ज शासकीय कूप आकोदडा मार्ग के पास ग्राम करजू | Approved | 25899.46 | 0 | 2025-04-25
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1716004078/WC/22012035286809 — JGSA 2025 Dugwell Recharge कूप रिचार्ज शासकीय कूप चौसला मार्ग के पास ग्राम करजू | Approved | 25899.46 | 0 | 2025-04-25
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1716004078/WC/22012035299283 — JGSA 2025 Dugwell Recharge कूप रिचार्ज शासकीय कूप नई आबादी ग्राम करजू | Approved | 25899.46 | 0 | 2025-05-04
MANDSAUR / MANDSAUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1716004078/WC/VB/YD/22012035336477 — Roof Water harvesting Patwari Office Karju | Approved | 0 | 0 | 2026-04-14