## Work List
Exported on: 2026-10-21 06:13:21
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PATELA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDSAUR / MANDSAUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1716004088/DP/22012034555005 — निर्मल निर कुप निर्मण सेमलिया रास्ते पर खदान मे | Ongoing | 591511.94 | 0 | 2022-05-18
MANDSAUR / MANDSAUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1716004088/DP/22012034620168 — वृक्षारोपण कार्य ग्राम पटेला मगरा पर सगस बावजी के पास 202425 | Ongoing | 463755.17 | 0 | 2024-10-01
MANDSAUR / MANDSAUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1716004088/DP/22012034620169 — व़क्षारोपण कार्य लालाखेडा खेल मैदान व शमशान परिसर 202425 | Ongoing | 463755.17 | 0 | 2024-09-03
MANDSAUR / MANDSAUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716004088/IF/22012035104945 — निजी फलो उद्यान भागीरथ - धुरा 2023-24 | Physically Completed | 161000 | 0 | 2023-10-06 | 2026-07-06
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716004088/IF/22012035252004 — निजी फलोद्यान सत्यनारायण - बालमुकुन्द ग्राम लालाखेडा 2024-25 | Ongoing | 140000 | 0 | 2024-08-06
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716004088/IF/22012035252006 — निजी फलोद्यान रामकुंवरबाई - रूपचंद ग्राम लालाखेडा 2024-25 | Approved | 140000 | 0 | 2024-06-08
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1716004088/IF/22012035489211 — JGSA 2025 Dugwell Recharge कूप रिचार्ज रामदयाल मगनीराम | Approved | 25899.46 | 0 | 2025-05-07
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1716004088/IF/22012035489243 — JGSA 2025 Dugwell Recharge कूप रिचार्ज मांगीलाल हरिराम | Ongoing | 25899.46 | 0 | 2025-05-22
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1716004088/IF/22012035489258 — JGSA 2025 Dugwell Recharge कूप रिचार्ज रामनिवास कँवरलाल | New | 0 | 0 | 2025-05-07
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1716004088/IF/22012035489262 — JGSA 2025 Dugwell Recharge कूप रिचार्ज रामनिवास कँवरलाल | Approved | 25899.46 | 0 | 2025-05-07
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1716004088/IF/22012035575883 — JGSA 2025 Dugwell Recharge शांतिबाई बालूराम | Approved | 0 | 0 | 2025-06-22
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1716004088/IF/22012035606191 — एक बगिया मॉ के नाम बादाम बाई पति भवंरलाल | Ongoing | 229028.36 | 0 | 2025-09-13
MANDSAUR / MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/3814948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118578438 | Approved | 27000 | 0 | 2022-05-03
MANDSAUR / MANDSAUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/3816359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121697821 | Approved | 27000 | 0 | 2022-05-03
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/4611309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125584168 | Ongoing | 27000 | 0 | 2025-08-25
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/4782856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126128593 | Ongoing | 27000 | 0 | 2024-11-26
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/5344975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118578358 | Physically Completed | 23490 | 23400 | 2026-07-26 | 2026-08-23
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/5344979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118578491 | Approved | 27000 | 0 | 2025-03-07
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/5345479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125587733 | Physically Completed | 27000 | 23400 | 2026-07-09 | 2026-08-30
MANDSAUR / MANDSAUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/5346896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126579912 | Ongoing | 27000 | 16800 | 2026-09-18
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/5347039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126669972 | Approved | 27000 | 0 | 2025-03-07
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/5347750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126108609 | Approved | 27000 | 0 | 2025-03-07
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/5348313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121697355 | Physically Completed | 23490 | 0 | 2025-12-17 | 2026-08-16
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/5351121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125601760 | Physically Completed | 23490 | 0 | 2025-08-25 | 2026-08-02
MANDSAUR / MANDSAUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/5351497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126481769 | Physically Completed | 27000 | 14400 | 2025-08-25 | 2026-09-06
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/5353398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149666325 | Approved | 27000 | 0 | 2025-03-07
MANDSAUR / MANDSAUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716004088/IF/IAY/5458261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118578418 | Approved | 27000 | 0 | 2025-03-07
MANDSAUR / MANDSAUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1716004088/RC/22012034658518 — सीमेंट कांक्रीट रोड व नाली निर्माण 15वि+मनरेगा ग्राम पटेला में अशोक के घर से विक्रम के घर तक | Ongoing | 13000 | 0 | 2023-10-07
MANDSAUR / MANDSAUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1716004088/RC/22012034849164 — सिमेंट कांक्रीट चौक निर्माण मनरेगा एंव 5 वा वित्‍त ग्राम पटेला में बालाजी मंदिर के सामने | Approved | 25000 | 0 | 2025-08-01
MANDSAUR / MANDSAUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1716004088/RC/22012034849165 — सीसी चौक निर्माण मनरेगा एंव 5 वा वित्त ग्राम पटेला में नई आबादी बालाजी मंदिर के सामने | Approved | 14000 | 0 | 2025-08-01
MANDSAUR / MANDSAUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1716004088/RC/22012034849166 — सीसी चौक निर्माण मनरेगा एंव 5 वा वित्त ग्राम पटेला में देवनारायण मंदिर के सामने | Approved | 34000 | 0 | 2025-08-01
MANDSAUR / MANDSAUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1716004088/RC/22012034849170 — सीसी रोड निर्माण मनरेगा एंव ५ वा वित्‍त ग्राम पटेला में गोपाल धोबी के मकान से दौलतराम के मकान की ओर | Approved | 28000 | 0 | 2025-08-01
MANDSAUR / MANDSAUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1716004088/WC/22012035165112 — डगआउट पोंड निर्माण | New | 0 | 0 | 2024-04-01
MANDSAUR / MANDSAUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1716004088/WC/22012035213687 — डग आउट पोंड निर्माण ग्राम लालाखेडा से रिछालालमंहा मार्ग कांकड के पास 202425 | Approved | 661220.62 | 0 | 2024-06-26
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1716004088/WC/22012035299190 — JGSA 2025 Dugwell Recharge Nirmal nil kup shamshan parisar patela | Ongoing | 25899.46 | 0 | 2025-05-23
MANDSAUR / MANDSAUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1716004088/WC/22012035299197 — JGSA 2025 Dugwell Recharge Nirmal nir khadan ke pass patela | Approved | 25899.46 | 0 | 2025-05-04
MANDSAUR / MANDSAUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1716004088/WH/22012034910003 — स्टॉपडेम जीर्णोद्धार कार्य (15वावित्त+मनरेगा) भंवरी कुआं के पास ग्राम पटेला | Ongoing | 135000 | 0 | 2022-03-07