## Work List
Exported on: 2026-10-09 12:54:05
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: DIPAKHEDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MANDSAUR / SITAMAU | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1716005057/AV/22012034629712 — मुक्तिधाम निर्माण ग्राम दीपाखेड़ा आम्बा कुआ पर | Ongoing | 226087.68 | 0 | 2023-10-01
MANDSAUR / SITAMAU | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1716005057/DP/22012034605953 — वसुधा वंदन अमृत वाटिका तालाब के पास 2023-24 | Ongoing | 55847.4 | 0 | 2023-09-30
MANDSAUR / SITAMAU | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1716005057/DP/22012034621821 — JETPURA BALAJI KE PAS VRIKSHAROPAN KARY DEEPAKHEDA | Approved | 445538.87 | 0 | 2024-04-14
MANDSAUR / SITAMAU | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1716005057/IF/22012034566923 — कपिलधारा सह खेत तालाब मांगीलाल शंकरलाल व जगदीश संयुक्त | Ongoing | 242453.87 | 0 | 2021-01-31
MANDSAUR / SITAMAU | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1716005057/IF/22012034583014 — Niji khet me nandan faloudhyan bhanwarlal magan | Ongoing | 143000 | 0 | 2020-07-13
MANDSAUR / SITAMAU | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1716005057/IF/22012034816444 — CTR खेत तालाब भगवान सिंह केशर सिंह | Ongoing | 338902.57 | 0 | 2021-07-03
MANDSAUR / SITAMAU | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1716005057/IF/22012034816450 — CTR खेत तालाब भारतसिंह शिवसिंह | Ongoing | 338902.57 | 0 | 2021-07-03
MANDSAUR / SITAMAU | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1716005057/IF/22012035128107 — NANDAN FLODHYAN BALURAM LACHHIRAM DEEPAKHEDA | Ongoing | 145000 | 0 | 2023-07-26
MANDSAUR / SITAMAU | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1716005057/IF/22012035513944 — डग विल रिचार्ज रामकन्या बाई हरिराम | Approved | 25899.46 | 0 | 2025-04-14
MANDSAUR / SITAMAU | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1716005057/IF/22012035515063 — डग वेल रिचार्ज नाथी बाई सुखराम | Ongoing | 25899.46 | 0 | 2025-05-22
MANDSAUR / SITAMAU | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1716005057/IF/22012035515084 — डग विल रिचार्ज पीट गीता बाई जुझार | Ongoing | 25899.46 | 0 | 2025-05-20
MANDSAUR / SITAMAU | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1716005057/IF/22012035515092 — डग विल रिचार्ज बालू राम लचीराम | Ongoing | 25899.46 | 0 | 2025-05-18
MANDSAUR / SITAMAU | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1716005057/IF/22012035515112 — डग वेल रिचार्ज कस्तूरी बाई शवा जी | Ongoing | 25899.46 | 0 | 2025-05-20
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4569683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117020067 | Ongoing | 27000 | 0 | 2024-11-29
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4571259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117043247 | Ongoing | 27000 | 0 | 2024-10-25
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4577979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118609589 | Ongoing | 27000 | 0 | 2024-10-18
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4583487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120322484 | Ongoing | 27000 | 0 | 2024-10-18
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4583981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119291333 | Ongoing | 27000 | 0 | 2025-02-21
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4600840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122706868 | Ongoing | 27000 | 0 | 2024-10-18
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4604118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124068497 | Physically Completed | 23490 | 0 | 2025-01-31 | 2026-08-16
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4604137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124072970 | Ongoing | 27000 | 0 | 2024-10-18
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4615448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126287457 | Ongoing | 27000 | 0 | 2024-10-03
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4758234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118598611 | Ongoing | 27000 | 0 | 2025-01-17
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4758711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118864412 | Ongoing | 27000 | 0 | 2024-11-08
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4776359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125857348 | Ongoing | 27000 | 8400 | 2025-02-14
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4777497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126378746 | Ongoing | 27000 | 0 | 2024-12-27
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/4859305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117022268 | Ongoing | 27000 | 0 | 2025-02-21
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5157572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116549174 | Physically Completed | 23490 | 0 | 2026-03-11 | 2026-08-23
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5158962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123033883 | Ongoing | 27000 | 0 | 2025-08-08
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5162987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125274380 | Ongoing | 27000 | 0 | 2026-04-20
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5163139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118616580 | Ongoing | 27000 | 0 | 2025-04-11
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5182371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125541009 | Ongoing | 27000 | 0 | 2026-09-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5183386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119987046 | Physically Completed | 27000 | 0 | 2025-08-29 | 2026-09-06
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5188912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120322780 | Ongoing | 27000 | 0 | 2025-04-18
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5190545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123189894 | Ongoing | 27000 | 0 | 2025-06-25
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5196604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116549897 | Ongoing | 27000 | 0 | 2025-04-11
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5199564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124069525 | Ongoing | 27000 | 0 | 2025-04-11
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5207316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126289828 | Ongoing | 27000 | 0 | 2025-07-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5208566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122519717 | Ongoing | 27000 | 0 | 2025-04-18
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5210644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126261166 | Ongoing | 27000 | 0 | 2025-11-05
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5219716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123189635 | Ongoing | 27000 | 0 | 2025-04-29
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5221419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116549152 | Ongoing | 27000 | 0 | 2025-05-16
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5222243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119963474 | Ongoing | 27000 | 0 | 2025-10-27
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5223553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122521181 | Ongoing | 27000 | 0 | 2025-05-16
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5233387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120037105 | Ongoing | 27000 | 0 | 2025-04-11
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5235260 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122543271 | Ongoing | 27000 | 0 | 2025-05-09
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5239004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116549623 | Ongoing | 27000 | 0 | 2025-05-16
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5242334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123034745 | Ongoing | 27000 | 0 | 2025-05-16
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5425028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126379300 | Ongoing | 27000 | 0 | 2026-04-20
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5426378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118741395 | Ongoing | 27000 | 0 | 2025-07-22
MANDSAUR / SITAMAU | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5431047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119938908 | Approved | 27000 | 0 | 2025-03-21
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/5704088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116803708 | Ongoing | 27000 | 0 | 2025-11-05
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6123123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119930997 | Ongoing | 27000 | 0 | 2026-05-16
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6123124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119931121 | Ongoing | 27000 | 0 | 2026-05-16
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6125671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120801737 | Ongoing | 27000 | 0 | 2026-05-16
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6127281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126489845 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6129874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122033485 | Approved | 27000 | 0 | 2026-02-14
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6135817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126448649 | Approved | 27000 | 0 | 2026-02-11
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6138813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116794993 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6139955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122546501 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6141769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124066776 | Ongoing | 27000 | 4200 | 2026-05-16
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6145287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122530377 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6145589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126531317 | Ongoing | 27000 | 2100 | 2026-06-09
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6147333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123032329 | Approved | 27000 | 0 | 2026-02-11
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6150792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126440415 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6152099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120035960 | Ongoing | 27000 | 0 | 2026-05-02
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6153367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120373436 | Ongoing | 27000 | 0 | 2026-07-23
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6154733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125875474 | Approved | 27000 | 0 | 2026-02-14
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6154826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121375552 | Ongoing | 27000 | 0 | 2026-05-16
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6155538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126252447 | Approved | 27000 | 0 | 2026-02-07
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6159276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126254896 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6163645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118489527 | Approved | 27000 | 0 | 2026-02-14
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6164810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120652639 | Ongoing | 27000 | 0 | 2026-09-11
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6167973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116549735 | Ongoing | 27000 | 0 | 2026-05-16
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6170593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116550020 | Approved | 27000 | 0 | 2026-02-07
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6170622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118771230 | Approved | 27000 | 0 | 2026-02-11
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6170739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120329741 | Approved | 27000 | 0 | 2026-02-07
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6174547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117517860 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6174898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126523944 | Approved | 27000 | 0 | 2026-02-07
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6177066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124070161 | Ongoing | 27000 | 0 | 2026-09-15
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6177437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126377480 | Ongoing | 27000 | 0 | 2026-07-16
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6177913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116549312 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6177952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118790187 | Approved | 27000 | 0 | 2026-03-19
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6179171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121373903 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6180242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126494821 | Approved | 27000 | 0 | 2026-03-08
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6180640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120803770 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6181156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127162748 | Ongoing | 27000 | 0 | 2026-05-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6181776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119942063 | Approved | 27000 | 0 | 2026-03-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6181810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124074435 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6183493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118826529 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6184031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126256211 | Ongoing | 27000 | 0 | 2026-09-15
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6184041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118775791 | Ongoing | 27000 | 0 | 2026-05-16
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6185206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116549522 | Approved | 27000 | 0 | 2026-02-07
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6186679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126292178 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6186717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118494189 | Ongoing | 27000 | 0 | 2026-09-20
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6186758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126378095 | Approved | 27000 | 0 | 2026-03-19
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6186900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117514917 | Ongoing | 27000 | 0 | 2026-09-15
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6187111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118771336 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6187620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118841168 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6188368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126538486 | Approved | 27000 | 0 | 2026-03-02
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6188589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126528467 | Ongoing | 27000 | 0 | 2026-09-20
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6191416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126011595 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6191960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118791866 | Ongoing | 27000 | 0 | 2026-07-10
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6193137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118490663 | Approved | 27000 | 0 | 2026-02-07
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6193149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120322543 | Approved | 27000 | 0 | 2026-02-14
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6193721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116549442 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6195462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151353482 | Approved | 27000 | 0 | 2026-03-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6196350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125360073 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6196516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126544601 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6196597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126659779 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6197106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126542755 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6197916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122707635 | Approved | 27000 | 0 | 2026-03-19
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6198080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118633865 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6198193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122511030 | Ongoing | 27000 | 0 | 2026-09-15
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6198453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126520349 | Approved | 27000 | 0 | 2026-02-14
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6200396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130371136 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6202650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123550839 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6202877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118488195 | Approved | 27000 | 0 | 2026-02-14
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6203440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125301943 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6204408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125884208 | Approved | 27000 | 0 | 2026-03-02
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6204540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117268084 | Ongoing | 27000 | 0 | 2026-05-16
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6204749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124067292 | Ongoing | 27000 | 10500 | 2026-06-09
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6205256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126541021 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6205386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116549688 | Ongoing | 27000 | 0 | 2026-06-09
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6205662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119933183 | Ongoing | 27000 | 12600 | 2026-05-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6205784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116549399 | Approved | 27000 | 0 | 2026-03-02
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6205789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122523231 | Ongoing | 27000 | 16800 | 2026-08-04
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6206251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118746013 | Approved | 27000 | 0 | 2026-03-19
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6206314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122509472 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6209127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126247851 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6210869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126547938 | Approved | 27000 | 0 | 2026-02-07
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6210880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118736608 | Ongoing | 27000 | 0 | 2026-05-16
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6211317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118741354 | Approved | 27000 | 0 | 2026-02-11
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6211928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118613195 | Approved | 27000 | 0 | 2026-03-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6212070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118838946 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6212561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126522610 | Approved | 27000 | 0 | 2026-02-14
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6213944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118602153 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6215678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122544286 | Ongoing | 27000 | 0 | 2026-09-15
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6215953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116547512 | Approved | 27000 | 0 | 2026-02-07
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6216596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123902679 | Ongoing | 27000 | 0 | 2026-05-16
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6252497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116550068 | Approved | 27000 | 0 | 2026-02-11
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6255409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118487016 | Approved | 27000 | 0 | 2026-03-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6256102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118784293 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6256335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118771204 | Approved | 27000 | 0 | 2026-02-11
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6256356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118780548 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6256937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118737854 | Ongoing | 27000 | 0 | 2026-10-08
MANDSAUR / SITAMAU | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6257708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120376606 | Ongoing | 27000 | 0 | 2026-10-08
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6257735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118836755 | Approved | 27000 | 0 | 2026-02-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6257955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120329632 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6259151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121386621 | Approved | 27000 | 0 | 2026-03-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6260194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122811178 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6264190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125858448 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6265063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126251177 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6265080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126257860 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6290050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116549984 | Approved | 27000 | 0 | 2026-02-14
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6290051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121367881 | Approved | 27000 | 0 | 2026-03-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6290202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122708028 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6291100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118757623 | Approved | 27000 | 0 | 2026-02-11
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6297434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123555566 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6297612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130371252 | Approved | 27000 | 0 | 2026-03-02
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6297837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118485538 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6298239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126496444 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6306134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119935199 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6306960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118771255 | Approved | 27000 | 0 | 2026-02-11
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6306961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118771317 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6343610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126519348 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1716005057/IF/IAY/6343654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125775520 | Approved | 27000 | 0 | 2026-02-22
MANDSAUR / SITAMAU | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1716005057/RC/22012034846315 — Cement Kancrit Road nirman Nabinur Ke Ghar Se Tulsiram Ke Ghar Ki Or | New | 0 | 0 | 2025-04-14
MANDSAUR / SITAMAU | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1716005057/RC/22012034846413 — Cement Kancrit Road nirman Nabinur Ke Ghar Se Tulsiram Ke Ghar Ki Or | Ongoing | 134000 | 0 | 2025-12-20
MANDSAUR / SITAMAU | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1716005057/RC/22012034852181 — 05 wa vitt mgnrega tulsiram ke gar se ramchandr ke gar ki aur cc road | Ongoing | 74000 | 0 | 2026-02-14
MANDSAUR / SITAMAU | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1716005057/RC/22012034852248 — 05 wa vitt mgnrega ramchandr ke gar se school ki aur cc rod | Ongoing | 72000 | 0 | 2026-03-25
MANDSAUR / SITAMAU | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1716005057/WC/22012035301501 — Dug well recharge pit haveli kui dipakheda | Approved | 25899.46 | 0 | 2025-04-14