## Work List
Exported on: 2026-10-25 18:57:04
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: DIVEL
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
UJJAIN / KHACHAROD | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1718001010/AV/22012034658667 — माध्यमकि विधालय मे बाउन्ड्रीवाल एवं तारफेंसिग कार्य | New | 0 | 0 | 2024-04-14
UJJAIN / KHACHAROD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718001010/DP/1/2011नदन — गुलाबसिह1Ts 07/05/2011नदन फॅलोघान गुलाबसिह नरसिहदिवेल | Deleted | 0 | 0 | 2011-08-05
UJJAIN / KHACHAROD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718001010/DP/1/गटटु रतन — गटटु रतन Ts.95/5/08/2011नंदनॅलोघान गटटु रतन दिवेल | Completed | 191000 | 2196 | 2011-09-02 | 2014-01-10
UJJAIN / KHACHAROD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718001010/DP/1/गुलाबसिह — गुलाबसिह 07/05/2011नदन फॅलोघान गुलाबसिह नरसिहदिवेल | Deleted | 0 | 0 | 2011-08-05
UJJAIN / KHACHAROD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718001010/DP/1/नदनTs 07 — नदनTs 07/5/08/2011 नदन फलोघान गुलाबसिह नरसिह दिवेल | Completed | 191000 | 2196 | 2011-09-02 | 2013-03-10
UJJAIN / KHACHAROD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718001010/DP/1/नदन कुवर — नदन कुवर भुवानTs 96/5/08/2011 दिवेल | Completed | 191000 | 2196 | 2011-09-02 | 2013-03-10
UJJAIN / KHACHAROD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718001010/DP/1/नदन फलोघ — नदन फलोघान शम्‍भु भगवानTs 07/5/8/2011 | Completed | 191000 | 2196 | 2011-09-02 | 2013-03-10
UJJAIN / KHACHAROD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718001010/DP/22012034242515 — वृक्सारोपन प्रा.माध्य.विध्यालय परिसर दिवेल | Deleted | 335000 | 0 | 2017-05-22
UJJAIN / KHACHAROD | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001010/IF/1000002487 — कपिल् धारा कुपनिम्रान | Deleted | 0 | 0 | 2012-08-25
UJJAIN / KHACHAROD | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001010/IF/1000023634 — बलवन्‍त पिता स्‍वरूप कुप निर्माण् | Completed | 256000 | 201308 | 2013-07-01 | 2015-12-25
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1718001010/IF/22012034307404 — Nadep DAPU Bai Sankar divel | Completed | 12200 | 11795 | 2016-12-17 | 2018-07-01
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1718001010/IF/22012034307419 — Nadep bannesingh | Completed | 12200 | 11895 | 2016-12-17 | 2018-07-01
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1718001010/IF/22012034307454 — Nadep Sohan Kuwar | Completed | 12200 | 12017 | 2016-12-17 | 2018-07-01
UJJAIN / KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001010/IF/22012034324020 — kapil dhara kup nirman sayarbai bhairulal GP divel | Completed | 230000 | 49098 | 2017-03-02 | 2019-02-03
UJJAIN / KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001010/IF/22012034324023 — kapil dhara kup nirman sohan bai gordhan GP divel | Completed | 230000 | 159858 | 2017-03-02 | 2020-06-11
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001010/IF/22012034341981 — व़क्षारोपण शासकीय प्रा मा वि परिसर दिवेल | Completed | 335000 | 200526 | 2017-05-22 | 2024-07-10
UJJAIN / KHACHAROD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001010/IF/22012034605972 — kesibai mangu nandan falodyan | Completed | 125439 | 62239 | 2020-09-16 | 2025-06-13
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718001010/IF/22012035473759 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR SOHANBAI GOVARDHAN JI DIVEL | Completed | 25899.46 | 13702.41 | 2025-05-07 | 2026-01-13
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718001010/IF/22012035473819 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR AMBRAM SHIVAJI DIVEL | Completed | 25899.46 | 9787.44 | 2025-05-07 | 2026-01-13
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718001010/IF/22012035473836 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR LAXMAN NANDA JI DIVEL | Completed | 25899.46 | 15659.81 | 2025-05-07 | 2026-01-13
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718001010/IF/22012035473866 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR BHERUDAS JI DIVEL | Completed | 25899.46 | 15660 | 2025-05-08 | 2026-01-13
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718001010/IF/22012035473906 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR AMARSINGH BHUWAN JI DIVEL | Completed | 25899.46 | 15659.88 | 2025-05-07 | 2026-01-13
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718001010/IF/22012035575108 — JGSA 2025 DUG WELL RECHARGE PIT NIRMAN FOR KAILSH MOTILAL JI DIVEL | Physically Completed | 25899.46 | 15092.3 | 2025-06-29 | 2026-04-01
UJJAIN / KHACHAROD | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1718001010/IF/2/अम्‍बु स — अम्‍बु सेवाजी नवीन कुप दिवेल | Completed | 113000 | 201076 | 2011-05-24 | 2013-03-10
UJJAIN / KHACHAROD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001010/IF/9926736100 — rajibai magusingh divel | Completed | 256000 | 252542 | 2014-06-16 | 2016-05-11
UJJAIN / KHACHAROD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001010/IF/9926736418 — navikup nirman bherudas ramdas divel | Completed | 256000 | 270022 | 2014-06-16 | 2016-10-23
UJJAIN / KHACHAROD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001010/IF/9993662631 — नवीन कूप नीर्माण वजेसीह/वालाजी | Deleted | 0 | 0 | 2014-10-02
UJJAIN / KHACHAROD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001010/IF/9993662633 — केटल शेड गोपाल दीवेल | Deleted | 0 | 0 | 2014-10-02
UJJAIN / KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/9993679854 — gaturatan IAY | Completed | 14310 | 13356 | 2015-10-09 | 2016-07-03
UJJAIN / KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/9993679861 — dhanibai nadu IAy | Completed | 14310 | 13356 | 2015-10-09 | 2016-07-03
UJJAIN / KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001010/IF/9993698642 — केटल शेड नीर्माण सवी बाई /रूपाजी दीवेल | Completed | 100000 | 88688.63 | 2016-01-18 | 2016-10-23
UJJAIN / KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001010/IF/9993699061 — केटल शेड हूडीबाई/ऊंकारजी देवेल | Completed | 100000 | 97438.12 | 2016-01-02 | 2016-06-20
UJJAIN / KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001010/IF/9993699070 — केट्ल शेड बनेसिह-रुघनाथ दिवेल | Completed | 100000 | 96984.5 | 2016-01-25 | 2016-10-23
UJJAIN / KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001010/IF/9993699078 — केटल शेड अर्जून सीह/मोती दीवेल | Completed | 100000 | 95311.4 | 2016-01-04 | 2016-06-20
UJJAIN / KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001010/IF/9993699085 — केटल शेड मूरलीदास /मोहनदास दीवेल | Completed | 100000 | 95947.4 | 2016-01-04 | 2016-06-21
UJJAIN / KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001010/IF/9993700354 — केटल शेड मोहन /भगवान दीवेल | Completed | 100000 | 94036.4 | 2016-01-04 | 2016-06-20
UJJAIN / KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001010/IF/9993702585 — केट्ल शेड मोती-रतन | Completed | 100000 | 81076.65 | 2016-01-14 | 2016-06-21
UJJAIN / KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001010/IF/9993702841 — केटल शेड मौती रतन | Deleted | 0 | 0 | 2015-10-07
UJJAIN / KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001010/IF/9993702868 — कैटल सेड मोहन-नागू | Completed | 100000 | 91403.4 | 2016-01-10 | 2016-06-21
UJJAIN / KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001010/IF/9993741386 — Cattle Shed Bherusingh | Deleted | 0 | 0 | 2016-04-01
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/1394850 — Construction of IAY House -IAY REG. NO. MP2109314 | Completed | 15480 | 15660 | 2018-04-04 | 2018-09-20
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/1497991 — Construction of IAY House -IAY REG. NO. MP3493604 | Completed | 15480 | 15660 | 2018-04-04 | 2018-09-27
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/1569345 — Construction of IAY House -IAY REG. NO. MP3776947 | Completed | 15480 | 16704 | 2018-04-04 | 2018-08-15
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/1859279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5709992 | Completed | 15660 | 17748 | 2018-07-03 | 2018-11-12
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/1864048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4906088 | Completed | 15660 | 15660 | 2018-07-03 | 2018-11-01
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/1874337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5662555 | Completed | 15660 | 14616 | 2018-07-03 | 2019-01-05
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/1874344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5710031 | Completed | 15660 | 14616 | 2018-07-03 | 2019-01-10
UJJAIN / KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/229737 — Construction of IAY House -IAY REG. NO. MP1300696 | Completed | 15030 | 15180 | 2017-01-28 | 2018-04-02
UJJAIN / KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/233380 — Construction of IAY House -IAY REG. NO. MP1371885 | Completed | 15030 | 15085 | 2017-01-28 | 2018-03-08
UJJAIN / KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/257070 — Construction of IAY House -IAY REG. NO. MP2174877 | Completed | 15030 | 14589 | 2017-01-28 | 2018-03-13
UJJAIN / KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/263990 — Construction of IAY House -IAY REG. NO. MP3430725 | Completed | 15030 | 14619 | 2017-02-04 | 2018-03-13
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4059277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105851671 | Completed | 18360 | 17544 | 2022-06-15 | 2022-11-04
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4061510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113683825 | Completed | 18360 | 18360 | 2022-06-10 | 2022-11-04
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4065276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113908837 | Completed | 18360 | 17950 | 2022-06-15 | 2023-09-04
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4065282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113911567 | Completed | 18360 | 17544 | 2022-06-12 | 2022-11-04
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4067269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116666208 | Completed | 18360 | 18020 | 2022-06-12 | 2023-04-19
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4067273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116670302 | Completed | 18360 | 18241 | 2022-06-12 | 2023-12-07
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4067299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116680172 | Completed | 18360 | 18241 | 2022-06-12 | 2023-12-12
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4072586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118055168 | Completed | 18360 | 18241 | 2022-06-12 | 2023-12-07
UJJAIN / KHACHAROD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4083899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120770433 | Completed | 18360 | 18343 | 2023-06-06 | 2023-10-16
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4188849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113894681 | Completed | 18360 | 18156 | 2022-08-07 | 2022-11-04
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4191594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116681803 | Completed | 18360 | 18156 | 2022-08-01 | 2022-12-30
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4386535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122755491 | Completed | 18360 | 18988 | 2023-02-28 | 2023-12-12
UJJAIN / KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4609611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124944959 | Completed | 21870 | 21627 | 2024-10-10 | 2025-02-13
UJJAIN / KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4626032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126884986 | Completed | 23490 | 22014 | 2025-01-22 | 2025-12-29
UJJAIN / KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4742554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113479177 | Completed | 21870 | 6804 | 2024-11-12 | 2025-12-29
UJJAIN / KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4776314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125849803 | Completed | 21870 | 21870 | 2024-11-12 | 2025-03-18
UJJAIN / KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4776319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125850446 | Completed | 23490 | 20223 | 2025-01-22 | 2025-12-29
UJJAIN / KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/4781788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127932019 | Completed | 23490 | 20430 | 2024-11-14 | 2025-12-29
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5182266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126799272 | Completed | 23490 | 23229 | 2025-04-11 | 2025-12-29
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5214012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113473981 | Completed | 23490 | 21924 | 2025-04-11 | 2025-12-29
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5230374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113888950 | Completed | 23490 | 23229 | 2025-04-11 | 2025-12-29
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5246650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116675710 | Completed | 23490 | 22185 | 2025-04-11 | 2025-12-29
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5246756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116684868 | Completed | 23490 | 23229 | 2025-04-11 | 2025-12-29
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5257056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125852207 | Completed | 23490 | 21402 | 2025-05-08 | 2025-12-29
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5258489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106839281 | Completed | 23490 | 23229 | 2025-05-08 | 2025-10-17
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5262994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127749618 | Physically Completed | 23490 | 21663 | 2025-04-11 | 2026-04-16
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5279208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126884512 | Completed | 23490 | 21924 | 2025-04-11 | 2025-12-29
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5279321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127977608 | Completed | 23490 | 22707 | 2025-04-11 | 2025-12-29
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5296022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126885532 | Completed | 23490 | 21924 | 2025-04-11 | 2025-12-29
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5315050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113897321 | Completed | 23490 | 22707 | 2025-04-11 | 2025-12-29
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5334015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127500209 | Completed | 23490 | 21924 | 2025-04-11 | 2025-12-29
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5337016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116895830 | Completed | 23490 | 23229 | 2025-04-11 | 2025-12-29
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5426109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125848058 | Physically Completed | 23490 | 20097 | 2025-05-08 | 2026-04-16
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5427597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125844716 | Completed | 23490 | 23229 | 2025-06-01 | 2026-04-16
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5459784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116895871 | Completed | 23490 | 19053 | 2025-05-08 | 2026-04-04
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/5710899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117629888 | Completed | 23490 | 23229 | 2025-07-25 | 2026-04-04
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6102210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127107352 | Approved | 23490 | 0 | 2026-02-19
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6102440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127974300 | Approved | 23490 | 0 | 2026-02-11
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6102623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126888863 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6102737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120770741 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6103348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116678836 | Ongoing | 23490 | 21924 | 2026-04-18
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6103387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127169438 | Ongoing | 23490 | 21924 | 2026-04-18
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6103765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127501173 | Ongoing | 23490 | 22470 | 2026-04-18
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6104111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118175601 | Ongoing | 23490 | 3654 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6104221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127936140 | Ongoing | 23490 | 18270 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6104222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127936576 | Ongoing | 23490 | 7308 | 2026-06-12
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6104496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127244582 | Ongoing | 23490 | 21924 | 2026-04-18
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6104689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117631241 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6104722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127943581 | Ongoing | 23490 | 18270 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6104746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127100328 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6104747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127102760 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6104779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106843348 | Ongoing | 23490 | 18270 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6104780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106843488 | Ongoing | 23490 | 18270 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6105277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113683905 | Ongoing | 23490 | 18270 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6105488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127746832 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6105635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118055263 | Approved | 23490 | 0 | 2026-02-11
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6105834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113888864 | Ongoing | 23490 | 21924 | 2026-04-18
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6106796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125845436 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6106863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127102193 | Ongoing | 23490 | 23229 | 2026-04-18
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6107330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126808841 | Ongoing | 23490 | 22470 | 2026-04-18
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6107534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117272497 | Approved | 23490 | 0 | 2026-02-11
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6107569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106848423 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6107764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124502235 | Ongoing | 23490 | 7308 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6108247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106843206 | Ongoing | 23490 | 21924 | 2026-04-18
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6108323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116685053 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6108967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127978026 | Ongoing | 23490 | 18270 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6109092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106850896 | Ongoing | 23490 | 18270 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6110588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113688665 | Ongoing | 23490 | 18270 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6112108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116683308 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6112289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127194949 | Ongoing | 23490 | 10962 | 2026-05-19
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6112832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126800504 | Approved | 23490 | 0 | 2026-02-11
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6113420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106843094 | Ongoing | 23490 | 23229 | 2026-04-18
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6113869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118055345 | Approved | 23490 | 0 | 2026-02-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6114634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118734465 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6115061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113477582 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6115194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121575679 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6115198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113472475 | Ongoing | 23490 | 14616 | 2026-05-19
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6115208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124506526 | Ongoing | 23490 | 21924 | 2026-04-18
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/6243506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106842950 | Approved | 23490 | 0 | 2026-02-11
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/729061 — Construction of IAY House -IAY REG. NO. MP1939737 | Completed | 15030 | 15660 | 2018-04-04 | 2018-08-25
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/769619 — Construction of IAY House -IAY REG. NO. MP3416770 | Completed | 15030 | 14616 | 2018-04-04 | 2018-08-17
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/772846 — Construction of IAY House -IAY REG. NO. MP3565777 | Completed | 15030 | 14790 | 2018-04-04 | 2018-09-20
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/776468 — Construction of IAY House -IAY REG. NO. MP3762876 | Completed | 17100 | 2088 | 2018-05-29 | 2025-01-24
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/776674 — Construction of IAY House -IAY REG. NO. MP3775099 | Completed | 15030 | 15660 | 2018-04-04 | 2018-09-20
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/776837 — Construction of IAY House -IAY REG. NO. MP3783283 | Completed | 15030 | 15636 | 2018-03-04 | 2018-10-24
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/777018 — Construction of IAY House -IAY REG. NO. MP3795682 | Completed | 15030 | 15480 | 2017-07-05 | 2018-03-08
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/967985 — Construction of IAY House -IAY REG. NO. MP3497859 | Completed | 15480 | 15480 | 2017-06-17 | 2018-04-02
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/974080 — Construction of IAY House -IAY REG. NO. MP3650199 | Completed | 15480 | 15480 | 2017-06-17 | 2018-04-02
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001010/IF/IAY/987664 — Construction of IAY House -IAY REG. NO. MP3551685 | Completed | 15480 | 15516 | 2017-07-05 | 2018-05-04
UJJAIN / KHACHAROD | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718001010/LD/1/शान्तिधा — शान्तिधाम निर्माण दिवेल ४.१९ | Completed | 419000 | 387163.7 | 2012-05-09 | 2015-02-02
UJJAIN / KHACHAROD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1718001010/LD/22012034294321 — खेल मैैदान प्रााथमिक माध्‍यमिक विघालय DIVEL | Deleted | 474000 | 0 | 2016-12-03
UJJAIN / KHACHAROD | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718001010/LD/3799382612 — ग्रामीन किडगन | Deleted | 0 | 0 | 2012-08-25
UJJAIN / KHACHAROD | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718001010/LD/जैटोफा रतनजोत — जैटोफा रतनजोत वक्षारोपड दिवेल | Completed | 60800 | 24073 | 2008-04-25 | 2008-08-11
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1718001010/PG/9425891126 — खेल मैैदान प्रााथमिक माध्‍यमिक विघालय DIVEL | Completed | 474000 | 468731.25 | 2016-12-03 | 2019-07-17
UJJAIN / KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718001010/RC/22012034156138 — आंतरीक मागं | Completed | 488000 | 466374 | 2013-06-24 | 2014-02-10
UJJAIN / KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718001010/RC/22012034205457 — आतरिकमार्ग मुरमीकरणनालीनिर्माण पेमाघासी केमकानसेहन | Completed | 498000 | 431673.1 | 2014-02-17 | 2016-06-20
UJJAIN / KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034211767 — Manrega+pp Divel | Completed | 83000 | 72000 | 2014-03-05 | 2015-12-22
UJJAIN / KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034211774 — मनरेगा पंच परमेश्वर सीसी काम दीवल | Completed | 83000 | 82503 | 2014-03-05 | 2014-07-25
UJJAIN / KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718001010/RC/22012034211817 — Divel Sudur marg | Completed | 1463000 | 1314886.8 | 2014-03-05 | 2017-03-30
UJJAIN / KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034212308 — Manrega+Panch Par.3.24 DIVEL | Completed | 124000 | 85986 | 2014-03-13 | 2015-06-01
UJJAIN / KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718001010/RC/22012034223015 — खेतसडक दिवेलसेकेसरियाकाकडतक दिवेल | Completed | 1462000 | 1227388.58 | 2014-06-26 | 2017-03-30
UJJAIN / KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718001010/RC/22012034265309 — सुदूर मार्ग दीवेल से बरखेडा की ओर | Deleted | 0 | 0 | 2014-10-02
UJJAIN / KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718001010/RC/22012034265311 — सुदूर मार्ग दीवेल से लेकोडीया कांकड की ओर | Deleted | 0 | 0 | 2014-10-02
UJJAIN / KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034287711 — पुष्कर के मकान से माताजी कि ओर पंचपरमेश्वर (7 th) कीस्त | Completed | 71000 | 70653 | 2015-11-09 | 2016-06-20
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034302244 — manrega pachparmesver | Deleted | 0 | 0 | 2016-04-01
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034302247 — manrega pachparmesver | Deleted | 0 | 0 | 2016-04-01
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034329650 — पंचपरमेश्‍वर प्रधानमंृृी रोड से रूपा जी घर तक | Completed | 28762 | 28056 | 2017-03-06 | 2018-02-24
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034335532 — CC road | Deleted | 0 | 0 | 2017-04-01
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034349232 — cc road- rughnathsingh ke ghar se hukumsingh ke ghar ki or | Completed | 793100000 | 7224 | 2017-08-14 | 2018-02-24
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034350587 — भवर सीह के घर से रुघनाथ सीह के घर कि ओर cc रोड दिवेल | Completed | 5198 | 5160 | 2017-08-23 | 2018-02-24
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034361761 — हुकुम सिंह के घर से भेरूलाल प्रजापत के घर की ओर | Completed | 11515 | 11352 | 2017-09-28 | 2018-02-24
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034361993 — sitla mata mandir se chandodiya road ki or | Completed | 95460 | 9288 | 2017-09-29 | 2018-02-24
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034386964 — देवनारायण स्‍थान से माताजी मदिर की और सीसी रोड | Completed | 22238 | 21924 | 2018-04-03 | 2018-08-07
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034386965 — रूगनाथ सिह के घर से भेरूसिह के घर की और | Completed | 6391 | 6264 | 2018-04-04 | 2018-08-07
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034386966 — बालुसिह के घर से दीपक गोरधन के घर की और सीसीरोड | Completed | 2484 | 2088 | 2018-04-04 | 2018-08-07
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034386967 — शम्‍भुलाल स्‍वरूप के घर से रमेश स्‍वरूप के घर की और सीसी रोड | Completed | 8694 | 7308 | 2018-04-20 | 2019-02-27
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034387336 — उदयसिह के घर से ि‍शिवजीमदिर कीऔर सीसी रोड | Completed | 18713 | 17748 | 2018-09-10 | 2018-12-21
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034387337 — परमानंद के घर से बापुजी के घर की और सीसी रोड | Completed | 6831 | 5220 | 2018-09-26 | 2018-12-21
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034387338 — माना केशुराम केघर से अमरसिह भीमा जी के घर की और | Completed | 5865 | 5220 | 2018-09-26 | 2018-12-21
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034433853 — देवस्‍थान पर चबुतरा | Completed | 25668 | 22968 | 2018-12-31 | 2019-08-13
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034433854 — भेरूलाल के घर से बालु के घर की ओरसीसीरोड | Completed | 5681 | 5244 | 2019-01-14 | 2019-08-13
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034435003 — दिपक के घर से दयाराम के घर की और सीसी रोड | Completed | 4140 | 3144 | 2019-01-14 | 2019-08-13
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034435004 — चाभुजा मदिर चाैराहा सीसी | Completed | 6624 | 6600 | 2019-01-14 | 2019-08-13
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034435005 — मागु रूपा के घर की और सीसी रोड | Completed | 13438 | 13434 | 2019-01-14 | 2019-08-13
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034435006 — गोपाल रायसिह के घर से भारत के घर की और | Completed | 5055 | 5040 | 2019-01-14 | 2019-08-13
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034435007 — पंचायत भवन के सामने चौराहा सीसी | Completed | 66240 | 65832 | 2019-01-14 | 2020-01-21
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034435008 — अमरसिह के घर से विनोद चौधरी के घर की और सीसी रोड | Completed | 9705 | 9630 | 2019-02-25 | 2019-10-31
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034438880 — CC road | Deleted | 0 | 0 | 2019-01-27
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034441648 — Cc road | Deleted | 0 | 0 | 2019-01-26
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034470763 — Ccrod Ramesh mahatar ke ghar ki or | Deleted | 0 | 0 | 2019-07-12
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034470764 — सीसी रोड प्रधानमंत्री रोड से मांगू दला के घर तक | Deleted | 0 | 0 | 2019-07-12
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034476518 — pradhanmantrirod se jiwan balu ke ghar tak | Completed | 37800 | 36784 | 2019-09-12 | 2020-07-06
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034476548 — rupa salam ke ghar se ramesh mehtar ke ghar tak | Completed | 41850 | 41184 | 2019-10-10 | 2020-01-21
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034476556 — balwan ke ghar se mangu -dalla ke ghar tak | Deleted | 37200 | 0 | 2019-08-15
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034481841 — Amru ke ghar se muralidas ke ghar ki our cc road | Completed | 32550 | 31680 | 2019-12-10 | 2020-07-06
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034481842 — Chandodiya raste par cc road | Completed | 12600 | 11616 | 2019-11-14 | 2020-07-06
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034514036 — Cc road | Deleted | 0 | 0 | 2019-04-26
UJJAIN / KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034524463 — Amaru mehatra ke ghar se mualidas ke ghar ki our cc road | Deleted | 32550 | 0 | 2020-04-01
UJJAIN / KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034524841 — माना चौधरी के घर से धर्मशाला तक सीसी रोड़ | Completed | 39525 | 38760 | 2020-06-30 | 2020-09-11
UJJAIN / KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034536111 — PM road se mana chudhary ke ghar ki our cc road | Completed | 26190 | 27360 | 2020-09-04 | 2021-10-28
UJJAIN / KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034536112 — PM road se sitaram ke ghar ki our cc road | Closed | 29100 | 0 | 2020-04-02
UJJAIN / KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034553905 — पीएम रोड से सीताराम के घर की ओर | Completed | 49509 | 49350 | 2021-01-02 | 2021-10-28
UJJAIN / KHACHAROD | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034611682 — Cc Road balu puna ke ghar se bheru ji ki or | Completed | 35432 | 34272 | 2022-04-29 | 2022-06-02
UJJAIN / KHACHAROD | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034621576 — nali niraman balu poona ke ghar se bheru ji ki or | Completed | 14821 | 14688 | 2022-12-07 | 2025-08-29
UJJAIN / KHACHAROD | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034623367 — nali niraman balavant ke ghar se chandodiya raste par | Completed | 39000 | 38995 | 2022-12-30 | 2025-08-29
UJJAIN / KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034645161 — Nali Nirman jivan Ke Ghar se shantilal Ke Ghar ki or | Completed | 37000 | 35150 | 2023-09-13 | 2025-08-29
UJJAIN / KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034663096 — CC ROD BALU KE GHAR SE MURLIDASH KE GHAR KI OR | Deleted | 0 | 0 | 2023-06-08
UJJAIN / KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034663378 — Cc Road Balu ke Ghar se murlidas ke Ghar ki or | Completed | 49332 | 48882 | 2023-10-07 | 2026-03-04
UJJAIN / KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/22012034671563 — nali niraman radeshyam ke ghar se muralidas ke ghar ki or | Completed | 21896 | 21463 | 2024-02-23 | 2025-08-29
UJJAIN / KHACHAROD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1718001010/RC/22012034831044 — nali niraman umravsingh ke ghar se panchayt bhawn ki or | Completed | 48055 | 47509.13 | 2024-12-11 | 2025-08-29
UJJAIN / KHACHAROD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1718001010/RC/22012034833489 — cc road panchayat bhwan se vinod chodhary ke ghar ki or | Completed | 73060 | 65714 | 2025-01-30 | 2026-03-04
UJJAIN / KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/72 — दितीयकिशत मनरेगा पचपरमेश्‍वर दिवल | Completed | 110000 | 43500 | 2014-03-03 | 2015-12-25
UJJAIN / KHACHAROD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/7/पंच परमे — पंच परमेशवर+मनरेगा | Completed | 110000 | 100084 | 2012-07-05 | 2015-02-02
UJJAIN / KHACHAROD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001010/RC/8/विधायक — विधायक+ मनरेगा 1.35 | Completed | 135000 | 107969 | 2012-07-01 | 2015-02-02
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001010/RS/22012034359457 — SOCHALAY NIRMAN MOHAN BHAGWAN | Deleted | 12000 | 0 | 2017-07-17
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001010/RS/22012034359953 — SOCHALAY NIRMAN MOHANLAL BAGWAN | Completed | 12000 | 11734 | 2017-07-24 | 2018-05-03
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001010/RS/22012034359962 — SOCHALAY NIRMAN MUNNA BHIMA | Completed | 12000 | 11734 | 2017-07-24 | 2018-05-03
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001010/RS/22012034359966 — SOCHALAY NIRMAN GOWARDAN DOLA | Completed | 12000 | 11734 | 2017-07-24 | 2018-05-03
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001010/RS/22012034359967 — SOCHALAY NIRMAN DULA NARSINGH | Completed | 12000 | 11734 | 2017-07-24 | 2018-05-03
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001010/RS/22012034359969 — SOCHALAY NIRMAN NARPAT FATTU JI | Completed | 12000 | 11734 | 2017-07-24 | 2018-05-03
UJJAIN / KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718001010/RS/22012034496180 — 15 वित्‍त अशंदान स्वच्छता परिसर स्कूल के पास | Completed | 48000 | 43320 | 2020-10-07 | 2021-10-23
UJJAIN / KHACHAROD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001010/WC/22012034382075 — चेकडेम | Deleted | 0 | 0 | 2018-04-16
UJJAIN / KHACHAROD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001010/WC/22012034383825 — Cheakdem | Deleted | 0 | 0 | 2017-10-12
UJJAIN / KHACHAROD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001010/WC/22012034383826 — Cheakdem Naleper | Deleted | 0 | 0 | 2017-10-02
UJJAIN / KHACHAROD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001010/WC/22012034383827 — Cheakdem Nale ke pass | Deleted | 0 | 0 | 2017-10-02
UJJAIN / KHACHAROD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001010/WC/22012034383828 — Nala Traching | Deleted | 0 | 0 | 2017-10-02
UJJAIN / KHACHAROD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001010/WC/22012034383829 — Nala tracjhing | Deleted | 0 | 0 | 2017-10-25
UJJAIN / KHACHAROD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001010/WC/22012034383830 — Nala tracjhing godaghata | Completed | 67000 | 70812 | 2019-03-10 | 2019-07-26
UJJAIN / KHACHAROD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1718001010/WC/22012034441578 — nala trench1 | Completed | 92295 | 86301 | 2019-02-25 | 2019-07-26
UJJAIN / KHACHAROD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001010/WC/22012034469719 — new talab nirman arogyadevi mandir ke pas | Deleted | 0 | 0 | 2019-06-22
UJJAIN / KHACHAROD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001010/WC/22012034514765 — cheka dem divel | Completed | 994855.03 | 952856 | 2020-01-15 | 2021-09-19
UJJAIN / KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718001010/WC/22012034552555 — रिचार्ज पोंड दिवेल | Completed | 332572.21 | 274740 | 2020-05-26 | 2021-10-28
UJJAIN / KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1718001010/WC/22012034558335 — Samudayik coop nirman shamshan ghat Ke paas dive | Completed | 464568.96 | 391747 | 2020-10-07 | 2022-09-25
UJJAIN / KHACHAROD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001010/WC/22012034580503 — Check Dem nirman Kansiya ke pas divel | Deleted | 0 | 0 | 2019-11-19
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1718001010/WC/22012034698897 — Nalatrinching sawaji ratanji ke khet ke pass gram divel | Closed | 107913.48 | 0 | 2021-04-02
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001010/WC/22012034746624 — सोख्ता गड्ढा निर्माण देव जी के मंदिर के पास | Completed | 14467.3 | 10422 | 2021-09-24 | 2022-03-05
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001010/WC/22012034746626 — सोख्ता गड्ढा निर्माण स्कूल के पीछे हेड पंप पर | Completed | 14467.3 | 9264 | 2021-10-08 | 2022-03-05
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001010/WC/22012034746640 — सोख्ता गड्ढा निर्माण कान्हा जी की घर के पास | Completed | 14467.3 | 11580 | 2021-10-08 | 2022-03-05
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001010/WC/22012034754601 — Nala tracing Balu puna khet ke pass | Completed | 266086.38 | 199755 | 2021-06-17 | 2021-10-28
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001010/WC/22012034754603 — Nala tracing Balu puna khet ke pass | Deleted | 0 | 0 | 2021-04-02
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001010/WC/22012034836208 — Shokta ghadda Bheruji ke paas Divel | Deleted | 0 | 0 | 2021-05-14
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001010/WC/22012034836210 — Shokta ghadda pani ki tanki ke pass divel | Deleted | 0 | 0 | 2021-05-14
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001010/WC/22012034897325 — Nala Traching Shambhu mistri ke khet ke pass | Deleted | 0 | 0 | 2022-01-05
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718001010/WC/22012034897389 — Nala Traching Shambhu mistri ke khet ke pass | Completed | 221480.22 | 171170 | 2022-02-01 | 2022-05-02
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718001010/WC/22012034925282 — Talab Jirnodawar gram abdi ke pass Diwel | Completed | 136000 | 132822 | 2022-03-16 | 2022-07-30
UJJAIN / KHACHAROD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001010/WC/22012035004057 — Nala teaching Nirman bhandya mein gram divel | Completed | 225413.74 | 134962 | 2022-10-23 | 2025-05-25
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001010/WC/22012035268069 — Samudayik richarge pit Divel | Completed | 25899.46 | 14616 | 2025-05-05 | 2026-01-26
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718001010/WC/22012035295434 — Amrit sarowar Divel | Physically Completed | 2409130.46 | 2159451.26 | 2025-05-05 | 2026-05-18
UJJAIN / KHACHAROD | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001010/WC/3नवीन कुप — नवीन कुप निर्माण कुवर जी भुवान जी दिवेल | Completed | 165000 | 148761 | 2009-12-15 | 2011-01-25
UJJAIN / KHACHAROD | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001010/WC/3/सामुदायि — सामुदायिक कूप निर्माण दिवेल ४.२२ | Completed | 422000 | 269031.8 | 2012-05-01 | 2015-02-02
UJJAIN / KHACHAROD | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001010/WC/ नवीन कुप — नवीन कुप निर्माण लक्ष्‍मण पिता नंदा जी दिवेल | Completed | 165000 | 126791.85 | 2009-02-19 | 2010-06-07
UJJAIN / KHACHAROD | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718001010/WC/नवीन कुप — नवीन कुप निर्माण शम्‍भु भगवान दिवेल | Completed | 165000 | 136616.99 | 2009-12-15 | 2011-02-03
UJJAIN / KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718001127/RC/22012034211801 — Khet Sadak Divel | Completed | 1462000 | 3504 | 2014-03-05 | 2023-04-11
UJJAIN / KHACHAROD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001/IF/22012034594584 — मनरेगा निजी खेत मे फलोधान श्री भारत पिता रतनजी ग्राम दिवेल | Completed | 166808 | 62994 | 2020-08-14 | 2025-12-28
UJJAIN / KHACHAROD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001/IF/22012034601226 — मनरेगा निजी खेत मे फलौधान श्री जगदीश पिता शंकर लाल ग्राम दिवेल | Physically Completed | 166808 | 73484 | 2020-09-30 | 2026-06-13
UJJAIN / KHACHAROD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001/IF/22012034603370 — मनरेगा निजी खेत मे फलौधान श्री कूवर पिता भुवानजी ग्राम दिवेल | Physically Completed | 218692 | 91403 | 2020-09-30 | 2026-06-13